## Matters Affecting Opinion
Financial Year: 2023/2024
Annexure: Matters Affecting Audit Report
Audit Action Plan Status: All
Implementation Status: Not Yet Started¦In Progress¦Completed¦Agreed Findings Addressed
Line Item | Finding | Amount | Root Cause | Nature of Findings | Repeat Finding | No. of Years Repeated | Responsible Person | Due Date Dev | Due Date Imp | Action Plan | Management Approval Comments | CFO Approval Comments | IA Assurance Comments | AC Approval Comments | Council Approved Date | Council Resolution No. | Action Plan Status | Implementation Progress % | Implementation Status | Completed Date | Agreed Findings | IA Review Date | IA Review Comments | NT/PT Recommendation Considered (AAP) | COGTA Recommendation Considered (AAP) | SALGA Recommendation Considered (AAP) | NT/PT Recommendation Considered (IP) | COGTA Recommendation Considered (IP) | SALGA Recommendation Considered (IP) | Addressed Current Year | Implementation Progress Comment Considered
Suppliers’ tax affairs not in order | 1.Contracts were awarded to suppliers whose tax matters were not declared to be in order by SARS | 402 500 | No Comment | Non-compliance with applicable legislation | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Missing or incomplete information | 2. A contractor awarded a quotation is registered in the class of construction works thatthe projects does not relates to. |  | No Comment | Non-compliance with applicable legislation | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Missing or incomplete information | 3. Selection of service providers from panel without following Competitive bidding process | 1 643 150 | Internal control deficiency | Non-compliance with applicable legislation | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Reasonable steps were not taken to prevent Irregular Expenditure. |  | There was no timely implementation of action plans to ensure that non-compliance instances dueto same root cause do not re-occur.No adequate implementation of proper controls to ensure that laws and regulations applicable tothe municipality is complied with. | Non-compliance with applicable legislation | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Contracts were awarded to suppliers whose tax matters were not declared to be in order by SARS. | 402 500 | The evaluation committee did not conduct a tax verification exercise before/prior to communicating the award decision. | Internal control deficiency | Yes | 1 | [10 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Other Important Matters
Financial Year: 2023/2024
Annexure: Matters Management Audit Report
Audit Action Plan Status: All
Implementation Status: Not Yet Started¦In Progress¦Completed¦Agreed Findings Addressed
Line Item | Finding | Amount | Root Cause | Nature of Findings | Repeat Finding | No. of Years Repeated | Responsible Person | Due Date Dev | Due Date Imp | Action Plan | Management Approval Comments | CFO Approval Comments | IA Assurance Comments | AC Approval Comments | Council Approved Date | Council Resolution No. | Action Plan Status | Implementation Progress % | Implementation Status | Completed Date | Agreed Findings | IA Review Date | IA Review Comments | NT/PT Recommendation Considered (AAP) | COGTA Recommendation Considered (AAP) | SALGA Recommendation Considered (AAP) | NT/PT Recommendation Considered (IP) | COGTA Recommendation Considered (IP) | SALGA Recommendation Considered (IP) | Addressed Current Year | Implementation Progress Comment Considered
| Quotations were awarded to suppliers whose tax matters were not declared to be in order by SARS. | 404 950 | The evaluation committee did not conduct a tax verification exercise before/prior to communicating the award decision. | Non-compliance with applicable legislation | Yes | 0 | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Selection of service providers from panel without following quotation process | 723 500 | There are no proper controls in relation to the awarding of work/selection of service provers from panel. The SCM unit is not involved in ensuring that the process is done fairly according to the SCM requirements, and that quotation process is applied consistently on a fair rotational basis when selecting suppliers for awarding of work. In some instances, only one supplier is selected and awarded work without invitation of at least 3 different suppliers from panel as it is practical to do so. Furthermore, the memo approved by the municipal manager for selection of just one supplier does not specify the reasons from deviating from the normal quotation process. | Non-compliance with applicable legislation | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Competitive bidding not invited | Selection of service providers from panel without following quotation process | 723 500 | There are no proper controls in relation to the awarding of work/selection of service provers from panel. The SCM unit is not involved in ensuring that the process is done fairly according to the SCM requirements, and that quotation process is applied consistently on a fair rotational basis when selecting suppliers for awarding of work. In some instances, only one supplier is selected and awarded work without invitation of at least 3 different suppliers from panel as it is practical to do so. Furthermore, the memo approved by the municipal manager for selection of just one supplier does not specify the reasons from deviating from the normal quotation process. | Non-compliance with applicable legislation | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Internal control deficiencies on the panel procedure/policy and listing for panel rotation | 0 | Management does not keep a register to track rotation of work to suppliers on panel to ensure fairness on procurement process followed through panel.There are no proper controls in relation to the awarding of work/selection of service provers from panel. | Internal control deficiency | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Rotation of work to panel suppliers is not visible | 562 500 | Management does not keep a register to track rotation of work to suppliers on panel to ensure fairness on procurement process followed through panel.There are no proper controls in relation to the awarding of work/selection of service provers from panel.The SCM unit is not involved in ensuring that the process is done fairly according to the SCM requirements, and that quotation process is applied consistently on a fair rotational basis when selecting suppliers for awarding of work.In some instances, only one supplier is selected and awarded work without invitation of at least 3 different suppliers from panel as it is practical to do so. Furthermore, the memo approved by the municipal manager for selection of just one supplier does not specify the reasons from deviating from the normal quotation process. | Internal control deficiency | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Declarations of interest not submitted by suppliers | Suppliers in the same panel with the same directors | 363 000 | The officials assessing the bidders’ files supporting evidence received from the bidders, including the evaluation committee was not able to detect the companies with the same directors and the same shareholders bidding for the same contract. | Internal control deficiency | No | [11 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Suppliers’ tax affairs not in order | Control deficiency on panel suppliers included in panel with tax not in order | 0 | The evaluation committee did not conduct a tax verification exercise to ensure that the taxes of the successful bidder are in order. | Internal control deficiency | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Incomplete disclosures required by GRAP 3 | 8 639 385 | GRAP 11 was previously not being applied that fits the contract scenario that municipality has in regards with INEP. Municipality previously applied GRAP 109 agent principle requirements, however as per the INEP accounting guide, the municipality is not an agent in this regard.No considerations made in terms of GRAP 3 disclosure requirements in relation to changes made from prior year in this regard. | Internal control deficiency | No |  | Mbuso Mtshali | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Repeat of a disclosure note -INEP construction contract in note 26 28. | 0 | No proper review of duplicates in terms of reported information and furthermore this is a new application of GRAP 11. | GRAP non-compliance | No |  | Mbuso Mtshali | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Irregular expenditure | Diff between amount written off on AFS Irregular Expenditure vs MPAC report | 435 998 | The recovered amount was incorrectly accounted twice on the note and write off included not accurately agreed to the MPAC report. | MFMA s123, s124 & s125 disclosures | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Irregular Expenditure disclosed is not complete | 1 004 843 | There was irregular expenditure identified by the third party which it was not disclosed by the municipality.Management did not adequately review and monitor compliance with applicable laws and regulations relating to disclosure of IE as required by MFMA to ensure compliance and completeness of disclosure note. | Internal control deficiency | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cash flow statement | Cashflow statement presentation calculation of cash generated from operations | 1 545 333 | The above is due to non-cash items being correctly adjusted from surplus, however non-cash items that does not impact changes in working capital being also reflected.The detailed management calculations of Cash flow statement not being adequately reviewed. | Internal control deficiency | No |  | Sbonelo Ngidi | 31-Jan-2025 | 30-Jun-2025 | The matter was resolved during the audit however it will be monitored during the preparation of 2024/2025 AFS to ensure that there is no finding related to this to avoid the repeat finding. | [6 empty] | Under Development |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cash flow statement | Cashflow statement transfers and subsidies | 0 | The review of the financial statements was not able to identify that the presentation of the cashflow statement is not in line with GRAP 2. | GRAP non-compliance | No |  | Sbonelo Ngidi | 31-Jan-2025 | 30-Jun-2025 | The matter will be finalized during the interim AFS where one of the lines in the cashflow GRAP template will be modified to be transfer and subsidies as per specimen to be in line with AG recommendation. | [6 empty] | Under Development |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cash flow statement | Cashflow statement presentation | 0 | The above is as a result of internal control deficiency. | Internal control deficiency | No |  | Sbonelo Ngidi | 31-Jan-2025 | 30-Jun-2025 | The matter was resolved during the audit, and it will be checked during the 2024/2025 interim AFS to avoid the repeat finding. | [6 empty] | Under Development |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Property, plant and equipment | Assets that could not be verified | 458 270 | Lack in adequate timeliness in identifying and addressing asset verification discrepancies identified. This is due to the verification performed by consultants completed on 02 July 24 and the consolidated report was compiled and submitted to management after year-end. | Internal control deficiency | Yes | 1 | Noluthando Dlamuka | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Omission of Work-in-Progress (WIP) Projects in Verification Report. | 0 | This omission has resulted in an internal control deficiency. | Internal control deficiency | No |  | Noluthando Dlamuka | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Commitments | Commitment schedule not complete | 2 662 918 | Oversight from review processes to ensure that all active contracts at year end are included in the commitments register. | MFMA s123, s124 & s125 disclosures | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Contingent liabilities | Understatement of Legal Liability in the Annual Financial Statements | 1 061 723 | The control process for recognizing and estimating legal liabilities was inadequate. There was no proper review or reconciling of the details as per the legal report to the contingent liabilities note. | Internal control deficiency | Yes | 2 | Thabani Mlaba | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Non-Compliance with Acting Appointment Policy | 0 | The organization did not effectively enforce its policy on acting appointments, resulting in employee 0164 serving as acting director for 17 months, which exceeds the maximum allowable period of 12 months. | Internal control deficiency | No | 0 | Granny Mthembu | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Reported information not reliable | The achievement reported does not include % as per the progress report | 0 | Management did not ensure that reported information for non-achieved target includes the percentage included on progress report to be aligned with the approved targets and measurement criteria as set out in the SDBIP.Further, did not use the progress reports to clearly report the actual percentage of progress made. | Internal control deficiency | No |  | Leeanne Naidoo | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Reported information not reliable | Indicators not well defined (Immaterial indicators) | 0 | The SDBIP/TID does not include in detail the explanation of the nature number of outputs produced over the specified time period for easy understanding. | Internal control deficiency | No |  | Leeanne Naidoo | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Underlying records/planning documents not submitted for auditing | No comparison between current and prior year performance | 0 | Management did not adequately validate the classification and comparability of performance indicators in the Annual Performance Report (APR) against prior year indicators. | Internal control deficiency | No |  | Leeanne Naidoo | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Reported information not reliable | Inconsistencies on reporting of indicator status | 0 | There was no proper alignment between initial targets and revised targets for some indicators, leading to inaccurate reporting. Management revised targets after Q1 due to project cessation and funding withdrawal, but included reasons for underachievement at year-end, despite meeting the revised targets. This misalignment resulted in misleading performance reporting. | Internal control deficiency | No |  | Leeanne Naidoo | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Reported information not reliable | Indicators not achieved in prior year not planned for in current year. | 0 | Management when adjusting the SDBIP did not include the projects carried over from prior year that were only finalized in current year to allow for progress to be tracked and reported on in the current year until it is achieved. | Internal control deficiency | No |  | Leeanne Naidoo | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Employee-related costs | Leave Accrued closing balance days differences noted between June payslip and leave report. | 0 | The internal control deficiency identified is the lack of proper reconciliation and validation processes for leave data.This discrepancy arises because the municipality used a leave system report that incorrectly includes 2/less days of leave that were accrued for July 2024, as a result, the report does not accurately reflect the leave days accrued for the year ending June 30, 2024. This was due to a leave system issue in June and the report could not be generated at the time, however no adjustments of July days were made when calculation of Accrued leave was done. | Internal control deficiency | No |  | Granny Mthembu | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Provisions | Leave Accrued Misstatements in calculation done. | 74 638 | Lack of comprehensive procedures for maintaining and updating employee records in the leave stabilization report.This omission suggests insufficient oversight in ensuring that all employees' leave data is accurately captured and reported. Additionally, the leave system operates on a January to December cycle, while the financial statements are prepared on a July to June basis. This misalignment could further contribute to discrepancies in the leave days balances, leading to inaccuracies in financial reporting and liability calculations. | Internal control deficiency | No |  | Granny Mthembu | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Provisions | Omission of employee from leave stabilization report | 3 751 | Lack of comprehensive procedures for maintaining and updating employee records in the leave stabilization report. This omission suggests that there is insufficient oversight in ensuring all employees' leave data is accurately captured and reported, which can lead to inaccuracies in financial reporting and liability calculations. | Internal control deficiency | No |  | Granny Mthembu | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cash and cash equivalents | Cash book vs bank statements differences from prior years not cleared on CY bank recon | 0 | The courses of differences are the payments and deposit that are on the system but are not on the bank statement, some are duplicates amount that never reflected on the bank statement. Majority of these items are coming from prior years and are not being followed up on and resolved by management, similar issue was raised in the prior year. | Internal control deficiency | Yes | 1 | Chris Khoza | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cash and cash equivalents | Differences noted on Interest received from Investments. |  | Adequate reviews of investment registers for figures disclosed in current year AFS’s was not done accurately to ensure accuracy of amounts recorded in AFS. Furthermore, the bank confirmations received for interest are not agreed to the investment register. | Internal control deficiency | No |  | Chris Khoza | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Current tax payable | Issues noted on Vat payable Account | 0 | Management did not ensure that amounts are correctly cleared on the vat account to ensure that vat statement at year end agrees to amount recorded as vat payable/receivable at year end. Management did not ensure that they follow up with national Treasury with regards to the INEP issue on vat to get clarity based on new guidelines and be able to adjust accordingly based on NT consultation done. Furthermore, ensure correct application of INEP guide and SARS requirements. | Internal control deficiency | Yes | 1 | Khethukuthula Buthelezi | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Current tax payable | Misalignment of VAT Accounting in Expenditure for Contracted services and Revenue Construction contracts | 1 544 855 | The municipality has not been implementing the recording vat om the INEP transactions in according with the National treasury guides as they require further clarity on the guide. | GRAP non-compliance | No |  | Khethukuthula Buthelezi, Mbuso Mtshali | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Grant received in prior year omitted in corresponding figures for 2023/24. | 10 000 000 | This omission was caused by the fact that in the current year the INEP grant is not included in going concern for the current year and therefore have been missed in the comparative figure when reviews were done.Inadequate comparison of balances for corresponding figures disclosed in current year AFS’s against prior year closing balance as per 2023 AFS’s to ensure completeness of disclosure note. | GRAP non-compliance | No |  | Sbonelo Ngidi, Mbuso Mtshali | 31-Jan-2025 | 30-Jun-2025 | The finding was resolved during the Audit hence no action is required to resolve the matter. Moving forward more review will be done to avoid the repeat finding. | [6 empty] | Under Development |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Interest on overdue accounts for bursaries not disclosed as FEW. | 67 171 | There was no proper monitoring of this account to ensure effective management and no overdue account. This deficiency has led to the accumulation of interest charges. | Internal control deficiency | No |  | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Contracted services | The amount of invoice recorded inclusive of vat-Contracted services | 350 000 | The recording of this transaction was not properly reviewed against the supporting evidence for accuracy. | Internal control deficiency | Yes | 2 | Khethukuthula Buthelezi | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Incorrect calculation of points on evaluation of suppliers | 0 | There was inadequate review on the evaluation performed by BEC in order to identify errors. | Internal control deficiency | Yes | 2 | Ntombikayise Priscilla Nkabinde | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Internal control deficiency-Tariffs policy not clear | 0 | Rates policy not clear how exemption is applied on properties with market values above R60 000. | Internal control deficiency | No |  | Chris Khoza | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | No consultancy reduction plan in place | 0 | The lack of documentation indicates inadequate follow-through on issues and strategies discussed in meetings to reduce reliance on consultants. | MFMA non-compliance | No |  | Xolani Hlekwane | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Councilors not trained on the professionalization framework |  | Councillors were not trained on National framework towards the professionalization of the public sector. | Internal control deficiency | No |  | Granny Mthembu | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Internal control deficiencies noted on the Indigent policy | 0 | The indigent policy does not cover the circumstances that must be met by an applicant/household to be accepted for free basic service relating to electricity by Eskom paid by Ndwedwe. | Internal control deficiency | No |  | Chris Khoza | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other | Internal control deficiencies noted on the Indigent register | 0 | 1. The indigent register does not indicate the status of the application, whether accepted/rejected and furthermore it does not cover comments for all applicants.2. The indigent register include inaccurate ID numbers of applicants, and this has resulted in these ID numbers being unverifiable from home affairs national population register-Refer to Annexure A table A for the list.3. The indigent register include applications approved that were done by people declared dead on home affairs national population register at the time of application- Refer to Annexure A table B for the list. | Internal control deficiency | No |  | Chris Khoza | 31-Jan-2025 | 30-Jun-2025 | [7 empty] | Not Yet Started |  | Not Yet Started |  | Not Addressed |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A