## Technical
NDWEDWE LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
Period: 2015/2016 Financial Year
Department: Technical Services
KPI NO | National KPA | Project/ Programme Description | IDP Strategic Objective | Output | Key Performance Indicator | Annual Target | September 2015 |  |  |  | Budget Allocation | Vote No | Source of Funding
[7 empty] | Target Q1 | Actual | Variance | Corrective Measure
171 | Basic Service Delivery and Infrastructure Development | Blading of Access Roads in all Wards. | To facilitate the provision of sustainable infrastructure delivery | Maintenance of Access Road.. | Number of Access Road kilometres maintained by date | 190 km by 30 June 2016 (Completion of blading maintenance of 5 x 2.0km access road per ward for a total of 19 wards) | Appointment of Service Provider to provide with grader operators by the end of September 2015. |  |  |  | 2000000 |  | Municipality
172 |  | Blading of Sportfields in all Wards. |  | Maintenance of Sportfield | Number of Sportsfields maintained by date | 75 Sportsfields by 30 June 2016 | 15 Maintenace done by 30 September 2015 |  |  |  | 300000 |  | Municipality
173 |  | Nkalangwe Access Road |  | Construction of Gravel Road | Number of Gravel Road Kilometres constructed by date | 4.1 Kilometres by 30 June 2016 | Appointment of Construction Company and establishment of contractor on site by 30 September 2015 |  |  |  | 6790000 |  | MIG
174 |  | Mdanda |  | Construction of Gravel Road | Number of Gravel Road Kilometres constructed by date | 2016-06-30 | Appointment of Construction Company and establishment of contractor on site by 30 September 2015 |  |  |  | 3573900 |  | municipality
175 |  | Diphini Access Road |  | Construction of Gravel Road | Number of Gravel Road Kilometres constructed by date | 2016-06-30 | Appointment of Construction Company and establishment of contractor on site by 30 September 2015 |  |  |  | 3260400 |  | Municipality
176 |  | Gems School Access Road |  | Construction of Gravel Road | Number of Gravel Road Kilometres constructed by date | 3.0 Kilometres by 30 June 2015 | Appointment of Construction Company and establishment of contractor on site by 30 September 2015 |  |  |  | 3605200 |  | MIG
177 |  | Mary Grey Sportscentre |  | Construction of Sportscentre | % Construction by date | 100% Construction by 30 June 2016 | (1) Appointment of Service Provider (2) Foundation - 25% by 30 September 2015 |  |  |  | R2984047.66 |  | Municipality
178 |  | Bulk line from Sonkombo substation to Bhamshela Mall |  | Facilitation and reporting on project | Number of monthly reports submitted to Infrastructure Committee by date | 10 Reports submitted by 30 June 2016 | 3 Reports submitted by 30 September 2015 |  |  |  | 5600000 |  | Municipality
179 |  | Electrification in Ward 07 |  | Hlalakahle Electrification Project | Appointment of consultant for design and appointment of contractor by date | 2016-06-30 | (1) Appointment of Electrical Engineering Consultant (2) Completion of Pre-marketing by 30 September 2015 . |  |  |  | 2000000 |  | Energy
180 |  | Electrification in Ward 10 |  | Hlomatshe Electrification Project | Appointment of consultant for design and appointment of contractor by date | 2016-06-30 | (1) Appointment of Electrical Engineering Consultant (2) Completion of Pre-marketing by 30 September 2014 . |  |  |  | 6000000 |  | Energy
181 |  | Project Management |  | Establishment of the PMU Unit. | Number of Positions in Unit filled by date | 4 posts by 30 June 2016 | HR Processes complete |  |  |  | 1300000 |  | MIG
182 |  | Nhlangwini Sportsfield |  | Construction of a Sportsfield and Change Rooms | % Construction by date | 100% Construction by 30 June 2016 | Appointment of Contractor by 30 September 2015 |  |  |  | 5623241 |  | muniiciplaity
183 |  | EPWP Program | Job Creation | Employment of local community members for identified period | Number of community members employed | 85 local labour for 12 months till end of December 2015 | Appointment of local labour and arrangment of Protective Clothes for them |  |  |  | R 2 000 000.00 |  | Public Works and Municipality
184 |  | Municipal Infrastructure Maintenance | To facilitate the provision of sustainable infrastructure delivery | Electricity Infrastructure | Submission of Draft 2016 - 2017 Maintenance Plan to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | Municipality
185 |  |  |  |  | 2015-2016 Implementation Plan | Number of Quarterly Reports presented by date | 4 Quarterly Reports presented by 30 June 2016 |  |  |  | 4th Quarter Report presented by 30 June 2016
186 |  |  |  | Hoti-Culture | Number of Expenditure Reports submitted to Portfolio Committee by date | 12 Reports by 30 June 2016 | 3 Reports submitted by 30 September 2015 |  |  |  | 1500000 |  | Municipality
187 |  |  |  | Buildings | Number of Expenditure Reports submitted to Portfolio Committee by date | 5 Reports by 30 June 2016 | 3 Reports submitted by 30 September 2015 |  |  |  | 1300000 |  | Municipality
188 |  | Waste Management |  | Collection of waste | Number of collections per month | 14 Collections monthly until 30 June 2016 | 42 Collections by 30 September 2015 |  |  |  | 100000 |  | Municipality
189 |  | Community Hall |  | Magwaza CDC Hall | % Construction by date | 100% Construction by 30 June 2016 | Appointment of Contractor by 30 September 2015 |  |  |  | 4200000 |  | Municipality
190 |  | Ward 12 |  | Multipurpose Centre | % Construction by date | 100% Construction by 30 June 2016 | Appointment of Contractor by 30 September 2015 |  |  |  | 5000000 |  | Municipality
191 |  | Plant Aquire |  | Roller |  | 2016-06-30 | Advert |  |  |  | 1500000 |  | Municipality
192 |  | Plant Hire |  | Water Cutier and excavator |  | 2016-06-30 | Advert |  |  |  | 2000000 |  | Municipality
193 |  | Skills Transfer |  | Constructive skills transfer by Service Provider | All Service Providers appointed | 2016-06-30 | All Service Providers appointed |  |  |  | 0 |  | N/A
194 |  | Compliance Reports |  |  | Reports by Service Provider on SLA Compliance | 12 Monthly Reports on compliance by service provider by 30 June 2015 | 3 Reports presented by 30 September 2014 |  |  |  | 0 |  | N/A
195 |  | Compliance Reports |  |  | % Compliance of Service Provider to SLA | 100% Compliance by 30 June 2016 | 100% Compliance |  |  |  | 0 |  | N/A
196 |  | Assets Transfer |  | Assets Transfer | Submission to BTO on Assets to be transferred | 7 days after issue of practical completion certificate to contractor | Submission to BTO on Assets to be transferred 7 days after issue of practical completion certificate to contractor |  |  |  | 0 |  | N/A
197 |  | Project Documentation |  | Project Documentation | % up to date of Project File Index | 100% up tp date till 30 June 2016 | 100% up to date of Project File Index weekly |  |  |  | 0 |  | N/A
198 |  | EPWP Program |  | EPWP Policy | Submission of Draft EPWP Policy to standing committee for adoption | 2016-05-30 | N/A |  |  |  | 0 |  | N/A

## Corporate_Services
NDWEDWE LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
Period: 2015/2016 Financial Year
Department: Corporate Services
KPI NO | National KPA | Project/ Programme Description | IDP Strategic Objective | Output | Key Performance Indicator | Annual Target | September 2015 |  |  |  | Budget Allocation | Vote No | Source of Funding
[7 empty] | Target Q1 | Actual | Variance | Corrective Measure
56 | Institutional Development and Transformation | Filling of all funded vacant posts | To facilitate institutional transformation and organisational development | Filling of funded vancant posts | Number of posts filled by date | 13 Posts filled by 30 June 2016 | 12 Posts filled by 30 September 2015 |  |  |  | 1500000 |  | Municipality
57 |  | Municipal Policies Management |  | Reviewed Policies | Number of Draft Policies submitted to Manco for Council Adoption by date | 5 Policies by 30 May 2016 | Review Collective Assessment |  |  |  | 0 |  | N/A
58 |  |  |  | Policy Register | % Up to date of Policy Register by date | 100% up to date policy register by 30 June 2016 | 100% up to date register by 30 September 2015 |  |  |  | 0 |  | N/A
59 |  | Municipal Organogram |  | Organogram reviewed | Submission of Draft Organogram to MANCO for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
60 |  | Staff Management |  | Electronic Register | Number of Electronic Register Operation Report presented to MANCO by date | 12 Reports presented by 30 June 2015 | 3 Report presented by 30 September 2015 |  |  |  | 0 |  | N/A
61 |  | Procedure Manual |  | Orientation/induction manual Reviewed | Submission of Draft Manual to MANCO for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
62 |  | Workplace Skills Plan |  | 2016 - 2017 Workplace Skills Plan | Submission of Draft WSP to MANCO for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
63 |  |  |  | 2015-2016 WSP Implementation | Number of Quarterly Reports presented to Manco for Council adoption by date | 4 Quarterly Reports presented by 30 June 2016 | 1st Quarter Report presented by 30 September 2015 |  |  |  | 900000 |  | N/A
64 |  | Service Charter |  | Municipal Service Charter | Submission of Draft Service Charter to MANCO for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
65 |  | Bursary Scheme |  | Bursary Scheme Implementation | Number of beneficiaries supported by date | 19 Beneficiaries by 30 June 2016 | 19 Beneficiaries supported throughout the financial year |  |  |  | 0 |  | N/A
66 |  | Community Skills Support Programme |  | Internship Programme | Number of interns enrolled in Programme by date | 10 Interns enrolled by 30 June 2015 | 10 Interns enrolled throughout the year |  |  |  | 0 |  | N/A
67 |  | Council Support |  | Effective Support of Council | Timespan from submission of Agenda to Council Meeting | Council agenda prepared and dispatched 7 days before the date of the meeting | Council agenda prepared and dispatched 7 days before the date of the meeting |  |  |  | 0 |  | N/A
68 |  |  |  | Agenda for Committee Members | Timespan for preparing of Draft Agenda | 7 days prior to meeting | 7 days prior to meeting |  |  |  | 0 |  | N/A
69 |  |  |  |  | Timespan for Distribution of Agenda | Chairperson : 7 Days prior to meeting | 7 Days prior to meeting |  |  |  | 0 |  | N/A
70 | [5 empty] | Members : Within a day after Chairperson approval by signature | Within a day after Chairperson approval by signature |  |  |  | 0 |  | N/A
71 |  |  |  | Minutes for Council and Committees | Timespan for the submission of minutes after meeting | 7 Days after the seating of meeting | 7 Days after the seating of meeting |  |  |  | 0 |  | N/A
72 |  | Council Resolution Implementation |  | Implementation of Council Resolutions by Municipality | Number of monthly implementation reports presented to Manco for Council adoption by date | 12 Monthly Reports by 30 June 2015 | 3 Reports presented by 30 September 2014 |  |  |  | 0 |  | N/A
73 |  | Annual schedule of meetings in Municipality |  | 2016 - 2017 Annual Calendar of Council, EXCO and Portfolio Committee meetings schedule | Submission of Draft Calendar to Manco for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
74 |  | Council Administration Support |  | Compliance to Council Standards in terms of submissions | % Compliance by date | 100% Compliance by 30 June 2016 | 100% Compliance by 31 September 2015 |  |  |  | 0 |  | N/A
75 |  | Labour Relations |  | Local Labour Forum | Number of Quarterly Forum Meetings held by date | 4 Quarterly Forum Meetings held by 30 June 2016 | 1st Quarter Meeting held by 30 September 2015 |  |  |  | 0 |  | N/A
76 |  | OHS |  | OHS Policy Compliance | % Compliance by date | 100% Compliance by 30 June 2016 | 100% Compliance by 30 September 2015 |  |  |  | 50000 |  | N/A
77 |  |  |  | OHS Policy Implementation | Number of monthly implementation reports presented to Manco for Council adoption by date | 12 Monthly Reports by 30 June 2016 | 3 Reports presented by 30 September 2015 |  |  |  | 0 |  | N/A
78 |  | Fleet Management |  | Fleet Management Reporting | Number of monthly implementation reports presented to Manco for Council adoption by date | 12 Monthly Reports by 30 June 2016 | 3 Reports presented by 30 September 2015 |  |  |  | 300000 |  | N/A
79 |  | Employee Wellness Programme |  | EWP Implementation | Number of EWP activities performed by date | 4 Activities by 30 June 2016 | 1 Activity by 30 September 2015 |  |  |  | 200000 |  | N/A
80 |  | Records Management |  | Records Register | % Up to date of Register by date | 100% up to date register by 30 June 2016 | 100% up to date register by 30 September 2015 |  |  |  | 0 |  | N/A
81 |  |  |  | Filing System | % Up to date of System by date | 100% up to date system by 30 June 2016 | 100% up to date system by 30 September 2015 |  |  |  | 0 |  | N/A
82 |  |  |  | Records Control Schedule | Submission of Draft Records Control Schedule to Manco for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
83 |  | Disaster Management |  | IT Disastster Recovery Implementation Plan | Number of monthly implementation reports presented to Manco for Council adoption by date ( daily back-ups and tests conduted) | 12 Monthly Reports by 30 June 2016 | 3 Reports presented by 30 September 2015 |  |  |  | 0 |  | N/A
84 |  | Municipal Website |  | Revamp of Municipal Website | New Municipal Webiste live by date | 2016-06-30 | Revised Website live by 30 September 2015 |  |  |  | 400000 |  | Municipality
85 |  | IT help desk |  | Efficient and functional IT Helpdesk | Turnaround time from request to assistance | 24 hours from written request | 24 hours from written request |  |  |  | 0 |  | N/A
86 |  | Risk and Legal |  | Legal Services | Number of Quarterly Reports presented to Manco for Council adoption by date | 4 Quarterly Reports presented by 30 June 2016 | 1st Quarter Report presented by 30 September 2015 |  |  |  | 529000 |  | Municipality
87 |  | Access Control Policy Compliance |  | Access Control Policy Compliance | Draft Access Control Policy submission to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
89 |  | IT Security Policy |  | IT Security Policy Compiance | Draft IT Security Policy submission to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
90 |  | Comlpiance |  |  | % Compliance by date | 100% Compliance by 30 June 2016 | 100% Compliance by 31 September 2015 |  |  |  | 0 |  | N/A
91 |  | ICT Steering Committee |  | ICT Steering Committee | Functional ICT Steering Committee by date | 4 Quarterly ICT Steering Committee meeting by 30 June 2016 | 1st Quarter ICT Steering Committee meeting by 30 September 2015 |  |  |  | 0 |  | N/A
92 |  | Performance Agreements |  | Submission of Performance Agreements for all Contracted Managers | Signed Perfomance Agreements submitted by date | 2015-07-31 | (1) Sending of Memo to all Departmental Managers and (2) Filing of all received Perfomance Agreements |  |  |  | 0 |  | N/A
92 |  | Assesments Coordination |  | Assessments Coordination | Quarterly Assessment Reports submitted to MANCO | 3 Quarterly Assessment reports submitted to MANCO | N/A |  |  |  | 0 |  | N/A
94 |  | Access to Information |  | Promotion of Access to information Act | Quarterly Implementation reports submitted to MANCO | 4 Quarterly Implementation reports submitted by 30 June 2016 | (1) Translation (2) 1st Quarter Report on functioning |  |  |  | 0 |  | N/A
95 |  | Staff excellence Awards |  | Staff Excellence Awards ('15 - '16 Perfomance) | Ndwedwe Municipality Staff excellence awards event | 2016-06-30 | N/A |  |  |  | 100000 |  | N/A
96 |  | Team Building |  | Team building session for senior management | Date of session | 2016-02-28 | N/A |  |  |  | 50000 |  | n/A

## Office_of_the_MM
NDWEDWE LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
Period: 2015/2016 Financial Year
Department: Office of the Municipal Manager
KPI NO | National KPA | Project/ Programme Description | IDP Strategic Objective | Output | Key Performance Indicator | Annual Target | September 2015 |  |  |  | Budget Allocation | Vote No | Source of Funding
[7 empty] | Target Q1 | Actual | Variance | Corrective Measure
01 | Good Governance and Public Participation | Media Management | Promote good governance and public participation | Municipal Media Slots on radio | Number of media slots conducted by date | 56 media slots conducted by 30 June 2016 | 14 Media slots conducted by September 2015 |  |  |  | 200000 |  | Municipality
02 |  |  |  | Municipal Newsletter | Number of Quartly Municipal newsletter | 4 Quartely Municipal newsletters published by 30 June 2016 | 1st Quarter Minicipal newsletter published by 30 September 2014 |  |  |  | 100000 |  | N/A
03 |  |  |  | Media Response | Timespan for response to media requests by date | Within stipulated times | Within stipulated times |  |  |  | 0 |  | N/A
04 |  | HIV/ Aids |  | HIV/ Aids Strategy | Submission of Draft Strategy to Manco for Council Adoption by date | 2015-05-30 | Draft HIV and Aids Strategy developed by 30 September 2015 |  |  |  | 200000 |  | Municipality
05 |  |  |  | HIV/ Aids Awareness | Number of awareness campaigns held by date | 4 Campaigns by 30 June 2016 | N/A
06 |  |  |  | Aids Commitees | Number of Quarterly Seatings by date | 4 Quarterly Seatings by 30 June 2016 | 1st Quarter Meetings held by 30 September 2015
|  | IDP |  | IDP Preparation for 2016/ 2017 | Number of IDP Forums and Mayoral Izimbizo hosted | Resolution adopting IDP for 2016/ 2017 | Process Plan adopted adopted by Council |  |  |  | 340000
|  | IDP Printing |  | IDP Printing for 2016/ 2017 | Number of copies printed for the Community | 500 Copies printed for the community | N/A |  |  |  | 160000
07 |  | Community Participation |  | Izimbizo | Number of Izimbizo held by date | 2 Speakers Izimbizo hosted by 30 June 2014. | N/A |  |  |  | R500 000.00 |  | Municipality
08 |  |  |  | Training of Ward Commitees | Number of training sessions held by date | 2 Session by 30 June 2016 | N/A |  |  |  | R600 000.00
09 |  |  |  | Ward Operations | Number of Ward Meetings held by date | 12 Meetings held by 30 June 2016 | 3 Meetings held by 30 September 2015 |  |  |  | N/A
10 |  |  |  | 2016 - 2017 IDP Consultation Meetings (IDP forum) | Number of consultation meetings held by date | 3 IDP Consultation Meetings hosted by 30 June 2016 | N/A |  |  |  | 500000 |  | Municipality
11 |  | OPMS |  | 2016 - 2017 IDP/Budget and PMS Adoption | Submission of IDP/Budget and PMS to MANCO for Council Adoption by date | 2016-05-30 | Preparation of the Process Plan done by 31 August 2016
12 |  | Inter-governmental Relations |  | Participate in IGR Forum meetings | Number of Forum meetings participated in by date | 4 Quarterly Forum meetings by 30 June 2016 | 1st Quarter Meetings held by 30 September 2015 |  |  |  | 0 |  | N/A
13 |  | Moral Regeneration |  | Reed Dance | Participation of Municipality in event by date | 2015-09-30 | Participation in Reed dance by Ndwedwe Maidens |  |  |  | 100000 |  | Municipality
14 |  | Outreach programme (Tertaiary institutions) |  | Career Guidance | Number of schools visited and event held by date | 10 schools benefiting from outreach programme and 1 event held by 30 June 2016 | N/A |  |  |  | 100000 |  | Municipality
15 |  | Youth Development |  | Leadership Training | Number of youths that benefit from training by date | 20 Youth in Business benefiting from Programme by 31 March 2016 | N/A |  |  |  | 30000 |  | Municipality
16 |  | OPMS |  | OPMS Policy | Submission of Draft Policy to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0
17 |  |  |  | Strategic planning 2016/2017 | Date of Session | 1 Strategic planning session by 30 june 2016 | N/A |  |  |  | 500000
18 |  |  |  | 2016/ 2017 SDBIP | Submission of Draft SDBIP to Manco for Council Adoption by date | 28 days after approval of budget by council | N/A |  |  |  | 0
19 |  |  |  | Mid Term SDBIP | Submission of Draft adjusted SDBIP to Manco for Council Adoption by date | 2016-02-28 | N/A |  |  |  | 0 |  | N/A
20 |  |  |  | Performance Reporting | Submission of Quarterly Performance Reports to Manco for Council Adoption by date | 4 Quarterly Reports submitted by 30 June 2016 | 1st Quarter Reports submitted by 30 September 2015 |  |  |  | 0
21 |  |  |  | Annual Report | Submission of Draft Annual Report to Manco for Council Adoption by date | 2016-03-31 | Submission of Performance Information to AG by 31 September 2015 |  |  |  | 150000 |  | Municipality
22 |  |  |  | Oversight Report | Submission of Draft Oversight Report to Manco for Council Adoption by date | 2016-03-31 | N/A
23 |  | IPMS |  | Section 56/57 Performance | Submission of Sect. 56/57 Performance Agreements by date | 2015-07-30 | Submission of Performance Agreements by 30 July 2015 |  |  |  | 0 |  | N/A
24 |  |  |  |  | Assessment of Sect. 56/57 Performance by date | 2 Assessments held by 14 July 2015 (Note: 14 days after the end of the financial year is noted as within the year) | N/A |  |  |  | 0
25 |  |  |  |  | Personal Development Plans submitted to HR by date | 2015-07-30 | Submission of signed PDP as part of PA Package to HR |  |  |  | 0
26 |  | Community Participation |  | Public Participation Strategy | Submission of Draft Strategy to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
27 |  |  |  | Ward Committee Elections | Time span for Ward Committee Election from reported vacancy | Elections held within 90 days from reported vacancy | Elections held with 90 days from reported vacancy |  |  |  | 0
28 |  |  |  | Ward Operations | No of Montly Ward Operations Reported presented to MANCO, Speaker and COGTA | 12 Ward Operations Reports presented by 30 June 2016 | 3 Ward Operations Reports presented |  |  |  | 0
29 |  |  |  | Public Participation Policy | Submission of Draft Public ParticipationPolicy to MANCO for Council Adoption | 2016-05-30 | Not applicable |  |  |  | 0
30 |  |  |  |  | No of Quarterly Reports on the implementation of Public Participation Policy | 4 Quarterly Reports submitted to MANCO for Council noting by 30 June 2016 | 1st Quarter Public Participation Policy Implementation Report submitted |  |  |  | 0
31 |  | Audit Compliance |  | 2015 - 2016 Audit Plan | Submission of 2015 - 2016 Audit Plan to Manco for AC and Council Adoption by date | 2016-06-30 | N/A |  |  |  | 0 |  | N/A
32 |  |  |  | 2014 - 2015 Audit Plan Implementation | Submission of Implementation Reports to AC and Council by date | 4 Quarterly Reports submitted by 30 June 2016 | 1st Quarter Reports submitted by 30 September 2015 |  |  |  | 850000 |  | Municipality
33 |  |  |  | MPAC Seating coordination | Number of MPAC Seatings coordinated by date | 5 Seatings coordinated by 30 June 2016 | 1 Seating held |  |  |  | 0
34 |  |  |  | Audit Opinion | Number of Quarterly submissions of AG Dashboard by date | 4 Quarterly submissions by 30 June 2016 | 1st Quarter Dashboard Reports submitted by 30 September 2015 |  |  |  | 0 |  | N/A
35 |  | Sports and Recreation |  | SALGA Games | Coordination of SALGA Games by date | 2015-12-01 | N/A |  |  |  | 600000
36 |  | Porverty Alleviation and eradication |  | Operation Sukuma Sakhe | Number of meetings held by date | 24 Meetings by 30 June 2016 | 6 Meetings by 30 September 2015 |  |  |  | 100000 |  | N/A
37 |  | National Calendar |  | Youth Day | Municipal Event held by date | 2015-06-16 | N/A |  |  |  | 600000 |  | Municipality
38 |  |  |  | World Aids Day | Municipal Event held by date | 2015-12-01 | N/A | [5 empty] | Municipality
39 |  |  |  | Umkhosi welembe | Municipal Event held by date | 2015-09-01 | Umkhosi Welembe Event | [5 empty] | Municipality
40 |  |  |  | SONA - State of the Nation Address | Municipal Event held by date | 2016-02-01 | N/A | [5 empty] | Municipality
41 |  |  |  | Womens day | Municipal Event held by date | 2015-08-01 | Womens day Event | [5 empty] | Municipality
42 |  |  |  | Senior Citizens Day | Municipal Event held by date | 2015-10-01 | N/A | [5 empty] | Municipality
43 |  | Corporate Identity Policy |  | Corporate Identity Policy | Submission of a Draft ULM Corporate Identity Policy to Standing Committee for Council Adoption | 42277 | Research on Municipal Corporate Identity Policy Framework, 1st Draft Compiled and submission of Final Draft to Manco for Council Adoption by 30 Sept 2015 |  |  |  | R30 000.00 |  | N/A
44 |  | SDBIP Publication |  | Publication of SDBIP for public viewing | SDBIP made public within allocated timespan after signing by Mayor | 14 Days after signing by Mayor | Not Applicable |  |  |  | 0 |  | N/A
45 |  | Annual Performance Report |  | Annual Performance Report | Publication of 2014 - 2015 APR on Municipal Media Platrforms | 42261 | Publication of 2014 - 2015 APR on Municipal Media Platrforms |  |  |  | 0 |  | N/A
46 |  | Annual Report |  | Annual Report | Publication of 2014 - 2015 AR on Municipal Media Platrforms | 42474 | Not Applicable |  |  |  | 0 |  | N/A
47 |  | Protocol Pictures |  | Office appeal and Protocol Pictures | All Management Offices to have RSA Flags and RSA Leadership Pictyres | 42551 | Not Applicable |  |  |  | R50.000.00 |  | N/A
48 |  | Municipal Bill boards |  | Municipal Billboards | Review of billboard content | 4 Quarterly Billboards Review by 30 June 2016 | 1st Quarter Billboard Review Report |  |  |  | 0 |  | N/A
49 |  | Municipal Newsletter |  | Municipal Newspaper | Frequency of newspaper publishing and distribution | 4 Quarterly editions by 30 June 2016 | 1st Quarter Newspaper Edition produced and distributed |  |  |  | 0 |  | N/A
50 |  | Marketing and Communication Strategy |  | Marketing and Communications Strategy | Submission of Draft Marketing and Communications Strategy to Standing Committee for Council Approval | 42277 | Research on Strategy Framework, 1st Draft Compiled and submission of Final Draft to Manco for Council Adoption by 30 Sept 2015 |  |  |  | R100,000.00 |  | Municipality
51 |  | Communication Forum |  | Communicatons Forum | Established forums and frequency of seatings | 11 Monthly seatings by 30 June 2016 | (1) Established Forums and (2) 2 Monthly seatings |  |  |  | 0 |  | N/A
52 |  | Municipal Website |  | Municipal Website | Frequency of content updates on the website | Within 2 days of submission of new content | Within 2 days of submission of new content |  |  |  | 0 |  | N/A
53 |  | Media Briefing |  | Media Briefings | Timespan for organising media briefings from internal request | Within 24 hours from noting/ event/ stipulated time | Within 24 hours from noting/event/ stipulated time |  |  |  | 0 |  | N/A
54 |  | Events Policy |  | Events Policy and Procedure Manual | Submission of a Draft Events Policy and Procedure Manual | 42520 | Research on Municipal Events Policy and Procedure Manual Framework |  |  |  | 0 |  | N/A
55 |  | Promotion Material |  | Promotions Material | Promotional Material acquired incl. Podium | 42551 | Not Applicable |  |  |  | 0 |  | N/A

## Finance
NDWEDWE LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
Period: 2015/2016 Financial Year
Department: Finance
KPI NO | National KPA | Project/ Programme Description | IDP Strategic Objective | Output | Key Performance Indicator | Annual Target | September 2015 |  |  |  | Budget Allocation | Vote No | Source of Funding
[7 empty] | Target Q1 | Actual | Variance | Corrective
97 | Financial Viability | Procurement Plan | Ensure Municipal Financial Viability | 2015 - 2016 Procurement Plan implementation | Number of Implementation Reports presented to MANCO for Council adoption by date | 12 Reports presented by 30 June 2016 | 3 Report presented by 30 September 2015 |  |  |  | 0 |  | Municipality
98 |  |  |  | 2016 - 2017 Procurement Plan | Submission of Draft 2016 - 2017 Procurement Plan to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
99 |  | Debt recovery and Revenue enhancement | Revenue Enhancement | Reduction of Debtors book | % Reduciton of Debtors book by date | 20% Reduction by 30 June 2016 | 20% Reduction by 30 September 2015 |  |  |  | 0 |  | N/A
100 |  |  |  | Revenue Enhancement Strategy Implementation | Number of Implementation Reports presented to MANCO for Council adoption by date | 4 Reports presented by 30 June 2016 | 1 Report presented by 30 September 2015 |  |  |  | 0 |  | N/A
101 |  |  |  | Revenue enhancement and debt management policy | % Compliance to Revenue Enhancement and Debt Management Policy by date | 100% Compliance by 30 June 2016 | 100% Compliance by 31 September 2015 |  |  |  | 0 |  | N/A
102 |  | Governance | Ensure Municipal Financial Viability | Fixed Assets Register (GRAP17) | Number of Fixed Assets Maintenance Reports presented to Manco by date | 12 Reports by 30 June 2016 | 3 Report presented by 30 September 2015 |  |  |  | 400000 |  | FMG
103 |  |  |  | Financial Reporting | Number of Financial Reports Produced by date | 12 S71 and S66 Reports produced within 10 days after month ends | 3 S71 and S66 Reports produced |  |  |  | 150000 |  | Municipality
104 | [5 empty] | 4 S52 Quarterly Reports Produced Within 15 days after the end of Quarter | 1 S52 Quarterly Reports Produced
105 | [5 empty] | 1 Mid year/ Adjustment Budget Review. S72 Submission by 28 February 2016 | Not applicable
106 |  |  |  | Cash Flow Management | Ratio of monthly expenditure to cash available | 1 ; 3 | 1 ; 3 |  |  |  | 0 |  | N/A
107 |  |  |  | Budget for 2015/ 2016 | Submission of Draft Budget to Manco for Council adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
108 |  |  |  | Mid Year Budget Adjustment | Submission of Draft Adjusted Budget to Manco for Council adoption by date | 2016-02-28 | N/A |  |  |  | 0 |  | N/A
109 |  |  |  | Finance Policy Review | Submission of Budget Related Policies to Manco for Council Adoption by date | 2016-05-30 | N/A |  |  |  | 0 |  | N/A
110 |  | Revenue Collection |  | Collection Rate | % Collection of billed customers | 60% by 30 June 2016 | 60% by 30 September 2015 |  |  |  | 0 |  | N/A
111 |  | General Evaluation Roll |  | Supplementary valuation roll | Supplementary valuation roll presented to Manco for Council Adoption by date | 2016-06-30 | N/A |  |  |  | 500000 |  | Municipality
112 |  | Governance |  | Compliance to SCM Regulations | Number of state officials appoiunted through bid process by date | 0 staff appointed by 30 June 2016 | 0 by 30 September 2015 |  |  |  | 0 |  | N/A
113 |  |  |  | Avoid irregular,wasteful, fruitless and unauthorised expenditure | % of Expenditure incured by date | 0% by 30 June 2015 | 0% by 30 September 2014 |  |  |  | 0 |  | N/A
114 |  |  |  | MFMA Compliance | % Compliance by date | 100% Compliance by 30 June 2016 | 100% Compliance by 31 September 2015 |  |  |  | 400000 |  | FMG
115 |  |  |  | Bid Processing | Time lapse in processing of bids | 14 Days for quotation by 30 June 2016 | 14 Days for quotations by 31 September 2015 |  |  |  | 0 |  | N/A
116 | [5 empty] | 90 Days for Tenders by 30 June 2016 | 14 Days for Tenders by 31 September 2015 |  |  |  | 0 |  | N/A
117 |  | Indigent |  | Indigent Register | Development of Indigent Register by date | 4 Progress Reports presented by 30 June 2016 | 1 Progress Report presented by 30 September 2015 |  |  |  | 300000 |  | 0
118 |  | Governance |  | Reconciliations | Number of Reconciliations Report Procuded | 12 Debtors Reconciliations | 3 Monthly Reports produced |  |  |  | 0 |  | N/A
119 | [5 empty] | 12 Clearing of suspense accounts | 3 Monthly Reports produced |  |  |  | 0 |  | N/A
120 | [5 empty] | 12 Rates Reconcilations | 3 Monthly Reports produced |  |  |  | 0 |  | N/A
121 | [5 empty] | 12 Consumer Deposit Reconciliations | 3 Monthly Reports produced |  |  |  | 0 |  | N/A
122 | [5 empty] | Bank Reconcilliations | 3 Monthly Reports produced |  |  |  | 0 |  | N/A
123 |  |  |  | Investments | Municipal Investments Report submitted to Standing Committee | 12 Monthly Investments Reports by 30 June 2016 | 3 Monthly Investments Reports |  |  |  | 0 |  | N/A
124 |  |  |  | Audit Opinion | Audit Report from the Auditor General | Unqualified audit without matters of emphasis by 30 June 2016 | Not applicable |  |  |  | 0 |  | N/A
125 |  |  |  | Maintain an accurate grant register | % accurate grant register prepared and maintained | 100% accurate grant register by 30 June 2016 | 100% accurate grant register |  |  |  | 0 |  | N/A
126 |  |  |  |  | Reports submitted to Standing Committee | 12 Monthly Reports submitted by 30 June 2016 | 3 Monthly Reports submitted |  |  |  | 0 |  | N/A
127 |  |  |  | Creditors Payments | Time lapse from submission of invoice till payment | 30 Days from submission by 30 June 2016 | Payment of Invoice 30 days from submission |  |  |  | 0 |  | N/A
128 |  |  |  | Payrol | % up to date of Payrol Database | 100% up to date by 30 June 2016 | 100% up to date |  |  |  | 0 |  | N/A
129 |  |  |  |  | Payment date | 25th day monthly | 25th day of each month |  |  |  | 0 |  | N/A
129.1 | [5 empty] | Last day of the month for 3rd parties | Last day of each month for 3rd parties |  |  |  | 0 |  | N/A
130 |  |  |  | Budget Process Plan | Submission of Draft Legislative Budget process Plan to Standing Committee for Council Approval | 2015-08-31 | (1) Submission of Draft to Council - 31 August 2015 (2)Submission of Council Approved Plan to Treasury - 10 Days after adoption (3) On Website - 10 Days after adoption |  |  |  | 0 |  | N/A
131 |  |  |  | Rates Clearance | Time lapse in the issue of Rates Clearance Certificate | 3 Months after the request from buyer/seller | Issue Rates Clearance Certificate 3 Months after the request from buyer/seller |  |  |  | 0 |  | N/A
132 |  |  |  | Annual Financial Statements | Submission of Financial Statements to Auditor General, Treasury and CoGTA | 2015-08-31 | Financial Statements submitted to Auditor General, Treasury and CoGTA - 31 August 2015 |  |  |  | 0 |  | N/A
133 |  |  |  | Quartely Financial Statements | Submission of Financial Statements to Standing Committee | 4 Financial statement prepared and submitted by 30 June 2016 | 1 Financial statement prepared and submitted by 30 September 2015 |  |  |  | 0 |  | N/A
134 |  |  |  | Prepare and Maintain Retension and Reconciliations | Monthly Reconcialiations Reports submitted to Standing Committee | 12 Monthly Reconcialiations Reports submitted by 30 June 2016 | 3 Monthly Reconcialiations Reports submitted by 30 September 2015 |  |  |  | 0 |  | N/A

## Community
NDWEDWE LOCAL MUNICIPALITY
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
Period: 2015/2016 Financial Year
Department: Community Services
KPI NO | National KPA | Project/ Programme Description | IDP Strategic Objective | Output | Key Performance Indicator | Annual Target | September 2015 |  |  |  | Budget Allocation | Vote No | Source of Funding
[7 empty] | Target Q1 | Actual | Variance | Corrective Measure
149 | Infrastructure and Service Delivery | disaster management |  | disaster management Advisory Meetings | Number of Quarterly Disaster Management Advisory Meetings held by date | 4 Quarterly Meeting Reports presented to Manco by date | 1st Quarter Report presented by 30 September 2015 | Done |  |  | 200000 |  | N/A
150 |  |  |  |  | Number of awareness campaigns conducted by date | 8 Campaigns by 30 June 2016 | 2 Campaigns by 30 September 2015 | Not Done | Disaster Management Official was attending workshops | To be done on the 18th and the 24th November 2015 | 0 |  | N/A
151 |  |  |  |  | Submission of Draft 2016 - 2017 Disaster Management Plan to MANCO for Council adoption by date | 2016-05-30 | N/A | N/A |  |  | 0 |  | N/A
152 |  | indigent burial |  | Indigent Burial Policy | Submission of Draft Indigent Burial Policy to Manco for Council adoption by date | 2016-05-30 | N/A | N/A |  |  | R450 000 |  | N/A
166 |  | EPWP |  | Employment of local community members for identified period | Number of community members employed | 85 local labour for 12 months till end of December 2015 | Appointment of local labour and arrangment of Protective Clothes for them | Done |  |  | R 2 000 000.00 |  | Public Works and Municipality
167 |  | Waste Management |  | Collection of waste | Number of collections per month | 14 Collections monthly until 30 June 2016 | 42 Collections by 30 September 2015 | Done |  |  | 100000 |  | Municipality
|  |  |  | Establishment of Buy-Back (Recycling Centre) | Number of Job Created | 20 Permanent Jobs Created, Recycling Hirachy Established | Research/ Feasibility Studies/ Proccesses Completed by 30 September 2015 | Done |  |  | 0.00 |  | Municipality
168 | Infrastructure and Service Delivery | Motor Licencing and Traffic |  | Drivers Licence Testing Centre Establishment | Approval for establishment from Department of Transport | Certificate of Establishment from Department of Transport, Motor Services, Devolution | Resolution approving the establishment of Drivers Licence Testing Centre by 30 August 2015 | Done |  |  | 0.00 |  | Municipality
169 |  | Fire Station Establishment |  | Satellite Fire Station Establishment | Completion Certificate from Provincial DMC | Completion Certificate | Research/ Feasibility Studies/ Proccesses Completed by 30 September 2015 | Not Done | Disaster Management Official was attending workshops |  | 0.00 |  | Municipality
|  | Parks and Recreation |  | Identification of Strategic Areas for Parks | Number of Parks established | Fully Functional Parks and Recreationa Areas | Identification of Parks and Recreational Areas in the Scheme | Done |  |  | 0.00 |  | Municipality
|  | Parks and Recreation |  | 3 Outdoor Gyms Established | Number of Outdoor Gyms established by 30 June 2016 | Hand Over Certificate | Application Submitted to Dpt of S AND R | Not Done | Delays in obtaining application forms from Dept of S nad R | To be done before the end of November 2015 | 0.00 |  | Municipality