## MM Org SCard
DEPARTMENT: OFFICE OF THE MUNICIPAL MUNICIPAL
MUNICIPAL MANAGER: MR M.F.HADEBE
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | STRATEGIC OBJECTIVE | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th QUARTER TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE REF. NUMBER | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
TOP LAYER SDBIP 2020-2021
MUNICIPAL MANAGER PERFORMANCE PLAN
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To enhance organisational performance and compliance | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | MM-01 | Internal Audit Reporting to Audit Committee | Municipal Manager | Administration | Number of reports submitted to Audit Committee by target date. | Number | Achieved.4 reports submitted. | 4 Reports submitted to Audit Committee by 30 June 2021 | 0 | N/A | 1 report submitted by 30 September 2020 | 1 report submitted by 31 December 2020 | 1 report submitted by 31March 2021 | 1 report submitted by 30 June 2021 | Equitable share | MM-BUDG | Default | Municipality | IA quarterly reports schedule of findings per department | H | Office of the Municipal Manager: Internal Audit
[5 empty] | MM-02 | Tabling of Annual Report 2019/2020 to Council within 9 months after the end of a financial year | Municipal Manager | Administration | 2019/20 Annual Report approved and adopted by Council by target date. | Date | Achieved. 2018/19 Annual Report adopted by Council 31 March 2020 | 2019/20 Annual Report for approval and adopted by Council by 30 June 2021 | 150000 | N/A | Submission of draft Annual report to Auditor General by 31 August 2020 | N/A | N/A | Mayor tables AR to Council for approval and adoption by 30 June 2021 | Equitable share | MM-BUDG | Default | Municipality | Council Resolution | H | Office of the Municipal Manager
[5 empty] | MM-03 | Tabling of Oversight report on the AR 2019/20 to Council by no later than 2(two) months from the date in which the AR was tabled as per MFMA Section 127 (5) | Municipal Manager | Administration | 2019/20 Oversight Report approved and adopted by Council by target date. | Date | Achieved. Oversight report adopted by Council on 31 March 2020 | 2019/20 Oversight Report for approval and adopted by Council by 30 June 2021 | 0 | N/A | N/A | N/A |  | Oversight Report tabled to Council for approval and adoption by 30 June 2021 | Equitable share | MM-BUDG | Default | Municipality | Council Resolution | H | Chaiperson MPAC
[5 empty] | MM-04 | Reviewed Performance Management Framework |  |  | Reviewed Performance Management Framework approved and adopted by Council by target date. |  | New measure | Reviewed Performance Management Framework for approval and adopted by Council by 30 June 2021 | 0 | N/A | N/A | N/A | N/A | Reviewed Performance Management Framework for approval and adopted by Council by 30 June 2021 | Equitable share |  |  | Municipality | Council Resolution | M | Office of the Municipal Manager:Manager IDP/PMS
|  |  | To ensure enhancement of good governance and public participation and To strengthen partnership with various stakeholders through communicating municipal business . |  | MM-05 | IDP/Budget/PMS Process Plan 2021/2022 | Municipal Manager | Administration | Adoption of the IDP/Budget & PMS Process plan for 2021/2022 by target date. | Date | Achieved. Adopted 2020/2021 IDP/Budget & PMS Process Plan 29 August 2019 | 2021/2022 IDP/Budget & PMS Process plan adopted by Council by 30 September 2020 | 0 | N/A | Final IDP Process plan adopted by Council by 30 September 2020 | N/A | N/A | N/A | Equitable share | MM-BUDG | Default | Municipality | Council Resolution | M | Office of the Municipal Manager:Manager IDP/PMS
[5 empty] | MM-06 | Annual IDP Review |  |  | Adoption of the 2021/2022 IDP Review in line with S129 MFMA & Chapters 5&6 MSA by Council by target date. | Date | New measure | 2021/2022 Final IDP adopted by 30 June 2021 | 0 | N/A | N/A | N/A | Prepare draft IDP 2021/2022 for submission to KZN COGTA by 31 March 2021 | Final IDP 2021/2022 for adoption by Council by 30 June 2021 | Equitable share |  |  | Municipality | Letter of receipt from COGTA & Council Resolution | M | Office of the Municipal Manager:Manager IDP/PMS
[5 empty] | MM-07 | Speaker Izimbizo | Municipal Manager | Administration | Number of Speaker's Izimbizo hosted by target date. | Number | Achieved. 1 Izimbizo held on 7 December 2019 | 2 Izimbizo's hosted by 30 June 2021 | 1040000 | N/A | N/A | 1 Izimbizo 31 December 2020 | N/A | 1 Izimbizo by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Attendance Register of Participants | M | Office of the Municipal Manager: Manager Public Participation
[5 empty] | MM-08 | Mayoral/IDP Izimbizo | Municipal Manager | Administration | Number of Mayoral Izimbizo by target date. | Number | Achieved. 4 Mayoral/ IDP Izimbizo held. | 8 Mayoral/ IDP Izimbizo by 30 June 2021 | 3155000 | N/A | N/A | 4 Izimbizo by 31 December 2020 | N/A | 4 Izimbizo by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager IDP/Public Participation
[5 empty] | MM-10 | Ward Committees Training | Municipal Manager | Administration | Number of Ward Committees training by target date. | Number | Achieved. 1 Ward Committee Training conducted. | 2 Ward Committee trainings conducted by 30 June 2021 | 5287000 | N/A | N/A | 1 Training conducted by 31 December 2020 | N/A | 1 Training conducted by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Attendance Registers | M | Office of the Municipal Manager:Manager Public Participation
[5 empty] | MM-11 | Ward Committees Quarterly Meeting | Municipal Manager | Administration | Number of Ward Committee meetings held by target date. | Number | Not achieved.2 Ward Committee meetings were held. | 4 Ward Committee meetings held by 30 June 2021 |  | N/A | 1 Ward Committee Meeting held by 30 September 2020 | 1 Ward Committee Meeting held by 31 December 2020 | 1 Ward Committee Meeting held by 31 March 2021 | 1 Ward Committee Meeting held by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Attendance register and Minutes of the meeting | M | Office of the Municipal Manager:Manager Public Participation
[5 empty] | MM-12-19/21 | Mayoral Media slots | Municipal Manager | Administration | Number of Media slots conducted by target date. | Number | 20 Media Slots completed. | 20 Media Slots conducted by 30 June 2021 | 1580000 | N/A | 5 Media slots conducted by 30 September 2020 | 5 Media slots by 30 conducted by December 2020 | 5 Media slots by 31 conducted by March 2021 | 5 Media slots by 30 conducted by June 2021 | Equitable share | MM-BUDG | Default | all wards | Newspapers clips,Attendance Register | M | Office of the Municipal Manager:Manager Communication
|  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. |  | MM-13 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of progress reports on Risk Management by target date. | Number | Not achieved 1 Risk register report from July 2019 to March 2020. | 4 Progress Reports on Risk Management by 30 June 2021 | 0 | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 31 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | Equitable share | MM-BUDG | Default | Municipality | Progress report & Risk registers | H | Office of the Municipal Manager: Risk Manager (VACANT)
|  |  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | MM-14 | Review performance of effective enterprise risk management | Municipal Manager | Administration | Number of ethics/Risk Committee meetings held by target date. | Number | Over Achieved. 4 Risk meetings held (1 October 2019, 10 June , 19 June and 30 June 2020. | 4 Ethics/Risk Committee meetings held by 30 June 2021 | 0 | N/A | 1 Ethics/Risk Committee meeting held by 30 September 2020 | 1 Ethics/Risk Committee meeting held by 31 December 2020 | 1 Ethics/Risk Committee meeting held by 31 March 2021 | 1 Ethics/Risk Committee meeting held by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Agenda, Minutes & Risk attendance registers | H | Office of the Municipal Manager: Risk Manager (VACANT)
[5 empty] | MM-15 | Risk Management | Municipal Manager | Administration | Risk assessment process & develop risk register for 2021/2022 by target date. | Date | 2021 Risk register was developed and tabled to the Risk committee on the 30 June 2020. | Risk assessment process & develop risk register for 2021/2022 by 30 June 2021 | 0 | N/A | N/A | N/A | N/A | Conduct risk assessment & develop risk register for 2021/2022 by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Risk assessment & Risk register | H | Office of the Municipal Manager: Risk Manager (VACANT)
[5 empty] | MM-16 | Enterprise Risk Management Register | Municipal Manager | Administration | 2021/2022 Enterprise Risk Management Register submitted to Risk Mngt Committee for approval by target date. | Date | Achieved. | 2021/2022 Enterprise Risk Management Register submitted to Risk Mngt Committee for approval by 30 June 2021 | 0 | N/A | N/A | N/A | N/A | Submit 2021/2022 Enterprise Risk Management Register to Risk Mngt Committee for approval by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Enterprise Risk Management Register | H | Office of the Municipal Manager: Risk Manager (VACANT)
[5 empty] | MM-17 | Enterprise Risk Management Policy and Framework | Municipal Manager | Administration | Reviewed Enterprise Risk Management Framework and Policy by target date. | Date | Achieved. | Reviewed Risk Mngt Framework and Policy by 30 June 2021 | 0 | N/A | N/A | N/A | N/A | Reviewed Risk Mngt Framework and Policy by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | Office of the Municipal Manager: Risk Manager (VACANT)
[5 empty] | MM-19 | Anti-Fraud and Corruption Strategy & Policy | Municipal Manager | Administration | Reviewed Anti-Fraud and Corruption Strategy & Policy by target date. | Date | Not Achieved. | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2021 | 0 | N/A | N/A | N/A | N/A | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | Office of the Municipal Manager: Risk Manager (VACANT)
|  |  | To promote sports within local communities |  | MM-20 | Sports Developmet programmes | Municipal Manager | Administration | Number of Sports development programmes hosted by target date. | Number | Not achieved. 16 Sports development programmes held. | 40 Sports development programmes hosted by 30 June 2021 | 1510000 | N/A | 10 Sports development programmes hosted by 30 September 2020 | 10 Sports development programmes hosted 31 December 2020 | 10 Sports development programmes hosted by 31 March 2021 | 10 Sports development programmes hosted by 30 June 2021 | Equitable share |  |  | All Wards | Attandance registers, media/ photos | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-21 | Women in Sport Symposium | Municipal Manager | Administration | Number of Sports Symposium for Women hosted by target date. | Number | Project was cancelled during the adjustment budget due to budget constraints. | 1 Women in Sport Symposium and sport day hostedby 31 March 2021 |  | N/A | N/A | N/A | 1 Women in Sport Symposium hosted by 31 March 2021 | N/A | Equitable share | MM-BUDG | Default | all wards | Attandance registers, media/ photos | L | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-22 | ECD's sport day | Municipal Manager | Administration | Number of events hosted by target date. | Number | Achieved. | 1 ECD's sport day by 31 December 2020 |  | N/A | N/A | 1 ECD's sport day by 31 December 2020 | N/A | N/A | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-23 | Municipal Sport Award | Municipal Manager | Administration | Number of sports awards hosted by target date. | Number | Project was cancelled during the adjustment budget due to budget constraints. | 1 Municipal Sport Award hosted by 31 March 2021 |  | N/A | N/A | N/A | 1 Municipal Sport Award hosted by 31 March 2021 | N/A | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-24 | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance |  | Number of Salga events hosted by target date. | Number | Achieved | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2020 | 1275000 | N/A | Preparations for Salga Games by 30 September 2020 | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2020 | N/A | N/A | Equitable share |  |  | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-25 | Mayoral Sports Development Cup Tournament | Mayoral Sports Development Cup Tournament |  | Number of Mayoral sports hosted by target date. | Number | Achieved | 1 Mayoral Sports Development Cup Tournament hosted by 31 January 2021 | 405000 | N/A | N/A | N/A | 1 Mayoral Sports Cup hosted by 30 January 2021 | N/A | Equitable share |  |  | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-26 | Sports and Recreation Capacity Building Workshops | Mayoral Sports Development Cup Tournament |  | Number of capacity building workshops for sports and recreation conducted by target date. | Number | New measure | 1 Sports and Recreation Capacity Building Workshop conducted by 31 December 2020 | 260000 | N/A | N/A | Sports and Recreation Capacity Building Workshop conducted by 31 December 2020 | N/A | N/A | Equitable share |  |  | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
|  |  | To provide educational guidance to local citizens and To provide career and job searching skills to the local unemployed |  | MM-27 | Job Readiness Programme | Municipal Manager | Administration | Number of job readiness conducted by target date. | Number | Not achieved. | 3 Job readiness programmes conducted by 30 June 2021 | 150000 | N/A | N/A | 1 Job readiness programmes conducted by 31 December 2020 | 1 Job readiness programmes conducted by 31 March 2021 | 1 Job readiness programmes conducted by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-28 | Youth in business (SMME) Seminar | Municipal Manager | Administration | Number of Youth SMME Seminars hosted by 30 June 2021 | Number | New measure | 2 Youth SMME Seminar hosted by 30 June 2021 | 350000 | N/A | N/A | 1 Youth SMME Seminar hosted by 31 December 2020 | N/A | 1 Youth SMME Seminar hosted by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-29 | Youth IDP | Municipal Manager | Administration | Number of Youth IDP hosted by target date. | Number | New measure | 1 Youth IDP hosted by 31 December 2020 | 260000 | N/A | N/A | 1 Youth IDP hosted by 31 December 2020 | N/A | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-30 | Examination Prayer | Municipal Manager | Administration | Number of Examination Prayer hosted by target date. | Number | Achieved. | 1 Examination Prayer hosted by 30 November 2020 | 280000 | N/A | N/A | 1 Examination Prayer hosted by 30 November 2020 | N/A | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-31 | Youth Sumit | Municipal Manager | Administration | Number of Youth Sumit hosted by target date. | Number | New measure | 1 Youth Sumit hosted by 30 June 2021 | 290000 | N/A | N/A | N/A | N/A | 1 Youth Sumit hosted by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-32 | Top Achievers Awards Ceremony |  |  | Number of awardsceremony for Top achievers hosted by target date. | Number | New measure | 1 Award ceremony for Top achievers hosted by 31 January 2021 | 135000 | N/A | N/A | N/A | 1 Award ceremony for Top achievers hosted by 31 January 2021 | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-33 | Junior Council Launch |  |  | Number of Junior Council Launch hosted by target date. | Number | New measure | 1 Junior Council Launch hosted by 31 March 2021 | 145000 | N/A | N/A | N/A | 1 Junior Council Launch hosted by 31 March 2021 | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-34 | Youth Revolutionary Programmes |  |  | Number of programs for Revolutionary youth hosted by target date | Number | New measure | 2 Youth Revolutionary Programmes hosted by 30 June 2021 | 220000 | N/A | N/A | N/A | 1 Youth Revolutionary Programmes hosted by 31 March 2021 | 1 Youth Revolutionary Programmes hosted by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | L | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-35 | Grade 12 Career guidance Expo programme | Municipal Manager | Administration | Number of career guidance Expo programmes facilitated for Grade 12 hosted by target date | Number | Achieved | 2 Career guidance Expo programmes hosted for Grade 12 by 30 June 2021 | 270000 | N/A | 1 Career Guidance programme hosted by 30 September 2020 | N/A | N/A | 1 Career Guidance programme hosted by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
|  |  | To preserve our History and heritage and To provide educational guidance to local citizens |  | MM-36 | Miss Heritage Ndwedwe |  |  | Number of events for Miss Hearitage Ndwedwe hosted by target date | Number | New measure | 1 Miss Heritage Ndwedwe events hosted by 30 September 2020 | 190000 | N/A | 1 Miss Heritage Ndwedwe events hosted by 30 September 2020 | N/A | N/A | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-37 | Faith based Youth Forum |  |  | Number of forums for faith based Youth held by target date. | Number | New measure | 1 Faith based Youth Forum held by 31 March 2021 | 90000 | N/A | N/A | N/A | 1 Forum for faith based Youth held by 31 March 2021 | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-38 | Young Local Artists Support Workshop |  |  | Number of support workshops for Young Local Artists support held by target date. | Number | New measure | 1 Young Local Artists Support workshop held by 30 March 2021 | 140000 | N/A | N/A | N/A | 1 Young Local Artists Support workshop held by 31 March 2021 | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-39 | Ndwedwe Boys Camp |  |  | Number of camps for Ndwedwe Boys hosted by target date. | Number | New measure | 1 Camp for Ndwedwe Boys hosted by 31 December 2020 | 260000 | N/A | N/A | 1 Camp for Ndwedwe Boys hosted by 31 December 2020 | N/A | N/A | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-40 | Drivers Licence Programme Code 10 | Municipal Manager | Administration | Number of Youth trained for Driver's licence programme by 30 June 2021 | Number | Not achieved. Drivers Licences Programme for Code 10 could continue and be booked for the testing of the learners due to Covid-19 lockdown restrictions. | 38 Youth trained for Driver's licence programme by 30 June 2021 | 400000 | N/A | N/A | Appointment of Service provider by 31 December 2020 | N/A | 38 Youth trained for Drivers License by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance register/ Drivers license certificate |  | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-41 | Youth Council Advisory Meeting | Municipal Manager | Administration | Number of Youth Council Advisory meetings held by 30 June 2021 | Number | Achieved. 2 meetings were held. | 4 Youth Council Advisory meetings held by 30 June 2021 | 0 | N/A | 1 Youth Council Advisory meeting held by 30 September 2020 | 1 Youth Council Advisory meeting held 31 December 2020 | 1 Youth Council Advisory meeting held by 31 March 2021 | 1 Youth Council Advisory meeting held by 30 June 2021 | Equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Office of the Municipal Manager:Manager Youth
[5 empty] | MM-42 | Ward Committee Training Covid 19 Respond |  |  | Number of Ward Committees trainings for Covid-19 respond conducted by target date. | Number | New measure | 1 Ward Committee training for Covid-19 respond conducted by 31 December 2020 | N/A | 1000000 | N/A | 1 Ward Committee training for Covid-19 conducted by 31 December 2020 | N/A | N/A | Equitable share |  |  | All Wards | Attendance registers | M | Office of the Municipal Manager:Manager Public Participation
[5 empty] | MM-43 | Feeding of Homeless/ Food Distribution Covid 19 Respond |  |  | Number of quarterly progress reports prepared for Feeding of Homeless/ Food Distribution for Covid 19 Respond by target date. | Number | New measure | 3 Quarterly progress reports prepared for Feeding of Homeless/ Food Distribution for Covid 19 respond by 30 June 2021 | N/A | 5000000 | N/A | 1 Quarterly progress report prepared for the Feeding of Homeless/ Food Distribution for Covid 19 Respond by 31 December 2020 | 1 Quarterly progress report prepared for the Feeding of Homeless/ Food Distribution for Covid 19 Respond by 31 March 2021 | 1 Quarterly progress report prepared for the Feeding of Homeless/ Food Distribution for Covid 19 Respond by 30 June 2021 | Equitable share |  |  | All Wards | 3 Quarterly progress reports and Beneficiary registers | M | Office of the Municipal Manager:Manager Public Participation
[5 empty] | MM-44 | Community and Awareness Campaigns Covid 19 Respond | Municipal Manager | Administration | Number of Community and Awareness Campaigns for Covid 19 respond held by target date. | Number | New measure | 2 Community and Awareness Campaigns for Covid 19 respond held by 31 March 2021 | N/A | 1000000 | N/A | 1 Community and Awareness Campaign for Covid 19 Respond held by 31 December 2020 | 1 Community and Awareness Campaign for Covid 19 Respond held by 31 March 2021 | N/A | Equitable share | Default | all wards | All Wards | Newspapers articles and Attendance Register for Campaign | M | Office of the Municipal Manager: Manager Communication
[5 empty] | MM-45 | Training of Youth for Covid 19 Respond Programmes |  |  | Number of trainings of Youth for Covid 19 Respond programmes to be held by target date. | Number | New measure | 3 Trainings of Youth for Covid 19 Respond Programmes to be held by 30 June 2021 | N/A | 1500000 | N/A | 1 Training of Youth for Covid 19 Respond programmes to be held by 31 December 2020 | 1 Training of Youth for Covid 19 Respond programmes to be held by 31 March 2021 | 1 Training of Youth for Covid 19 Respond programmes to be held by 30 June 2021 | Equitable Share |  |  | All wards | Attendance Register | H | Office of the Municipal Manager:Manager Youth
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | TS-14 | Ndwedwe Testing Station Intersection | Technical Services | Administration | Construction of Testing Station to be completed by target date. | Date | New measure | Construction Ndwedwe Testing Station Intersection to be completed by 30 June 2021 | 7000000 | N/A | Preliminary Design report to be completed by 30 September 2020 | Activities of construction (Site establishment, Demolish existing old building, Bush clearance) to be completed by 31 December 2020 | Activities of construction - (Road earthworks and Road layer works) to be completed by 31 March 2021 | Construction Ndwedwe Testing Station Intersection Activities of construction (complete Road intersection, road signals/robots) to be completed by 30 June 2021 | Equitable share | TECH-BUDG | Default | 6 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Director: Technical Services Manager: PMU
[5 empty] | TS-15 | INEP Electrification Ward 1, 4 & 9 | Technical Services | Administration | Number of household connections to be completed by target date. | Number of households connected | New measure | Construction of INEP Electrification(Ward 1, 4 & 9) infrastructure to 450 household connections to be completed by 30 June 2021 | 10000000 | N/A | Pre-Marketing Report and preliminary design to be completed by 30 September 2020 | Activities of construction - (Tender document and Site establishment) to be completed by 31 December 2020 | Activities of construction - (Pole plantation, Installation of electricity reticulation networks) to be completed by 31 March 2021 | Activities to be completed Construction of INEP Electrification- (Installation of electricity reticulation networks, Commisioning and Energizing of 450 connections to be by 30 June 2021 | INEP | TECH-BUDG | Default | 1,4,9 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | TS-25 | EPWP - Waste management | Technical Services | Administration | Number of EPWP work opportunities created by target date. | Number | Achieved. 73 EPWP Workers was appointed. | 80 EPWP work opportunities created by 30 September 2020 | 1760000 | N/A | 80 EPWP work opportunities created by 30 September 2020 | N/A | N/A | N/A | MIG | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Director: Technical Services Manager: Public Works
[5 empty] | COM-03 | Municipal Waste collection | Community and Social Services | Administration | Percentage of households earning less than R3200 per month with access to waste collection by target date. | Percetage | Achieved. | 100% of Households access to waste collection by 30 June 2021 | 950000 | N/A | 100% Households access to waste collection by 30 September 2020 | 100% Households access to waste collection by 31 December 2020 | 100% Households access to waste collection by 31 March 2021 | 100% Households access to waste collection by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | Waste collection registers |  | Director:Community and Social Services: Manager: Community Services
|  | 3: Human and Community Development | To ensure prevention and mitigation against disasters |  | COM-33 | Disaster Risk Reduction | Community and Social Services | Administration | Review Disaster Management Sector Plan by target date. | Number | The Finalised Disaster Management Plan was not submitted to Council for adoption. | Reviewed Disaster Management Sector Plan by 30 June 2021 | 200000 | N/A | Engagement and consultation with stakeholders to update Terms Of Reference To annually review the Plan by 30 September 2020. | Solicit Inputs from disaster management stakeholders and incorporate them in the Disaster Management Plan by 31 December 2020 | Consolidation of inputs as received from different disaster management stakeholders by 31 March 2021 | Consolidation of inputs as received from different disaster management stakeholders and reviewed Disaster plan by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All Wards | Reviewed Disaster Management Plan | M | Director:Community and Social Services
[5 empty] | COM-37 | Disaster Management Emergency Relief | Community and Social Services | Administration | Number of monthly consolidated incidents/disasters reports submitted to the Provincial disaster management centre by target date. | Number | New measure | 12 Monthly reports submitted to the Provincial disaster management centre by 30 June 2021 | 900000 | N/A | 3 Monthly reports submitted to the Provincial disaster management centre by 30 September 2020 | 3 Monthly reports submitted to the Provincial disaster management centre by 31 December 2020 | 3 Monthly reports submitted to the Provincial disaster management centre by the 8th by 31 March 2021 | 3 Monthly reports submitted to the Provincial disaster management centre by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All Wards | Disaster Management Records, Monthly reporting | H | Director:Community and Social Services
Local Economic Development | A responsive & accountable, effective & efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | EDP-5 | Community gardens support for Cooperatives | Community gardens supported Cooperatives | EDP | Number of Community gardens support for Cooperatives by target date. | Number | Achievevd. Makhuluseni cooperative.1 Functional community garden (Borehole, Fencing Installation and Seedlings support. | 2 Community gardens support for Cooperatives by 30 June 2021 | 1300000 | N/A | N/A | 1 Community garden support for Cooperatives by 31 December 2020 | N/A | 1 Community garden support for Cooperatives by 30 June 2021 | Internal Funding | EDP-BUDG | Default | Ward 18 | Pictures, Progress Report and attendance regsiters | p | Director: EDP
[5 empty] | EDP-12 | Ndwedwe Town Development Project | EDP | Administration | Title Deed/ Certificate of Proclamation by target date. | Date | Not achieved. Detail submission Pack to Surveyor General has not been completed. | Detail submission Pack submission to Surveyor General by 30 June 2021 | 1200000 | N/A | N/A | N/A | Final Application approved by Council by 31 March 2021 | Detail submission Pack submission to Surveyor General by 30 June 2021 | Equitable Share | Proof of submission Title Deed/ Certificate of Proclamation | M | All wards | Proof of submission Title Deed/ Certificate of Proclamation | M | Director: EDP
[5 empty] | EDP-13 | Ndwedwe Land Use Managament System | EDP | Administration | Approval and adopted of LUMS document by target date. | Date | Achieved. | Final Land Use Management System approved and adopted by Council by 30 June 2021 | 500000 | N/A | Appointment of the Service provider by 30 September 2020 | N/A | Final Draft Land Use Management System developed by 31 March 2021 | Final Land Use Management System approved and adopted by Council by 30 June 2021 | Equitable share | Draft LUMS DOC | M | All wards | Council resolution and Final LUMS | M | Director: EDP
INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive & accountable, effective & efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | CS-01 | Implement the Workplace Skills Plan (WSP) | Corporate Services | HR | Number of WSP training programmes implemented as per WSP by end of financial year target date. | Number | Overachieved. 14 WSP skills training programmes implemented. | 8 WSP training programmes implemented as per WSP by 30 June 2021 | 1000000 | N/A | 2WSP training programmes implemented as per WSP by 30 September 2020 | 2WSP training programmes implemented as per WSP by 31 December 2020 | 2WSP training programmes implemented as per WSP by 31 March 2021 | 2 WSP training programmes implemented as per WSP by 30 June 2021 | Equitable Share | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Director: Corporate Services:Manager: Human Resource
[5 empty] | CS-03 | Filling budgeted posts | Corporate Services | HR | Number of Budgeted posts filled by target date. | Number | Not achieved. 5 Budgeted posts were filled (Municipal Manger, Budget Manager, Social Cohenion Officer, PMS/IDP Officer and Youth Officer. | 12 Budgeted posts be filled by 30 June 2021 | 0 | N/A | 3 Budgeted posts be filled by 30 September 2020 | 3 Budgeted posts be filled by 31 December 2020 | 3 Budgeted posts be filled by 31 March 2021 | 3 Budgeted posts be filled by 30 June 2021 | Equitable Share | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Director: Corporate Services:Manager: Human Resource
[5 empty] | CS-10 | Council support services | Corporate Services | Admin | Number of Council meetings held by target date. | Number | Overachieved.15 Council meetings were held on 3 & 31 July 2019, 29 August, 11,30 October,28 November, 06 December 2019 and 8 January , 31 January, 27 February, 31 March, 8 May, 30 May, 15 June 2020 and 29 June 2020 | 4 Council meetings held by 30 June 2021 | 350000 | N/A | 1 Council meeting held by 30 September 2020 | 1 Council meeting held by 31 December 2020 | 1 Council meeting held by 31 March 2021 | 1 Council meeting held by 30 June 2021 | Equitable Share | DCS-BUDG | Default | N/A | Notices and attendance register | H | Director: Corporate Services Manager: Administration
Financial Viability and Management | A responsive & accountable, effective & efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management. To achieve a clean audit opinion | F-02 | Financial Reporting Section 71 MFMA Reports | FINANCE | Administration | Number of Section 71 MFMA Reports submitted by target date. | Number | Achieved | 12 Section 71 MFMA reports submitted at the end 30 June 2021 | 0 | N/A | 3 Monthly reports submitted by 30 September 2020 | 6 Monthly reports submitted by 31 December 2020 | 9 Monthly reports submitted by 31 March 2021 | 12 Monthly reports submitted by 30 June 2021 | Equitable Share | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Office of the CFO
[5 empty] | F-03 | Financial Reporting | FINANCE | Administration | Number of Section 72(1) (b) MFMA Reports by target date. | Number | Achieved | 71 MFMA Reports submitted at the end of 31 January 2021 | 0 | N/A | N/A | N/A | 1 MFMA 72 report submitted by 31 January 2021 | N/A | Equitable Share | FIN-BUDG | Default | N/A | 1 MFMA 72 report | H | Office of the CFO
[5 empty] | F-07 | Revenue protection and enhancement | FINANCE | Administration | % of Revenue collected by target date. | Percentage | Overachieved. 76% of Revenue collected by 30 June 2020 | 70% of Revenue collected by 30 June 2021 | 0 | N/A | 15% of Revenue collected by September 2020 | 25% of Revenue collected by December 2020 | 50% of Revenue collected by March 2021 | 70% of Revenue collected by 30 June 2021 | Equitable Share | FIN-BUDG | Default | N/A | Revenue Reports | H | Office of the CFO: the Mananger: Finance

## TECHNICAL
DEPARTMENT: TECHNICAL SERVICES
DIRECTOR: MR.D.H.MZOLO
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | STRATEGIC OBJECTIVE | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th Quarter TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
DEPARTMENTAL SDBIP
DIRECTOR TECHNICAL SERVICES PERFORMANCE PLAN 2020-2021
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality; To create job opportunities through infrastructure | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | TS-01 | Ngonyameni Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | New measure | 3.7km Construction of Ngonyameni Access Road to be completed by 31 March 2021 | 3445605.54 | N/A | Tender documentation completed by 30 September 2020 | Site establishment and 1.7km road layer works completed by 31 December 2020 | 2.0 km road layer works, culvert pipes , gabions and stone pitching completed by 31 March 2021 | N/A | MIG | TECH-BUDG | Default | 18 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-02 | Zondo Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | New measure | 2.3km Construction of Zondo Access Road to be completed by 31 March 2021 | 3778746.06 | N/A | Tender documentation completed by 30 September 2020 | Site establishment and 1km road layer works completed by 31 December 2020 | 1.3km road layer works, culvert pipes and gabions completed by 31 March 2021 | N/A | MIG | TECH-BUDG | Default | 15 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-03 | Nhlabamkhosi to Epitsini Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | New measure | 2km Construction of Nhlabamkhosi to Epitsini Access Road to be completed by 31 March 2021 | 1116387.21 | N/A | Tender documentation completed by 30 September 2020 | Site establishment and 1km road layer works, culvert pipes and gabions to be completed by 31 December 2020 | 2km construction of Nhlabamkhosi to Epitsini Access Road to be completed by 31 March 2021 | N/A | MIG | TECH-BUDG | Default | 13 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-04 | Nembeni Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | New measure | 2.9km Construction of Nembeni Access Road to be completed by 31 March 2021 | 5904482.2 | N/A | Tender documentation completed by 30 September 2020 | Site establishment and 1km road layer works, culvert pipes and gabions completed by 31 December 2020 | 1.9km road layer works, culvert pipes and gabions completed by 31 March 2021 | N/A | MIG | TECH-BUDG | Default | 9 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-05 | Etsheni Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | New measure | 2.5km Construction of Etsheni Access Road to be completed by 31 March 2021 | 3093304.5 | N/A | Tender documentation completed by 30 September 2020 | Site establishment and 1km road layer works, drainage system and gabions completed by 31 December 2020 | 1.5km Construction of Etsheni Access Road to be completed by 31 March 2021 | N/A | MIG | TECH-BUDG | Default | 7 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-06 | Gudlintaba Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | Achieved. Contractor appointed. | 1,75km Construction of Gudlintaba Access Road to be completed by 31 December 2020 | 2500000 | N/A | Site establishment and 1km road layer works and drainage system to be completed by 30 September 2020 | 1,75km Construction of Gudlintaba Access Road be completed by 31 December 2020 | N/A | N/A | MIG | TECH-BUDG | Default | 17 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-07 | Mangangeni CDC | Technical Services | Administration | Construction of CDC to be completed by target date. | Date | Achieved. Contractor appointed. | Construction of Mangangeni CDC to be completed by 30 June 2021 | 5075884.22 | N/A | Foundation and building walls completed by 30 September 2020 | Roofing and plumbing works completed by 31 December 2020 | Fencing and site cleaning to be completed by 31 March 2021 | Construction of Mangangeni CDC to be completed by 30 June 2021 | MIG | TECH-BUDG | Default | 19 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-08 | KwaNovimba Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | Achieved. Contractor appointed. | 1,75km Construction KwaNovimba Access Road to be completed by 31 December 2020 | 2624765.07 | N/A | 1km road layer works and drainage system completed by 30 September 2020 | 1,75km Construction KwaNovimba Access Road to be completed by 31 December 2020 | N/A | N/A | MIG | TECH-BUDG | Default | 18 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-09 | Chamani Access Road | Technical Services | Administration | Number of kilometers to be completed by target date. | Number | Achieved. Contractor appointed. | 0.5km Construction of Chamani Access Road to be completed by 31 December 2020 | 346457.02 | N/A | Tender documentation completed 30 September 2020 | 0.5km Construction of Chamani Access Road (layerworks, drainange systems and ancillary works)to be completed by 31 December 2020 | N/A | N/A | MIG | TECH-BUDG | Default | 16 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-10 | Noorsburg Access Road | Technical Services | Administration | Rehabilitation of access road to be completed by target date. | Date | New measure | Rehabilitation of Noorsburg access road completed to be completed by 31 December 2020 | 700000 | N/A | Site establishement and installation of drainage system and gabions to be completed by 30 September 2020 | Rehabilitation of Noorsburg access road completed to be completed by 31 December 2020 | N/A | N/A | internal | TECH-BUDG | Default | 6 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-11 | Nhlangwini Sports field | Technical Services | Administration | Construction of Sports field to be completed by target date. | Date | Achieved. Building structures (change rooms, ablution facility) completed | Construction of Nhlangwini Sports field to be completed by 31 March 2020 | 1900000 | N/A | Earthworks, blasting hard rock, V-drains to be completed by 30 September 2020 | Soccer field, grassing and plumbing works to be completed by 31 December 2020 | Construction of Nhlangwini Sports field to be completed by 31 March 2020 | N/A | internal | TECH-BUDG | Default | 1 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-12 | Mandlakazi Sports field | Technical Services | Administration | Construction of Sports field to be completed by target date. | Date | Achieved. Building structures (change rooms, ablution facility) completed | Construction of Mandlakazi Sports field to be completed by 31 March 2020 | 2500000 | N/A | Earthworks, Combo court and Drainage system to be completed by 30 September 2020 | Soccer field, grassing, floor tilling, plumbing works, painting to be completed by 31 December 2020 | Construction of Mandlakazi Sports field to be completed by 31 March 2020 | N/A | internal | TECH-BUDG | Default | 4 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-13 | Completion of Hloniphani Hall & Creche Ward 12 | Technical Services | Administration | Construction of Hall and Creche to be completed by target date. | Date | Achieved. Main Building structures completed | Construction (Paving, Security guard house and fencing) of Hloniphani Hall & Creche Ward 12 by 31 December 2020 | 900000 | N/A | Tender documentation completed by 30 September 2020 | Construction (Paving, Security guard house and fencing) of Hloniphani Hall & Creche Ward 12 by 31 December 2020 |  | N/A | Internal | TECH-BUDG | Default | 12 | Appointment letter, Technical Progress Report & Completion Certificate |  | Manager: PMU
[5 empty] | TS-14 | Ndwedwe Testing Station Intersection | Technical Services | Administration | Construction of Testing Station to be be completed by target date. | Date | New measure | Construction Ndwedwe Testing Station Intersection to be completed by 30 June 2021 | 7000000 | N/A | Preliminary Design report to be completed by 30 September 2020 | Activities of construction (Site establishment, Demolish existing old building, Bush clearance) to be completed by 31 December 2020 | Activities of construction - (Road earthworks and Road layer works) to be completed by 31 March 2021 | Construction Ndwedwe Testing Station Intersection Activities of construction (complete Road intersection, road signals/robots) to be completed by 30 June 2021 | Internal | TECH-BUDG | Default | 6 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | TS-15 | INEP Electrification Ward 1, 4 & 16 | Technical Services | Administration | Number of household connections to be completed by target date.. | Number of households connected | New measure | Construction of INEP Electrification(Ward 1, 4 & 16) infrastructure to 450 household connections by 30 June 2021 | 10000000 | N/A | Pre-Marketing Report and preliminary design to be completed by 30 September 2020 | Activities of construction - (Tender document and Site establishment) to be completed by 31 December 2020 | Activities of construction - (Pole plantation, Installation of electricity reticulation networks) to be completed by 31 March 2021 | Activities to be completed Constructionof INEP Electrification- (Installation of electricity reticulation networks, Commisioning and Energizing of 450 connections by 30 June 2021 | INEP | TECH-BUDG | Default | 1,4,16 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | TS-16 | Type 2 Electrification (Ward 17,16,19,15,14,12,11,6,3) | Technical Services | Administration | Number of household connections to be completed by target date. | Number of households connected | New measure | Construction of Type 2 Electrification (Ward 17,16,19,15,14,12,11,6,3) infrastructure to 288 household connections by 30 June 2021 | 1950000 | N/A | Activities of construction - (Site establishment, pole plantation) to be completed by 30 September 2020 | Activities of construction - (Pole plantation and installation of electricity reticulation networks) to be completed by 31 December 2020 | Activities of construction - (Installation of electricity reticulation networks) to be completed by 31 March 2021 | Activities to be completed Construction of Type 2 Electrification- (Commisioning and Energizing of 288 connections by 30 June 2021 | INTERNAL | TECH-BUDG | Default | 17,16,19,15,14,12,11,6,3 | Completion Certificate | H | Director: Technical Services
[5 empty] | TS-17 | Augmentation of Water Supply for EDP and Ndwedwe Main Office | Technical Services | Administration | Augmentation of water supply and installation of JOJO tanks by target date. | Date | Phase 1 Jojo tanks, booster pump installed | Augmentation of Water supply and installation of JOJO tanks for EDP and Ndwedwe Main Office by 31 December 2020 | 400000 | N/A | Tender document to be completed by 30 September 2020 | Augmentation of Water supply and installation of JOJO tanks for EDP and Ndwedwe Main Office by 31 December 2020 | N/A | N/A | Internal | TECH-BUDG | Default | 15 | Completion Certificate | H | Manager: Public Works
[5 empty] | TS-18 | Johnny Makhathini Hall Renovations | Technical Services | Administration | Renovations of hall to be completed by target date. | Date | New measure | Renovations to Jonny Makhathini Hall to be completed by 31 March 2021 | 1070000 | N/A | Activities for renovation - (Painting of ceiling, toilet revamp, flooring tiles) to be completed by 30 September 2020 | Activities for renovation - (Supply & install new whirlbirds, decommisioning of ventilation & its system, water backup) to be completed by 31 December 2020 | Jonny Makhathini Hall renovations to be completed by 31 March 2021 | N/A | Internal | TECH-BUDG | Default | 15 | Completion Certificate | M | Manager: Public Works
[5 empty] | TS-19 | Maintanance Projects (Ward 1,2,3,4,5,6,8,10,11,12,14,16,17,19) | Technical Services | Administration | Maintanance Projects to be completed by target date. | Date | New measure | Maintanance Projects (Wards1,2,3,4,5,6,8,10,11,12,14,16,17,19)assessments and maintanance works to be completed by 30 June 2021 | 9000000 | N/A | Tender documentation completed by 30 September 2020 | Activities for renovation - (Ceiling, windows, electrical works) to be completed by 31 December 2020 | Activities for renovation - (Road Re-gravelling, drainage system) to be completed by 31 March 2021 | Maintanance Projects (Wards1,2,3,4,5,6,8,10,11,12,14,16,17,19) assessments and maintanance works to be completed by 30 June 2021 | Internal | TECH-BUDG | Default | 1,2,3,4,5,6,8,10,11,12,14,16,17,19 | Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | TS-20 | Rehabilitation of Nhlangano Access Road Ward 4 | Technical Services | Administration | Rehabilitation of Access Road Ward 4 to be completed by by target date. | Date | New measure | Rehabilitation of Nhlangano Access Road Ward 4 to be completed by 31 December 2020 | 720000 | N/A | Rehabilitaion of access road (Backfilling, gabion baskes and drainage) to be completed by 30 September 2020 | Rehabilitation of access road 4 to be completed by 31 December 2020 | N/A | N/A | Internal | TECH-BUDG | Default | 4 | Completion Certificate | H | Manager: Public Works
[5 empty] | TS-21 | Rehabilitation of Cemetry Access Road Ward 15 | Technical Services | Administration | Rehabilitation of Access Road Ward 15 to be completed by target date.. | Date | New measure | Rehabilitation of Cemetry Access Road Ward 15 to be completed by 30 September 2020 | 450000 | N/A | Rehabilitaion activities completed ( Re-gravelling, conrete slab and drainage) to be completed by 30 September 2020 | N/A | N/A | N/A | Internal | TECH-BUDG | Default | 15 | Completion Certificate | H | Manager: Public Works
[5 empty] | TS-22 | Mary Grey Sport Centre Phase 2 | Technical Services | Administration | Construction (Paving blocks, Security guard house) to be completed by target date. | Date | Achieved. Main Building structures completed | Construction (Paving, Security guard house) of Mary Grey Sport Centre Phase 2 to be completed by 30 September 2020 | 594000 | N/A | Construction (Paving, Security guard house) of Mary Grey Sport Centre Phase 2 to be completed by 30 September 2020 | N/A | N/A | N/A | Internal |  |  | 7 | Completion Certificate | H | Manager: PMU
[5 empty] | TS-23 | Generator Installation-EDP Offices & Bhamshela Thusong Centre | Technical Services | Administration | Supply and Installation of generator to be completed by target date.. | Date | New measure | Supply and Installation of generator at the EDP Offices & Bhamshela Thusong Centre to be completed by 31 December 2020 | 1500000 | N/A | Tender documentation completed by 30 September 2020 | Supply and Installation of generator at the EDP Offices & Bhamshela Thusong Centre to be completed by 31 December 2020 | N/A | N/A | Internal |  |  | 15 & 6 | Appointment Letter and Completion Certificate | H | Manager: Public Works
[5 empty] | TS-24 | Ndwedwe Street Lights | Technical Services | Administration | Supply, installation and upgarding of Street lights to be completed by target date. | Date | New measure | Supply, installation and upgrading of high mast lights for Ndwedwe street lights to be completed by 31 March 2021 | 2000000 | N/A | Tender documentation completed by 30 September 2020 | Supply and installation of high mast light, street lights completed by 31 December 2020 | Supply, installation and upgrading of high mast lights for Ndwedwe street lights to be completed by 31 March 2021 | N/A | internal |  |  | 6,15,9 | Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | TS-25 | EPWP - Waste management | Technical Services | Administration | Number of work opportunities created by target date.. | Number | New measure | 80 EPWP work opportunities created by 30 September 2020 | 1760000 | N/A | 80 EPWP work opportunities created by 30 September 2020 | N/A | N/A | N/A | Integrated Grant (IG) | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works
[5 empty] | TS-26 | Capital expenditure monitoring | Technical Services | Administration | Percentage of municipality’s capital budget actually spent on capital projects identified for a particular financial year in terms of the municipality’s Integrated development plan completed by target date. | Percentage | New measure | 100% Capital expenditure spent by 30 June 2021 | 73735066.34 | N/A | 25% Capital expenditure spent by 30 September 2020 | 50% Capital expenditure spent by 31 December 2020 | 75% Capital expenditure spent by 31 March 2021 | 100% Capital expenditure spent by 30 June 2021 | Integrated Grant (IG) | TECH-BUDG | Default | All wards | Quarterly progress reports | H | Director: Technical Services
[5 empty] | TS-27 | Roads maintenance Covid 19 Respond | Technical Services | Administration | Number of quarterly progress reports prepared for Roads maintenance for Covid 19 Respond to be completed by target date. | Date | New measure | 3 Quarterly progress reports prepared for Roads maintenance for Covid 19 Respond to be completed by 30 June 2021 | 0 | 14000000 | N/A | 1 Quarterly progress report prepared for Roads maintenance for Covid 19 Respond to be completed by 31 December 2020 | 1 Quarterly progress report prepared for Roads maintenance for Covid 19 Respond to be completed by 31 March 2021 | 1 Quarterly progress report prepared for Roads maintenance for Covid 19 Respond to be completed by 30 June 2021 | Equitable share | TECH-BUDG | Default | 15 | Quarterly progress reports and Completion Certificate | H | Director: Technical Services
|  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. |  | TS-28 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of progress reports on Risk Management by target date. | Number of progress reports on Risk Management by target date. | New measure | 4 Progress Reports on Risk Management by 30 June 2021 | 0 | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 31 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Risk registers | H | MM - Risk Manager (VACANT)

## CORPORATE SERVICES
DEPARTMENT: CORPORATE SERVICES
DIRECTOR: DR M.G. NTULI
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | STRATEGIC OBJECTIVE | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th Quarter TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
DEPARTMENTAL SDBIP
DIRECTOR CORPORATE SERVICES PERFORMANCE PLAN 2020-2021
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive, accountable, effective and efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | CS-01 | Implement the Workplace Skills Plan (WSP) | Corporate Services | HR | Number of WSP training programmes implemented as per WSP by end of financial year target date. | Number | Overachieved. 14 WSP skills training programmes implemented. | 8 WSP training programmes implemented as per WSP by 30 June 2021 | 800000 | N/A | 2WSP training programmes implemented as per WSP by 30 September 2020 | 2WSP training programmes implemented as per WSP by 30 December 2020 | 2WSP training programmes implemented as per WSP by 31 March 2021 | 2 WSP training programmes implemented as per WSP by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | CS-02 | Implement the Workplace Skills Plan (WSP) | Corporate Services | HR | The percentage of a municipality’s budget actually spent on implementing its workplace skills plan by target date. | Pertcentage | 1% of budget spent on the municipality WSP | 1% of budget spent on the municipality WSP by 30 June 2021 |  | N/A | 0.25% of budget spent on WSP by 30 September 2020 | 0.25% of budget spent on WSP by 30 December 2020 | 0.25% of budget spent on WSP by 31 March 2021 | 0.25% of budget spent on WSP by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | CS-03 | Filling budgeted posts | Corporate Services | HR | Number of Budgeted posts filled by target date. | Number | Not achieved. 5 Budgeted posts were filled (Municipal Manger, Budget Manager, Social Cohenion Officer, PMS/IDP Officer and Youth Officer. | 12 Budgeted posts be filled by 30 June 2021 | 0 | N/A | 3 Budgeted posts be filled by 30 September 2020 | 3 Budgeted posts be filled by 30 December 2020 | 3 Budgeted posts be filled by 31 March 2021 | 3 Budgeted posts be filled by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Manager: Human Resource
[5 empty] | CS-04 | Implement, test and maintain ICT system backups | Corporate Services | ICT | Number of successful backups conducted by target date. | Number | Achieved. | 12 Backup reports submitted by 30 June 2021 | 400000 | N/A | 3 Reports submitted by 30 September 2020 | 3 Reports submitted by 30 December 2020 | 3 Reports submitted by 31 March 2021 | 3 reports submitted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Backup Reports | M | Manager: IT
[5 empty] | CS-05 | Convening of ICT Steering Committee | Corporate Services | ICT | Number of ICT Steering Committee Meetings held by target date. | Number | New measure | 4 ICT Steering Committee meeting minutes by 30 June 2021 | 0 | N/A | 1 ICT Steering Committee meeting minutes submitted by 30 September 2020 | 1 ICT Steering Committee meeting minutes submitted by 30 December 2020 | 1 ICT Steering Committee meeting minutes submitted by 31 March 2021 | 1 ICT Steering Committee meeting minutes submitted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Backup Reports | M | Manager: IT
[5 empty] | CS-06 | Conduct bi-annual municipal data recovery | Corporate Services | ICT | Number of successful data recovery test reports by target date. | Number | Not achieved.The contracted services ended in May 2020. | 2 Data recovery test reports by 30 June 2021 | 250000 | N/A | N/A | 1 report submitted by 30 December 2020 | N/A | 1 report submitted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Data recovery reports | M | Manager: IT
[5 empty] | CS-07 | Ctrack System | Corporate Services | Admin | Number of monthly systems generated reports by target date. | Number | Achieved. | 12 Monthly C track systerm generated report by 30 June 2021 | 350000 | N/A | 3 reports submitted by 30 September 2020 | 3 reports submitted by 30 December 2020 | 3 reports submitted by 31 March 2021 | 3 reports submitted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Ctrack system reports | M | Manager : Administration
[5 empty] | CS-08 | Fleet Management | Corporate Services | Admin | Number of monthly fleet repairs and maintanance reports generated by target date. | Number | New measure | 12 Monthly repaires and maintanace reports generated by 30 June 2021 | 900000 | N/A | 3 Reports submitted by 30 September 2020 | 3 Reports submitted by 30 December 2020 | 3 Reports submitted by 31 March 2021 | 3 reports submitted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Fleet repairs and maintanance reports | M | Manager : Administration
[5 empty] | CS-09 | Community skills support programme | Corporate Services | HR | Number of Interns and Inservice trainees recruited by target date. | Number | Not achieved. 7 Inservice trainees were appointed however no Interns were appointed due to the Covid-19 lockdown restrictions the target was not met. | 8 Interns and 6 Inservice trainees recruited by 30 June 2021 | 0 | N/A | 4 Interns appointed by 30 September 2020 | 4 Interns appointed by 30 December 2020 | 3 Inservice trainees appointed by 31 March 2021 | 3 Inservice trainees appointed by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Appointment Letters | M | Manager: Human Resource
[5 empty] | CS-10 | Council support services | Corporate Services | Admin | Number of Council meetings held by target date. | Number | Overachieved.15 Council meetings were held on 3 & 31 July 2019, 29 August, 11,30 October,28 November, 06 December 2019 and 8 January , 31 January, 27 February, 31 March, 8 May, 30 May, 15 June 2020 and 29 June 2020 | 4 Council meetings held by 30 June 2021 | 350000 | N/A | 1 Council meeting held by 30 September 2020 | 1 Council meeting held by 30 December 2020 | 1 Council meeting held by 31 March 2021 | 1 Council meeting held by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | CS-11 | Council support services | Corporate Services | Admin | Number of EXCO meetings held by target date. | Number | Not achieved. | 10 EXCO meetings held by 30 June 2021 |  | N/A | 3 Exco meetings held by 30 September 2020 | 3 Exco meetings held by 30 December 2020 | 3 Exco meetings held by 31 March 2021 | 1 Exco meeting held by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | CS-12 19/20 | Security Services Reports | Corporate Services | Admin | Number of Security Services Reports generated by target date. | Number | New measure | 10 Security Services Reports generated by 30 June 2021 | 5621200 | N/A | 3 Security Services Reports by 30 September 2020 | 2 Security Services Reports by 30 December 2020 | 2 Security Services Reports by 30 March 2021 | 2 Security Services Reports by 30 June 2021 | Municipality | DCS-BUDG | Default |  | Monthly Reports | M | Manager: Administration
[5 empty] | CS-13 | Drafting of Service Level Agreements (SLA) | Corporate Services | Legal | Number of SLA's drafted by target date. | Number | Overachieved. 106 SLA's prepared and developed. | 4 SLA's drafted by 30 June 2021 | 0 | N/A | 1 SLA drafted by 30 September 2020 | 1 SLA drafted by 30 December 2020 | 1 SLA Drafted by 31 March 2021 | 1 SLA drafted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Copies of SLA's drafted & Register of signed SLA | H | Manager: Legal Services
[5 empty] | CS-14 | Training on Policies and Legislations | Corporate Services | HR/Legal | Number of trainings provided for staff and councillors on Policies and Legislations by target date. | Number | Not achieved. 3 Trainings were conducted instead of 8 due to Covid-19 lockdown restrictions. | 8 Trainings conducted on Policies and Legislations by 30 June 2021 | 0 | N/A | 2 Trainings on Policies and Legislations by 30 September 2020 | 2 Traininings on Policies and Legislations by 30 December 2020 | 2 Trainings on Policies and Legislations by 31 March 2021 | 2 Trainings on Policies and Legislations by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Notices and attendance registers | M | Manager: Legal Services/HR
[5 empty] | CS-15 | Occupational, Health and Safety meeting | Corporate Services | HR | Number of occupational, Health and Safety Committee Meetings held by target date. | Number | New measure | 4 OHS Committee Meetings held by 30 June 2021 | 65000 | N/A | 1 OHS Committee Meetings held by 30 September 2020 | 1 OHS Committee Meetings held by 30 December 2020 | 1 OHS Committee Meetings held by 31 March 2021 | 1 OHS Committee Meetings held by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Notices and attendance registers | H | Manager: HR
[5 empty] | CS-16 |  | Corporate Services | HR | Number of occupational, Health and Safety Training conducted by target date. | Number | New measure | 4 OHS Training conducted by 30 June 2021 | 225000 | N/A | 1 OHS Training conducted by 30 September 2020 | 1 OHS Training conducted by 30 December 2020 | 1 OHS Training conducted by 30 March 2021 | 1 OHS Training conducted by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Notices and attendance registers | H | Manager: HR
[5 empty] | CS-17 | Internal and external bursaries awarded | Corporate Services | HR | Number of internal and external bursaries awarded by target date. | Number | New measure | 4 bursary progress reports by 30 June 2021 | 1230000 | N/A | 1 bursary progress report by 30 September 2020 | 1 bursary progress report by 30 December 2020 | 1 bursary progress report by 31 March 2021 | 1 bursary progress report by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Signed report | M | Manager: HR
[5 empty] | CS-18 | Fleet repairs and maintenance reports | Corporate Services | Admin | Number of fleet repairs and maintenance reports submitted by target date. | Number | New measure | 4 Fleet repairs and maintenance reports by 30 June 2021 | 900000 | N/A | 1 fleet repairs and maintenance report by 30 September 2020 | 1 fleet repairs and maintenance report by 30 December 2020 | 1 fleet repairs and maintenance report by 31 March 2021 | 1 fleet repairs and maintenance report by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Fleet reports | L | Manager: Administration
[5 empty] | CS-19 20/22 | Employment Assistant Programs | Corporate Services | HR | Number of Employment Assistant Programs organised by target date. | Number | New measure | 4 EAP programs organised by 30 June 2021 | 350000 | N/A | 1 EAP program organised by 30 September 2020 | 1 EAP program organised by 30 December 2020 | 1 EAP program organised by 31 March 2021 | 1 EAP program organised by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Attendance register | M | Manager: HR
[5 empty] | CS-20 | Policies/plans/strategies reviewed and developed | Corporate Services | HR/Legal/Admin/ICT | Number of Policies/plans/strategies reviewed and developed by target date. | Number | Not achieved. 4Policies were reviewed and developed instead of 6, due to Covid-19 lockdown restrictions. | 8 Policies/plans/strategies reviewed and developed by 30 June 2021 | 0 | N/A | 2 Policies/plans/strategies reviewed and developed by 30 September 2020 | 2 Policies/plans/strategies by 30 December 2019 | 2 Policies/plans/strategies by 31 March 20221 | Policies/plans/strategies by 30 June 2021 | Municipality | DCS-BUDG | Default | N/A | Signed report on reviewed and developed policies | M | Manager: Legal Services
|  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. |  | CS-21-20/21 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of progress reports on Risk Management by target date. | Number | New measure | 4 Progress Reports on Risk Management by 30 June 2021 | 0 | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 30 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | Municipality | MM-BUDG | Default | N/A | Risk registers | H | Director : Corporate Services

## FINANCE
DEPARTMENT: FINANCE
SENIOR MANAGER: MR S.G. MAJOLA
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | STRATEGIC OBJECTIVE | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th Quarter TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
DEPARTMENTAL SDBIP
CFO PERFORMANCE PLAN 2020-2021
Financial Viability and Management | A responsive, accountable, effective and efficient local government system | Governance and Policy | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes; To ensure an effective advisory role to management and council; To ensure that the revenue of the muncipality is collected and accounted; To ensure municipal budget complies with MFMA and Treasury regulations | Improvement of Cashflow Liquidity & Promotion of sound financial management | FV-01 | Transactional mSCOA Reports | FINANCE | Administration | Number of reports submitted to Finance Portfolio and Council for 2020/21 by target date. | Number | Achieved | 12 Transactional Mscoa reports submitted to Finance Portfolio and Council by 30 June 2021 | R400,000,00 | N/A | 3 Transactional Mscoa reports submitted to Finance Portfolio and Council by 30 September 2020 | 6 Transactional Mscoa reports submitted to Finance Portfolio and Council by 30 December 2020 | 9 Transactional Mscoa reports submitted to Finance Portfolio and Council by 31 March 2021 | 12 Transactional Mscoa reports submitted to Finance Portfolio and Council by 30 June 2021 | Municipality | FIN-BUDG | Default | N/A | 12 Reports | H | CFO
[5 empty] | FV-02 | Financial Reporting Section 71 MFMA Reports | FINANCE | Administration | Number of Section 71 MFMA Reports submitted by target date. | Number | Achieved | 12 Section 71 MFMA reports submitted at the end 30 June 2021 | 0 | N/A | 3 Monthly reports submitted by 30 September 2020 | 6 Monthly reports submitted by 30 December 2020 | 9 Monthly reports submitted by 31 March 2021 | 12 monthly reports submitted by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | FV-03 | Financial Reporting | FINANCE | Administration | Number of Section 72(1) (b) MFMA Reports by target date. | Number | Achieved | 1 MFMA 72 Report submitted at the end of 31 January 2021 | 0 | N/A | N/A | N/A | 1 MFMA 72 report submitted by 31 January 2021 | N/A | N/A | FIN-BUDG | Default | N/A | 1 MFMA 72 report | H | CFO
[5 empty] | FV-04 | Adjusted Budget for 2020/21 | FINANCE | Administration | Approved Adjusted Budget adopted by the Council by target date. | Date | Achieved | Adopted Adjusted Budget by 31 March 2021 | 0 | N/A | N/A | N/A | Adjusted Budget adopted by the Council by 31 March 2021 | N/A | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | F-05 | Budget for 2020/ 2021 | FINANCE | Administration | Approved Final Budget adopted by the Council by target date. | Date | Annual Budget Approved by 30 May 2020. | Adopted 2020/2021 Budget by the Council as at 30 June 2021 | 0 | N/A | N/A | N/A | Draft Budget adopted by the Council as at 31 March 2021 | Final Budget adopted by the Council as at 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | F-06 | Revenue Enhancement Strategy | FINANCE | Administration | Council adopted Revenue Enhancement Strategy by target date. | Date | Not achieved | Council adopted Revenue Enhancement Strategy by 31 March 2021 | 0 | N/A | Workshop the strategy to Council by 30 September 2020 | N/A | Strategy adopted by Council by 31 March 2021 | N/A | Equitable Share | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Finance
[5 empty] | FV-07 | Revenue protection and enhancement | FINANCE | Administration | % of Revenue collected by target date. | Percentage | Achieved. 76% of Revenue collected by 30 June 2020 | 70% of Revenue collected by 30 June 2021 | 0 | N/A | 15% of Revenue collected by September 2020 | 25% of Revenue collected by December 2020 | 50% of Revenue collected by March 2021 | 70% of Revenue collected by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Revenue Reports | H | Mananger: Finance
[5 empty] | FV-08 | Finances Policies (SCM,Tarrif, Credit Control Policy, S and T, Overtime Policy, Banking and investment, Budget, Indigent, Fixed Assets, Rates, Virement and Disposal) | FINANCE | Administration | Num ber of Finance Policies developed and reviewed adopted by Council by target date. | Number | Achieved | 11 Policies adopted by Council by 30 June 2021 | 0 | N/A | N/A | 11 Draft Policies developed and reviewed by 31 December 2020 | 11 Policies adopted by Council by 31 March 2021 | Approved 11 finance related policies with the Draft Budget adopted by Council by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | CFO
[5 empty] | FV-09 | Supplementary General Valuation Roll | FINANCE | Administration | Supplementary General Valuation Roll produced and submitted to KZN COGTA by target date. | Number | Not achieved. The municipality has applied for an extension for the validity of the Valuation roll, awaiting a response from COGTA. | Supplementary General Valuation Roll produced and submitted KZN COGTA by 30 June 2021 | R200,000,00 | N/A | N/A | N/A | N/A | Supplementary General Valuation Roll produced and submitted to KZN COGTA by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Proof of submission of Supplementary General Valuation Roll to KZN COGTA. | H | Mananger: Finance
[5 empty] | F-10 | Screening of State Employees from SCM Database | FINANCE | Administration | Number of reports generated for each quarter by target date. | Number | Achieved. 4 Quarterly reports generated. | 4 Quarterly reports generated by 30 June 2021 | 0 | N/A | 1 Quarterly reports generated by 30 September 2020 | 1 Quarterly reports generated by December 2020 | 1 Quarterly reports generated by 31 March 2021 | 1 Quarterly reports generated by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | F-11 | Appointment of Local Service Providers | FINANCE | Administration | Reports on Appointed local service providers submitted to Council Portfolio committee by target date. | Date | Achieved | 4 Quarterly reports submitted to Council Portfolio committee by 30 June 2021 | 0 | N/A | 1 Quarterly report submitted to Council Portfolio committee by 30 September 2020 | 1 Quarterly report submitted to Council Portfolio committee by 30 December 2020 | 1 Quarterly report submitted to Council Portfolio committee by 31 March 2021 | 1 Quarterly reports submitted to Council Portfolio committee by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | F-12 | Governance Reports ( Debtors Reconciliation Book) | FINANCE | Administration | Number of Debtors reconciliation by target date. | Number | Achieved | 12 Debtors reconciliation reports submitted by 30 June 2021 | 0 | N/A | 3 Monthly Reports by 30 September 2020 | 3 Monthly Reports by 30 December 2020 | 3 Monthly Reports by 31 March 2021 | 3 Monthly Reports by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | FV-13 | Property Rates Reconciliation | FINANCE | Administration | Number of Property rates reconciliations by target date. | Number | Achieved | 12 Property Rates Reconciliations reports by 30 June 2021 | 0 | N/A | 3 Monthly Reports by 30 September 2020 | 3 Monthly Reports by 30 December 2020 | 3 Monthly Reports by 31 March 2021 | 3 Monthly Reports by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Reports | H | Mananger: Finance
[5 empty] | FV-14 | Bank Reconciliation | FINANCE | Administration | Number of Bank Reconciliation Reports by target date. | Number | Achieved | 12 Bank Reconciliations reports by 30 June 2021 | 0 | N/A | 3 Monthly Reports by 30 September 2020 | 3 Monthly Reports by 30 December 2020 | 3 Monthly Reports by 31 March 2021 | 3 Monthly Reports by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | FV-15 | Investments | FINANCE | Administration | Number of monthly Investments reports by target date. | Number | Achieved | 12 Monthly Investments reports by 30 June 2021 | 0 | N/A | 3 Monthly Reports by 30 September 2020 | 3 Monthly Reports by 30 December 2020 | 3 Monthly Reports by 31 March 2021 | 3 Monthly Reports by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | FV-16 | Grant Register | FINANCE | Administration | Number of Accurate grant registers by target date. | Number | Achieved | 12 monthly grant registers by 30 June 2021 | 0 | N/A | 3 Monthly Reports by 30 September 2020 | 3 Monthly Reports by 30 December 2020 | 3 Monthly Reports by 31 March 2021 | 3 Monthly Reports by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | 12 Monthly Registers | H | Mananger: Finance
[5 empty] | FV-17 | Creditors Payment | FINANCE | Administration | Number of days from submission by target date. | Number | Achieved | 30 Days from submission by 30 June 2021 | 0 | N/A | Payment of Invoice 30 days from submission by 30 September 2020 | Payment of Invoice 30 days from submission by 30 December 2020 | Payment of Invoice 30 days from submission by 31 March 2021 | Payment of Invoice 30 days from submission by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Age analysis Reports | H | Mananger: Finance
[5 empty] | FV-18 | Third Party Payments | FINANCE | Administration | Number of Third Party Payments produced by target date. | Number | Achieved | Last day of the month for 3rd parties by 30 June 2021 | 0 | N/A | Last day of each month for 3rd parties by 30 September 2020 | Last day of each month for 3rd parties by 30 December 2020 | Last day of each month for 3rd parties by 31 March 2021 | Last day of each month for 3rd parties by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Third party payment report | H | Mananger: Finance
[5 empty] | FV-19 | AFS 2019/20 | FINANCE | Administration | Adopted AFS for 2019/20 by target date. | Date | Achieved | Adopted AFS for 2019/20 by 30 September 2020 | 0 | N/A | Adopted Financial statements submitted to Auditor General, Treasury and CoGTA by 30 September 2020 | N/A | N/A | N/A | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | CFO
[5 empty] | FV-20 | MFMA Quarterly report 2020/2021 | FINANCE | Administration | Number of Quarterly reports prepared and submitted by target date. | Number | Achieved | 2 MFMA Quarterly reports prepared and submitted by 30 June 2021 | R400,000,00 | N/A | N/A | N/A | 1 MFMA quarterly report prepared and submitted by 31 March 2021 | 1 MFMA quarterly report prepared and submitted by 30 June 2021 | N/A | FIN-BUDG | Default | N/A | Financial statement report for 2020/2021 | H | CFO
[5 empty] | FV-21 | SCM report | FINANCE | Administration | Number of monthly SCM reports submitted to Council by target date. | Number | Achieved | 4 SCM reports submitted to Council by 30 June 2021 | RO | N/A | 1 SCM report submitted to Council by 30 September 2020 | 1 SCM report submitted to Council by 30 December 2020 | 1 SCM report submitted to Council by 31 March 2021 | 1 SCM report submitted to Council by 30 June 2021 | Equitable Share | FIN-BUDG | Default | N/A | SCM Reports and Council resolutiuon | H | Manager: SCM
[5 empty] | FV-22 | Debt coverage (Pg 9 of MFMA circular 71) | Debt coverage (Pg 9 of MFMA circular 71) | FINANCE | Debt Total Borrowings & Revenue (Debt (Short Term Borrowing + Bank Overdraft + Short Term Lease + Long Term Borrowing + Long Term Lease) / Total Operating Revenue - Operating Conditional Grant) by 30 June 2020 (Norm is 45% & below) | Percentage | New measure | 45% Debt Total Borrowings & Revenue by 30 June 2020 | RO | N/A | N/A | 45% Debt Total Borrowings & Revenue by 31 December 2020 | 45% Debt Total Borrowings & Revenue by 31 March 2020 | 45% Debt Total Borrowings & Revenue by 30 June 2020 | Equitable Share | Default | N/A | Internal | Reports | H | CFO
[5 empty] | FV-23 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of progress reports on Risk Management by target date. | Number | New measure | 4 Progress Reports on Risk Management by 30 June 2021 | RO | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 31 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | Equitable share | MM-BUDG | Default | All Wards | Risk registers | H | CFO

## EPD
DEPARTMENT:ECONOMIC DEVELOPMENT AND PLANNING
DIRECTOR: MR S.D.G. KHUZWAYO
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | Strategies | KPI Ref No. | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th QUARTER TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
DEPARTMENTAL SDBIP
DIRECTOR ECONOMIC DEVELOPMENT AND PLANNING PERFORMANCE PLAN 2020-2021
Local Economic Development | A responsive, accountable, effective and efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To capitalize on tourism potential of the municipality ; To develop a resilient economy that creates sustainable decent jobs and reduces poverty; To ensure job creation; To facilitate co-ordinated planning and development; To upscale agriculture development in the municipality and To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 1 | MM-1-20/21 | Local Agricultural Indaba | Local Agricultural Indaba | EDP | Number of Local Agricultural Indaba hosted by target date. | Number | Achieved. 1 Local Agricultural Indaba held on 28 August 2019. | 1 Local Agricultural Indaba hosted by 30 June 2021 | 50000 | N/A | N/A | N/A | N/A | 1 Agricultural Indaba hosted by 30 June 2021 | Equitable share | EDP-BUDG | Default | Wards 15 | Attendance Registers | H | Director: EDP
[5 empty] | 2 | MM-2-20/21 | Ndwedwe Music Festival | Ndwedwe Music Festival | EDP | Number of Ndwedwe Music Festival event hosted by target date. | Number | New measure | 1 Ndwedwe Music Festival event hosted to be by 31 December 2020 | 1850000 | N/A | N/A | 1 Ndwedwe Music Festival event to be hosted by 31 December 2020 | N/A | N/A | Equitable share | EDP-BUDG | Default | All wards | Pictures and Report | H | Director: EDP
[5 empty] | 3 | MM-3-20/21 | Maskandi Festival | Maskandi Festival | EDP | Number of Maskandi Festival hosted by target date. | Number | Achieved. 1 Maskandi Festival held on 26 October 2019 | 1 Maskandi festival to be hosted by 30 September 2020 | 410000 | N/A | 1 Maskandi festival to be hosted by 30 September 2020 | N/A | N/A | N/A | Equitable share | EDP-BUDG | Default | ward 7 | Pictures and Report | M | Director: EDP
[5 empty] | 16 | MM-4-20/21 | Tourism Development | Tourism Development | EDP | Number of Tourism Indaba's attended by target date. | Number | New measure | 1 Tourism Indaba to be attended by 31 March 2021 | 400000 | N/A | N/A | N/A | 1 Tourism Indaba to be attended by 31 March 2021 | N/A | Equitable share |  |  | All wards | Attendance registers | M | Manager: LED
[5 empty] | 4 | MM-5-20/21 | Community gardens support for Cooperatives | Community gardens supported Cooperatives | EDP | Number of Community gardens support for Cooperatives by target date. | Number | New measure | 2 Community gardens support for Cooperatives by 30 June 2021 | 1300000 | N/A | N/A | 1 Community garden support for Cooperatives by 31 December 2020 | N/A | 1 Community garden support for Cooperatives by 30 June 2021 | Internal Funding | EDP-BUDG | Default | Ward 18 | Pictures and Progress Report and attendance regsiters | p | Director: EDP
[5 empty] | 5 | MM-6-20/21 | SMME Support | SMME Support | EDP | Number of SMMEs supported by target date. | Number | Overachieved. 12 SMMEs supported with land ploughing. | 10 SMME's supported by 30 June 2021 | 690000 | N/A | 3 SMME's supported by 30 September 2020 | 3 SMME's supported by 31 December 2020 | 3 SMME's supported by 31 March 2021 | 1 SMME supported by 30 June 2021 | Internal Funding | EDP-BUDG | Default | All wards | Pictures, Progress reports and Beneficiary signatures | M | Manager: LED
[5 empty] | 6 | MM-7-20/21 | Cooperatives Development and Support | Cooperatives Development and Support | EDP | Number of Cooperatives developed and supported by target date. | Number | 10 x Cooperatives/SMMEs supported with land plouging, with seeds and seedlings and information. Name of Cooperatives assisted: Zama Ngxabi, Farm Gal, Mdanyane, Nokuthula, Ndlala Beyduda, Zongen, Uthando, Yeslusandla, Xanyana and X Cele. | 10 Cooperatives developed and supported by 30 June 2021 | 750000 | N/A | 3 Cooperatives developed and supported by 30 September 2020 | 3 Cooperatives developed and supported by 31 December 2020 | 3 Cooperatives developed and supportedby 31 March 2021 | 1 Cooperatives developed and supported by 30 June 2021 | Internal Funding | EDP-BUDG | Default | TBC | Pictures, Progress reports and Beneficiary signatures | M | Manager: LED
[5 empty] | 6 | MM-8-20/21 | Cooperatives Development for COVID-19 respond | Cooperatives Development and Support | EDP | Number of Cooperatives developed for COVID-19 respond by target date. | Number | New measure | 10 Cooperatives developed for COVID-19 respond by 30 June 2021 | N/A | 3000000 | N/A | Tender documentation to be completed by 30 December 2020 | 5 Cooperatives developed for COVID-19 respond by 31 March 2021 | 5 Cooperatives developed for COVID-19 respond by 30 June 2021 | Equitable share | EDP-BUDG | Default | TBC | Beneficiary signatures and Appointments letter and pictures | M | Manager: LED
[5 empty] | 10 | MM-9-20/21 | Training of Emerging Subcontractors support programme (capacity building for Grade 1-3) | Training of Emerging Subcontractors support programme (capacity building for Grade 1-3) | EDP | Number of Emerging Contractors trained by target date. | Number | Achieved. | 10 Emerging Contractors to be trained by 31 December 2020 | 100000 | N/A | N/A | 10 Emerging Contractors to be trained by 31 December 2020 | N/A | N/A | Internal Funding | EDP-BUDG | Default | TBC | Beneficiary signatures | M | Manager: LED
[5 empty] | 7 | MM-10-20/21 | Housing Forum | Housing Forum | EDP | Number of Housing Forums reports presented by target date. | Number | Not achieved. The forum was not convened due to Covid-19 lockdown restrictions. | 4 Housing Forums reports presented by 30 June 2021 | 0 | N/A | 1 Housing Forum report presented by 30 September 2020 | 1 Housing Forum report presented by 31 December 2020 | 1 Housing Forum report presented by 31 March 2021 | 1 Housing Forum report presented by 30 June 2021 | Internal Funding | EDP-BUDG | Default | All wards | Minutes of meetng and attendace Registers | M | Director: EDP
[5 empty] | 8 | MM-11-20/21 | Development of Housing Sector Plan | Development of Housing Sector Plan | EDP | Adoption of Housing Sector Plan by by target date. | Date | New measure | Final Housing Sector Plan adopted by Council by 30 June 2021 | 150000 | N/A | N/A | N/A | Draft Housing Sector Plan developed by 31 March 2021 | Final Housing Sector Plan adopted by Council by 30 June 2021 | Internal Funding | EDP-BUDG | Default | All wards | Council resolution | H | Director: EDP
[5 empty] | 9 | MM-12-20/21 | LED Forum | LED Forum | EDP | Number of LED Forum meetings hosted by target date. | Number | Not achieved. | 2 LED Forums meetings hosted by 30 June 2021 | 170000 | N/A | N/A | 1 LED Forum meetings hosted by 31 December 2020 | N/A | 1 LED Forum meetings hosted by 30 June 2021 | Internal Funding | EDP-BUDG | Default | All wards | Minutes of meetng and attendace Registers | M | Manager: LED
[5 empty] | 11 | MM-13-20/21 | Ndwedwe Town Development Project | Ndwedwe Town Development Project | EDP | Title Deed/ Certificate of Proclamation by target date. | Date | Not achieved. Detail submission Pack to Surveyor General has not been completed. | Detail submission Pack submission to Surveyor General by 30 June 2021 | 1600000 | N/A | N/A | N/A | Final Application approved by Council by 31 March 2021 | Detail submission Pack submission to Surveyor General by 30 June 2021 | Equitable share | EDP-BUDG | Default | All wards | Proof of submission Title Deed/ Certificate of Proclamation | M | Director: EDP
[5 empty] | 12 | MM-14-20/21 | Ndwedwe Land Use Managament System | Ndwedwe Land Use Managament System | EDP | Approval and adopted of LUMS document by target date. | Date | Achieved. 2nd Draft LUMS completed. | Final Land Use Management System approved and adopted by Council by 30 June 2021 | 500000 | N/A | Appointment of the Service provider by 30 September 2020 | N/A | Final Draft Land Use Management System developed by 31 March 2021 | Final Land Use Management System approved and adopted by Council by 30 June 2021 | Equitable share | EDP-BUDG | Default | All wards | Council resolution and Final LUMS | M | Director: EDP
[6 empty] | MM-15-20/21 | Spatial Development Plan | Spatial Development Plan |  | Adoption of Reviewed Spatial Development Plan by target date. | Date | New measure | Final Reviewed Spatial Development Plan adopted by Council by 30 June 2021 | 200000 | N/A | Appointment of the Service provider by 30 September 2020 | Inception report by 31 December 2020 | Draft Spatial Development Plan developed by 31 March 2021 | Final Reviewed Spatial Development Plan adopted by Council by 30 June 2021 | Equitable share | EDP-BUDG | Default | All wards | Council resolution | M | Director: EDP
[6 empty] | MM-16-20/21 | Review of LED Strategy | Review of LED Strategy |  | Adoption of Reviewed LED Strategy by target date. | Date | Not achieved. | Final Reviewed LED Strategy adopted by Council by 30 June 2021 | 200000 | N/A | Appointment of the Service provider by 30 September 2020 | Inception report by 31 December 2020 | Draft LED Strategy developed by 31 March 2021 | Final Reviewed LED Strategy adopted by Council by 30 June 2021 | Equitable share | EDP-BUDG | Default | All wards | Council resolution | M | Manager: LED
[6 empty] | MM-17-20/21 | Agricultural Sector Plan | Agricultural Sector Plan |  | Adoption of Agricultural Sector Plan by target date. | Date | New measure | Final Agricultural Sector Plan adopted by Council by 30 June 2021 | 150000 | N/A | Appointment of the Service provider by 30 September 2020 | Inception report by 31 December 2020 | Draft Agricultural Sector Plan developed by 31 March 2021 | Final Agricultural Sector Plan adopted by Council by 30 June 2021 | Equitable share | EDP-BUDG | Default | All wards | Council resolution | M | Manager: LED
[5 empty] | 13 | MM-18-20/21 | Purchase of Agricultural Items and Tools | Purchase of Agricultural Items and Tools | EDP | Number of Agricultural Items and Tools purchased by target date. | Number | New measure | 100 Agriculturals Items and Tools purchased by 31 March 2021 | 300000 | N/A | N/A | 50 Agriculturals Items and Tools purchased by December 2020 | 50 Agricultural Items and Tools purchased by 31 March 2021 | N/A | Equitable share | EDP-BUDG | Default | Municipality | Proof of Purcahse | L | Director: EDP
[5 empty] | MM-13-20/21 | MM-19-20/21 | Monitoring performance of effective enterprise risk management | Monitoring performance of effective enterprise risk management | Municipal Manager | Number of progress reports on Risk Management by target date. | Number | New measure | 4 Progress Reports on Risk Management by 30 June 2021 | 0 | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 31 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | Equitable share | Default | N/A | Municipality | Risk registers | H | Director: EDP

## Community Services
DEPARTMENT: COMMUNITY SERVICES
DIRECTOR: MRS P. MBONAMBI
NATIONAL KPA | OUTCOME 9 | KZN PGDS | STRATEGIC OBJECTIVE | STRATEGIC OBJECTIVE | IDP/ SDBIP REF NO. | PROJECTS | Function/Sub-Function | Regional Identifier | KEY PERFORMANCE INDICATOR (KPI) | UNIT OF MEASURE | BASELINE | ANNUAL TARGET | ORIGINAL BUDGET | 1ST SPECIAL ADJUSTMENTS BUDGET | 1ST QUARTER TARGET End Sept 2020 | 2nd QUARTER TARGET End Dec 2020 | 3rd QUARTER TARGET End March 2021 | 4th QUARTER TARGET End June 2021 | SOURCE OF FUNDNG | MSC | Costing | WARDS | EVIDENCE | WEIGHTING | RESPONSIBLE DEPARTMEN/UNIT
DEPARTMENTAL SDBIP
COMMUNITY AND SOCIAL SERVICES PERFORMANCE PLAN 2020-2021
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of infrastructure | COM-01 | Procurement of the Library Books | Community and Social Services | Administration | Number of Books purchased by target date. | Number | New measure | 600 Books purchased by 31 March 2021 | 100000 | N/A | 200 books purchased by September 2020 | 400 books purchased by December 2020 | 600 books purchased by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | Wards 15 and 02 | Purchase Invoices and Delivery Notes | H | Manager: Community Services
[5 empty] | COM-02 | Municipal Waste collections | Community and Social Services | Administration | Number of Municipal waste collections done by target date. | Number | Achieved. | 912 Municipal waste collections done by 30 June 2021 | 950000 | N/A | 228 collections done from all sites by 30 September 2020 | 456 collections done from all sites by 31 December 2020 | 684 collections done from all sites by 31 March 2021 | 912 collections done from all sites by 30 June 2021 | Equitable Share | COMM-BUDG | Default | N/A | EPWP registers. | H | Manager: Community Services
[5 empty] | COM-03 | Municipal Waste collection | Community and Social Services | Administration | Percentage of households earning less than R3200 per month with access to waste collection by target date. | Percetage | Achieved. | 100% of Households access to waste collection by 30 June 2021 |  | N/A | 100% Households access to waste collection by 30 September 2020 | 100% Households access to waste collection by 31 December 2020 | 100% Households access to waste collection by 31 March 2021 | 100% Households access to waste collection by 30 June 2021 | Equitable Share | COMM-BUDG | Default | N/A | Indigent register. Waste collection registers. Truck schedule. | H | Manager: Community Services
[5 empty] | COM-04 | Integrated Waste Management Plan | Community and Social Services | Administration | Reviewed Integrated Waste Management Plan by target date. | Date | New measure | Final Reviewed Integrated Waste Management Plan by 30 June 2021 | 500000 | N/A | N/A | N/A | N/A | Final Reviewed Integrated Waste Management Plan by 30 June 2021 | Equitable Share | COMM-BUDG | Default | N/A | Council Resolution | H | Manager:Community Services
[5 empty] | COM-05 | Refurbished and Functional Telecentre | Community and Social Services | Administration | Number of Refurbished and Functional Telecentre by target date. | Number | New measure | 1 Refurbished and Functional Telecentre complete by 30 June 2021 | 500000 | N/A | Siiting of the Bid Committees by September 2020 | Procurement of the Service Provider by 31 December 2020 | Commencement of the Refurbishment BY 31 March 2021 | 1 Refurbished and Functional Telecentre by 30 June 2021 | Equitable Share | COMM-BUDG | Default | N/A | Appointment Letter, Progress Report & Completion Certificate | L | Manager: Community Services
[5 empty] | COM-06 | Sanitisation of Community Spaces COVID- 19 Respond |  |  | Percentage of Community spaces sanitised for COVID-19 respond completed by target date. | Percetage | New measure | 100% of Santisation of Community Spaces for COVID-19 respond completed by 31 March 2021 | 0 | 500000 | N/A | 100% Community spaces sanitised for COVID-19 respond completed by 31 December 2020 | 100% Community spaces sanitised for COVID-19 respond completed by 31 March 2021 | N/A | Equitable Share |  |  | All Wards | Community spaces report | H | Director:Community and Social Services
[5 empty] | COM-07 | Burial Assistance COVID-19 Respond |  |  | Percentage of applications processed for Burial Assistance COVID-19 respond completed by target date. | Percetage | New measure | 100% of Applications processed for Burial Assistance for COVID-19 respond completed by 30 June 2021 | 0 | 577000 | N/A | N/A | N/A | 100% of applications processed for Burial Assistance for COVID-19 respond completed by 30 June 2021 | Equitable Share |  |  | All Wards | Burial appilcations | H | Manager: Community Services
|  |  | To promote education of vulnerable childrens/youth; To ensure co-ordination and alignment of developmental programmes of the municipality with other spheres of government and To promote sports within local communities. |  | COM-08 | Men's Dialogue | Community and Social Services | Administration | Number of dialogues for men held by target date. | Number | Achieved.1 Men's Dialogue held in 30 July 2019 | 2 Men's Dialogues held by 30 June 2021 | 160000 | N/A | 1 Men's Dialogue held by 30 September 2020 | N/A | N/A | 1 Men's Dialogue held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register and Program | L | Manager Social Cohesion
[5 empty] | COM-09 | Womens day Commemoration Dialogues | Community and Social Services | Administration | Number of Women's Commemoration Dialogues held by by target date. | Number | Achieved.1 Womens day Commemoration Dialogue held on 22 August 2019 | 2 Women's Commemoration Dialogue held by 30 June 2021 | 300000 | N/A | Women'sCommemoration Dialogue held by 30 September 2020 | N/A | N/A | Women'sCommemoration Dialogue held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register | L | Manager Social Cohesion
[5 empty] | COM-10 | Disability Safety awareness | Community and Social Services | Administration | Number of Safety awareness for the disability hosted by target date. | Number | Not achieved. | 1 Disability Safety Awareness hosted by 31 December 2020 | 120000 | N/A | N/A | 1 Disability Safety awareness by 31 December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | COM-11 | Disability Games | Community and Social Services | Administration | Number of games for the disability hosted by target date. | Number | Achieved. | 1 Disability game hosted by 31 March 2021 | 180000 | N/A | N/A | N/A | 1 Disability game hosted by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register | L | Manager Social Cohesion
[5 empty] | COM-12 | Dress a child uniform campaign | Community and Social Services | Administration | Number of campaigns for Dress a child uniform held by target date. | Number | Achieved. | 1 Dress a child uniform campaign held by 31 March 2021 | 530000 | N/A | N/A | N/A | Dress a child uniform campaign held by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register | H | Manager Social Cohesion
[5 empty] | COM-13 | Ingoma Yesintu Program | Community and Social Services | Administration | Number of Ingoma Yesintu programs held by target date. | Number | Not achieved. | 2 Ingoma Yesintu programs held by 31 March 2021 | 190000 | N/A | N/A | 1 Ingoma Yesintu program held by 31 December 2020 | 1 Ingoma Yesintu program held by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance register | L | Manager Social Cohesion
[5 empty] | COM-14 | Orphans and Farm Workers Program | Community and Social Services | Administration | Number of programs for Orphans and Farm workers held by target date. | Number | New measure | 1 of Orphans and Farm workers Programs held by 30 June 2021 | 180000 | N/A | N/A | N/A | N/A | 1 Orphans and Farm workers programs held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | 1,8,3 and 12 | Attendance Register | M | Manager Social Cohesion
[5 empty] | COM-15 | Christmas Program for Senior Citizens | Community and Social Services | Administration | Number of Christmas programs for Senior citizens held by target date. | Number | Achieved.1 Christmas program held on the 20 December 2019 | 1 Christmas Program for Senior Citizens held by 31 December 2020 | 250000 | N/A | N/A | 1 Christmas program for Senior Citizens held by 31 December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | attendance register | L | Manager Social Cohesion
[5 empty] | COM-16 | Golden Games | Community and Social Services | Administration | Number of event for Golden games hosted by target date. | Number | Achieved. The Golden Games target was met on 17 July 2019 | 1 Golden Games hosted by 30 June 2021 |  | N/A | N/A | N/A | N/A | 1 Golden games hosted by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | attendance register | L | Manager Social Cohesion
[5 empty] | COM-17 | Umkhosi Wesintu | Community and Social Services | Administration | Number of events for Umkhosi Wesintu hosted by target date. | Number | New measure | 1 Umkhosi Wesintu events hosted by 30 September 2020 | 530000 | N/A | 1 Umkhosi Wesintu event hosted by 30 September 2020 | N/A | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance register | L | Manager Social Cohesion
[5 empty] | COM-18 | Moral Regeneration event | Community and Social Services | Administration | Number of event for Moral Regeneration hosted by target date. | Number | Not achieved. | 1 Moral Regeneration event hosted by 30 June 2021 | 90000 | N/A | N/A | N/A | N/A | 1 Moral Regeneration event hosted by June 2021 | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register | L | Manager Social Cohesion
[5 empty] | COM-19 | Civil Society Forum | Community and Social Services | Administration | Number of Civil Society Forums held by target date. | Number | New measure | 4 Civil Society Forums held by 30 June 2021 | 15000 | N/A | 1 Civil Society Forum by 30 September 2020 | 1 Civil Society by December 2020 | 1 Civil Society by 31 March 2021 | 1 Civil Society by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | COM-20 | Ndwedwe HIV/Aids Day event | Community and Social Services | Administration | Number of HIV/Aids Day events hosted by target date. | Number | Achieved. Ndwedwe Aids Day events held on 28 November 2019 | 1 HIV/Aids Day event hosted by 30 December 2020 | 310000 | N/A | N/A | 1 HIV/Aids Day event hosted by 31 December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register | M | Manager Social Cohesion
[5 empty] | COM-21 | 16 Days of Activism | Community and Social Services | Administration | Number of activism programs for 16 days held by target date. | Number | Achieved.16 Days of Activism was held on 22 October & 3 December 2019 | 1 16 Days of Activism program by 31 December 2020 | 100000 | N/A | N/A | 1 Activism program by 31 December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | COM-22 | Umkhosi Womhlanga Ndwedwe Reed Dance Celebrations | Community and Social Services | Administration | Number of Maidens participated in the Umkhosi Womhlanga Ndwedwe Reed Dance Celebrations events hosted by target date. | Number | Achieved. Umkhosi Womhlanga was held on 6 -8 September 2019. | 1 Umkhosi Womhlanga Ndwedwe Reed Dance Celebrations event held by 31 December 2020 490 Maidens participated in the Umkhosi Womhlanga September 2020 | 400000 | N/A | N/A | 1 Umkhosi Womhlanga Ndwedwe Reed Dance Celebrations event held by 31 December 2020 Maidens participated in the Umkhosi Womhlanga September 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register of Participants | L | Manager Social Cohesion
[5 empty] | COM-23 | Operation sukuma sakhe(OSS) local task team meetings | Community and Social Services | Administration | Number of OSS meetings held by target date. | Number | Not achieved. | 8 OSS meetings held by 30 June 2021 | 100000 | N/A | 2meetings held by 30 September 2020 | 2meetings held 31 December 2020 | 2meetings held by 31 March 2021 | 2meetings held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | L | Manager Social Cohesion
[5 empty] | COM-24 | Operation MBO | Community and Social Services | Administration | Number of Operation MBO meetings held by target date. | Number | Not achieved. | 4 Operation MBO meetings held by 30 June 2021 | 100000 | N/A | 1meeting held by 30 September 2020 | 1 meeting held by 31 December 2020 | 1 meeting held by 31 March 2021 | 1 meeting held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register | L | Manager Social Cohesion
[5 empty] | COM-25 | OSS Indaba | Community and Social Services | Administration | Number of OSS Indaba sessions held by target date. | Number | New measure | 1 OSS Indaba session held by 30 September 2020 | 15000 | N/A | 1 OSS session held by 30 September 2020 | N/A | N/A | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register | L | Manager Social Cohesion
[5 empty] | COM-26 | Ndwedwe Social Ills Awareness for Breast Cancer | Community and Social Services | Administration | Number of awareness for Social Ills for Breast Cancer held by target date. | Number | New measure | 1 Ndwedwe Social Ills Awareness for Breast Cancer held by 31 December 2020 | 15000 | N/A | N/A | 1 Social ill awareness for Breast Cancer held by December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register of Participants | M | Manager Social Cohesion
[5 empty] | COM-27 | Disability and Senior Citizens Forum | Community and Social Services | Administration | Number of forums for Disability and Senior Citizens held by target date. | Number | New measure | 4 Disability and Senior Citizens Forums held by 30 June 2021 | 15000 | N/A | 1 Disability and Senior Citizens forum by 30 September 2020 | 1 Disability and Senior Citizens forum by 31 December 2020 | 1 Disability and Senior Citizens forum by 31 March 2021 | 1 Disability and Senior Citizens forum by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register of Participants | L | Manager Social Cohesion
[5 empty] | COM-28 | Local Aids Committee Meetings | Community and Social Services | Administration | Number of Local Aids Committee meetings held by by target date. | Number | Not achieved. | 4 Local Aids Committee meetings held by 30 June 2021 | 15000 | N/A | 1meeting held by 30 September 2020 | 2meeting held by 31 December 2020 | 3meeting held by 31 March 2021 | 4meeting held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | L | Manager Social Cohesion
[5 empty] | COM-29 | Ndwedwe Safety Prayer | Community and Social Services | Administration | Number of Safety Prayers for Ndwedwe hosted by target date. | Number | Achieved. | 1 Safety Prayer for Ndwedwe hosted by 31 December 2020 | 15000 | N/A | N/A | 1 Prayer hosted by 31 December 2020 | N/A | N/A | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register of Participants | M | Manager Social Cohesion
[5 empty] | COM-30 | Child Protection Program | Community and Social Services | Administration | Number of Programs for Child Protection held by target date. | Number | Not achieved. | 1 Child Protection Programs held by 30 June 2021 | 15000 | N/A | N/A | N/A | N/A | 1 Child Protect Program held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | tbc | Attendance Register of Participants | M | Manager Social Cohesion
[5 empty] | COM-31 | Mandela Day Program | Community and Social Services | Administration | Number of programs for Mandela day held by target date. | Number | New measure | 1 Mandela Day Program held by 30 September 2020 | 15000 | N/A | 1 Mandela Day program held by 30 September 2020 | N/A | n/a | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register of Participants | L | Manager Social Cohesion
[5 empty] | COM-32 | Dress a Child Covid 19 Respond | Community and Social Services | Administration | Number of campaigns for Dress a Child Covid 19 Respond held by target date. | Number | New measure | 2 Dress a Child Covid 19 Respond held by 31 March 2021 | N/A | 1500000 | N/A | 1 Dress a Child Covid 19 Respond campaign to be held by 31 December 2020 | 1 Dress a Child Covid 19 Respond campaign held by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | All wards | Attendance Register of Participants | H | Manager Social Cohesion
|  |  | To ensure prevention and mitigation against disasters |  | COM-33 | Disaster Awareness Campaigns | Community and Social Services | Administration | Number of Community awareness campaigns held by target date. | Number | Achieved. 4 Awareness campaigns were held. | 4 Community awareness campaigns held by 30 June 2021 | 0 | N/A | 1 Awareness campaign held by 30 September 2020 | 2 Awareness campaign held by 31 December 2020 | 3 Awareness campaign held by 31 March 2021 | 4 Awareness campaign held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | Clustered wards | Attendance Register of Participants | M | Director:Community and Social Services
[5 empty] | COM-34 | Disaster Management Advisory Meetings | Community and Social Services | Administration | Number of Disaster Management Advisory meetings held by target date. | Number | Not achieved. 2 Advisory meetings were held. | 4 Disaster Management Advisory meetings held by 30 June 2021 | 0 | N/A | 1 Advisory meeting held by 30 September 2020 | 2 Advisory meeting held by 31 December 2020 | 3 Advisory meeting held by 31 March 2021 | 4 Advisory meeting held by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Director:Community and Social Services
[5 empty] | COM-35 | Local Disaster Management Workshops | Community and Social Services | Administration | Number of Local Disaster Management workshops held by target date. |  | Not achieved. 1 Local Disaster Management Workshop held. | 2 Local Disaster Management Workshops held by 31 March 2021 | 0 | N/A | 1 Workshop held by 30 September 2020 | N/A | 2 Workshop held by 31 March 2021 | N/A | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Director:Community and Social Services
[5 empty] | COM-36 | Disaster Risk Reduction | Community and Social Services | Administration | Review Disaster Management Sector Plan by target date. | Number | New measure | Reviewed Disaster Management Sector Plan by 30 June 2021 | 200000 | N/A | Engagement and consultation with stakeholders to update Terms Of Reference To annually review the Plan by 30 September 2020. | Solicit Inputs from disaster management stakeholders and incorporate them in the Disaster Management Plan by 31 December 2020 | Consolidation of inputs as received from different disaster management stakeholders by 31 March 2021 | Consolidation of inputs as received from different disaster management stakeholders and reviewed Disaster plan by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All Wards | Reviewed Disaster Management Plan | H | Director:Community and Social Services
[5 empty] | COM-37 | Disaster Management Emergency Relief | Community and Social Services | Administration | Number of monthly consolidated incidents/disasters reports submitted to the Provincial disaster management centre by target date. | Number | New measure | 12 Monthly reports submitted to the Provincial disaster management centre by 30 June 2021 | 900000 | N/A | 3 monthly reports submitted to the Provincial disaster management centre by 30 September 2020 | 3 monthly reports submitted to the Provincial disaster management centre by by 31 December 2020 | 3 monthly reports submitted to the Provincial disaster management centre by the 8th by 31 March 2021 | 3 monthly reports submitted to the Provincial disaster management centre by 30 June 2021 | Equitable Share | COMM-BUDG | Default | All Wards | Disaster Management Records, Monthly reporting | H | Director:Community and Social Services
|  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. |  | COM-38 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of progress reports on Risk Management by target date. | Number | New measure | 4 Progress Reports on Risk Management by 30 June 2021 | 0 | N/A | 1 Progress Report on Risk Management by 30 September 2020 | 1 Progress Report on Risk Management by 31 December 2020 | 1 Progress Report on Risk Management by held by 31 March 2021 | 1 Progress Report on Risk Management 30 June 2021 | N/A | MM-BUDG | Default | All Wards | Risk registers | H | Director:Community and Social Services