## MM Org SCard
DEPARTMENT: OFFICE OF THE MUNICIPAL MUNICIPAL
MUNICIPAL MANAGER: MR M.F.HADEBE
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Key Performance Indicator |  | Unit of Measure | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Management comments reason for 2nd Adjustments | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[9 empty] | Baseline |  |  | End September 2019 | End December 2019 | End March 2020 | End June 2020 |  |  |  |  | Reason for Adjustments
ORGANISATIONAL SCORECARD 2019-2020
MUNICIPAL MANAGER PERFORMANCE PLAN
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 1 | MM-01-19/20 | Internal Audit Reporting to Audit Committee | Number of reports submitted to Audit Committee by 30 April 2020 | Achieved.4 reports | Number | 4 reports submitted to Audit Committee by 30 April 2020 | 1 report submitted by 31 July 2019 | 1 report submitted by 30 October 2019 | 1 report submitted by 31 January 2020 msa 57 section | 1 report submitted by 30 April 2020 |  | 0 | 0 |  |  | 0 | MM-BUDG | Default | Municipality | Council Resolution | H | Internal Audit
[5 empty] | 2 | MM-02-19/20 | Tabling of Annual Report 2018/2019 to Council within 9 months after the end of a financial year | Approved Annual Report for 2018/2019 by 31 March 2020 | Achieved. Adopted Annual report | Date | Adopted Annual Report by 31 March 2020 | Draft Annual Performance Report adopted by Council by August 2019 | N/A | Final Annual Report approved by Council by 31 March 2020 | N/A |  | 0 | 0 |  |  | 0 | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 3 | MM-03-19/20 | Tabling of Oversight report on the AR 2018/2019 to Council by no later than 2(two) months from the date in which the AR was tabled as per MFMA Section 127 (5) | Approved Oversight Report for 2018/2019 by 31 March 2020 | Achieved. Adopted Oversight report | Date | Adopted Oversight Report for 2018/2019 by 31 March 2020 | N/A | N/A | Oversight Report Approved by Council 31 March 2020 | N/A |  | 0 | 0 |  |  | Equitable Share | MM-BUDG | Default | Municipality | Council Resolution | H | Chaiperson MPAC
[5 empty] | 4 | MM-04-19/20 | IDP/Budget/PMS Process Plan 2020/2021 | Adoption of Process Plan by 30 September 2019 | Achieved. Adopted Process Plan | Date | Process Plan adopted by 30 September 2019 | Adoption of Process Plan for 2020/2021 by 30 September 2019 | N/A | N/A | N/A |  | 0 | 0 |  |  | 0 | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 5 | MM-05-19/20 | Speaker Izimbizo | Number of Izimbizo Hosted by June 2020 | 2 | Number | 1 (was 2) Izimbizo hosted by 31 December 2019 (was 30 June 2020) | N/A | 1 Izimbizo 31 December 2019 | N/A | N/A (1 Izimbizo by 30 June 2020) | N/A-The Izimbizo will not be convened in the last quarter subject to COVID 19. | 760000 | 1206800 | R 1 235 800.00 | Due to COVID 19 Disaster Mngt. Act regulations., large gatherings have been restricted. | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register of Participants | M | Manager Public Participation
[5 empty] | 6 | MM-06-19/20 | Mayoral/IDP Izimbizo | Number of mayoral/ IDP Izimbizo by 30 June 2020 | 8 | Number | 4 (was 8) Mayoral/ IDP Izimbizo by 31 December 2019 (was 30 June 2020) | N/A | 4 Izimbizo by 31 December 2019 | N/A | N/A (4 Izimbizo by 30 June 2020) | N/A-The Izimbizo will not be convened in the last quarter subject to COVID 19. | 2520000 | 2520000 | R 1 595 752.60 | Due to COVID 19 Disaster Mngt. Act regulations., large gatherings have been restricted. | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 7 | MM-07-19/20 | Ward Committees Training | Number of Ward Committees training by 31 December 2019 | 1 | Number | 1 Training conducted by 31 December 2019 | N/A | 1 Training conducted by 31 December 2019 | N/A | N/A |  | 3958000 | 4196091.58 |  |  | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 8 | MM-08-19/20 | Ward Committees Quartely Meeting | Number of Ward Committee meetings hosted by 31 March 2020 (was 30 June 2020) | 4 | Number | 3 (was 4) Ward Committee meetings hosted bby 31 March 2020 (was 30 June 2020) | 1 Ward Committee Meeting by 30 September 2019 | 1 Ward Committee Meeting by 31 December 2019 | 1 Ward Committee Meeting by 31 March 2020 | N/A (1 Ward Committee Meeting by 30 June 2020) | The meeting will not be convened in the last quarter subject to COVID 19. |  |  |  | Due to COVID 19 Disaster Mngt. Act regulations., large gatherings have been restricted. | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 9 | MM-9-19/20 | Mayoral slots | Number of Media slots conducted by 30June 2020 | Not achieved. | Number | 20 Media Slots Conducted by 30 June 2020 | 5 Media slots by 30 September 2019 | 5 Media slots by 31 December 2019 | 5 Media slots by 31 March 2020 | 5 Media slots by 30 June 2020 |  | 810000 | 810000 | R1 696 375.00 |  | Equitable Share | MM-BUDG | Default | all wards | Attendance Register | M | Manager Communication
|  |  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | 10 | MM-10-19/21 | Monitoring performance of effective enterprise risk management | Number of risk registers updated by 30 June 2020 | New measure | Number | 4 Risk registers by 30 June 2020 | 1 Risk register updated by 30 September 2019 | 1 Risk registers updated by 31 December 2019 | 1 Risk registers to be updated by held by 31 March 2020 | 1 Risk registers to be updated held by 30 June 2020 |  | 0 | 0 | 0 |  | Equitable share | MM-BUDG | Default | All Wards | Risk registers | H | IDM Risk Officer
[5 empty] | 11 | MM-11-19/20 | Review performance of effective enterprise risk management | Number of ethics/Risk Committee meetings held by 30 June 2020 | New measure | Number | 3 (was 4) Ethics/Risk Committee meetings held by 30 June 2020 | 1 Ethics/Risk Committee meeting held by 30 September 2019 | 1 Ethics/Risk Committee meeting held by 31 December 2019 | N/A (was 1 Ethics/Risk Committee meeting held by 31 March 2020) | 1 Ethics/Risk Committee meeting held by 30 June 2020 |  | 0 | 0 | 0 | Due to capacity constraints the Q3 target has changed. | Equitable share | MM-BUDG | Default | All Wards | Attendance risk registers | H | IDM Risk Officer
[5 empty] | 12 | MM-12-19/20 | Risk Management | Risk assessment process for the 2020/2021 finalised by 30 June 2020 | New measure | Date | Risk assessment process for the 2020/2021 finalised by 30 June 2020 | N/A | N/A | N/A | Develop a 2021 Risk register by 30 June 2020 (was Conduct risk assessment for 2020/2021 & updated risk register finalised from process) | Project scope has been amended. | 0 | 0 | 0 |  | Equitable share | MM-BUDG | Default | All Wards | Risk assessment | H | IDM Risk Officer
[5 empty] | 13 | MM-13-19/20 | Enterprise Risk Management Register | Submit 2020/2021 Enterprise Risk Management Register to Risk Mngt Committee for approval by 30 June 2020 | New measure | Date | Submit 2020/2021 Enterprise Risk Management Register to Risk Mngt Committee for approval by 30 June 2020 (was 31 December 2019) | Submit Enterprise Risk Register to MANCO Risk Management Committee and Council by 30 September 2019 | N/A (was Submit the approved risk register to Heads of departments by 31 December 2019) | N/A | Submit 2020/2021 Enterprise Risk Management Register to Risk Mngt Committee for approval by 30 June 2020 (was N/A) |  | 0 | 0 | 0 |  | Equitable share | MM-BUDG | Default | All Wards | Enterprise Risk Management Register | H | IDM Risk Officer
[5 empty] | 14 | MM-14-19/20 | Enterprise Risk Management Policy and Strategy | Reviewed Enterprise Risk Management Framework and Strategy by 30 June 2020 | New measure | Date | Reviewed Risk Mngt Framework and Strategy by 30 June 2020 | N/A | N/A | N/A | Reviewed Risk Mngt Framework and Strategy by 30 June 2020 |  | 0 | 0 | 0 |  | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | IDM Risk Officer
[5 empty] | 15 | MM-15-19/20 | Conduct awareness on ERM processes and policies to all staff and Councillors | Number of Enterprise Risk Management workshops held by 30 June 2020 | New measure | Number | 1 (was 2) Enterprise Risk Management workshops held by 30 June 2020 | N/A | N/A | N/A (was 1 Workshop held by 31 March 2020) | 1 Workshop held by 30 June 2020 |  | 0 | 0 | 0 | Due to capacity constraints the meeting will take place in quarter 4. Due to COVID 19 Disaster Mngt. Act regulations., large gatherings have been restricted. | Equitable share | MM-BUDG | Default | All Wards | Attendance risk registers | H | IDM Risk Officer
[5 empty] | 16 | MM-16-19/20 | Anti-Fraud and Corruption Strategy & Policy | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2020 | New measure | Date | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2020 | N/A | N/A | N/A | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2020 |  | 0 | 0 | 0 |  | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | IDM Risk Officer
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 17 | MM-17-19/20 | Youth Plumbing Skills Programme | Number of Youth was assisted by 30 September 2019 (was 31 March 2020) | New measure | Number | 30 (was 60) Youth programmes assisted by 30 September 2019 (was 31 March 2020) | 30 Youth assisted by 30 September 2019 | N/A | N/A (was 30) Youth assisted by 31 March 2020 | N/A |  | 100000 | 0 |  | The project target was amended due to budget constraints. | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 18 | MM-18-19/20 | Nongoma Royal Reed Dance | Number of Maidens participated in the Reed Dance by 30 September 2019 | Achieved. Nongoma Royal Reed dance participated | Number | 500 Maidens participated by 30 September 2019 | 500 Maidens participated by 30 September 2019 | N/A | N/A | N/A |  | 200000 | 200000 |  |  | Equitable Share and Department of Arts and Culture | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 19 | MM-19-19/20 | Grade 9 and Grade 10 Career Guidance programme | Number of Career Guidance programmes held by 30 September 2019 | Achieved. 1 | Number | 1 Career Guidance programme held by 30 September 2019 | 1 Career Guidance programme held by 30 September 2019 | N/A | N/A | N/A |  | 150000 | 150000 |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 20 | MM-20-19/20 | Youth Arts and Culture events (was Festival) | Number of Arts and Culture Festival hosted by 31 December 2019 | Achieved. 1 | Number | 1 Arts and Culture Festival hosted by 31 December 2019 | Festival Cluster Festival Build-up Competitions by 30 September 2019 | 1 Arts and Culture Festival hosted by 31 December 2019 | N/A | N/A |  | 100000 | 100000 |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 21 | MM-21-19/20 | Examination Prayer Programme | Number of Examination Prayer Programme hosted by 31 December 2019 | Achieved. 1 | Number | 1 Prayer Programme hosted by 31 December 2019 | N/A | 1 Prayer Programme hosted by 31 December 2019 | N/A | N/A |  | 200000 | 200000 |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 22 | MM-22-19/20 | Youth (Sewing and Garmet making skills) programme | Number of Youth trained by 31 December 2019 (was30 June 2020) | Not achieved. | Number | 40 (was 80) Youth trained by 31 December 2019 (was30 June 2020) | N/A | 40 Youth trained by 31 December 2019 | N/A | N/A (was40 Youth trained by 30 June 2020) |  | 100000 | 0 |  | The project will not continue due to budget constraints. | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 23 | MM-23-19/20 | Youth Farming Programme | Number of Youth trained by 30 September 2019 (was31 March 2020) | Achieved. | Number | 40 (was 80) Youth trained by 30 September 2019 (was31 March 2020) | 40 Youth Trained by 30 September 2019 | N/A | N/A(was40 Youth trained by 31 March 2020) | N/A |  | 120000 | 120000 |  | The project tagert was amended due to budget constraints | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 24 | MM-24-19/20 | Drivers Licence Programme Code 10 | Number of Youth trained by 30 June 2020 | Not achieved. | Number | 19 Youth trained by 30 June 2020 | N/A | 19 Youth trained by 31 December 2019 | N/A | 19 Youth trained by 30 June 2020 |  | 200000 | 200000 |  | The project was readvertised. Project Warded in the Feb 2020 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 25 | MM25-19/20 | Youth Art Work Programme | Number of Youth assisted by 31 December 2019 (was30 June 2020) | Not achieved. | Number | 20 ( was40) Youth asssisted by 31 December 2019 (was30 June 2020) | N/A | 20 Youth assisted by 31 December 2019 | N/A | N/A (was 20 Youth assisted by 30 June 2020) |  |  |  |  | The project annual target was amended due to budget constraints | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 26 | MM-26-19/20 | Youth Council Advisory Meeting | Number of Youth Council Advisory meetings held by 31 December 2019 (was 30 June 2020) | Achieved. | Number | 2(was 4 ) Youth Council Advisory meetings held by 31 December 2019 (was 30 June 2020) | 1 Youth Council Advisory meeting held by 30 September 2019 | 1 Youth Council Advisory meeting held 31 December 2019 | N/A (was1 Youth Council Advisory meeting held by 31 March 2020) | N/A (was1 Youth Council Advisory meeting held by 30 June 2020) |  |  |  |  | No quorm to hold the meeting as the Chairperson and secreatait has been elected to serve at the district advisory team meeting | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 27 | MM-27-19/20 | Job Readiness Programme | Number of Youth assisted by 30 June 2020 | Not achieved. | Number | 100 (was 200) Youth assisted by 31 December 2019 (was 30 June 2020) | N/A | 100 Youth assisted by 31 December 2019 | N/A (was30 Youth assisted by 31 March 2020) | N/A (was70 Youth assisted by 30 June2020) |  |  |  |  | The project annual target was amended due to budget constraints | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 28 | MM-28-19/20 | Youth Campaign on social ills | Number of Youth Campaigns hosted by 31 December 2019 | Achieved. | Number | 1 Youth Campaign hosted by by 31 December 2019 | N/A | 1 Youth Campaign hosted by 31 December 2019 | N/A | N/A | [5 empty] | Equitable Share and Department of Arts and Culture | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 29 | MM-29-19/20 | Youth in business seminar | Number of Youth trained by 31 December 2019 (30 June2020) | New measure | Number | 10 (was 20 Youth trained by 31 December 2019 (30 June2020) | N/A | 10 Youth trained 31 December 2019 | N/A | N/A (was 10 Youth trained by 30 June2020) |  |  |  |  | The project annual target was amended due to budget constraints | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 30 | MM-30-19/20 | Sports Development programmes | Number of Sports development programmes to be held by 31 March 2020 (was 30 June 2020) | Achieved | Number | 29 (was 47) Sports development programmes to be held by 31 March 2020 (was 30 June 2020) | 12 Sports development programmes to be held by 30 September 2019 | 5 Sports development programmes to be held by by 31 December 2019 | 12 Sports development programmes to be held by 31 March 2020 | N/A (18 Sports development programmes to be held by 30 June 2020) | The programs will not be convened in the last quarter subject to COVID 19. | 600000 | 609999.04 | R 494 129.04 | Due to COVID 19 Disaster Mngt. Act regulations., large gatherings have been restricted. | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
[5 empty] | 31 | MM-31-19/20 | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance | Number of events hosted by 31 December 2019 | Achieved. | Number | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2019 | Preparations for Salga Games by 30 September 2019 | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2019 | N/A | N/A |  | 595000 | 559900 |  |  | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 32 | MM-32-19/20 | Women in Sport Symposium and sport day | Number of events hosted by 30 September 2019 (was31 March 2020) | Project was cancelled during the adjustment budget due to budget constraints. | Number | 1(was 2) Women in Sport Symposium and sport day hostedby 30 September 2019 (was31 March 2020) | 1 Women in Sport Symposium and sport day hosted by 30 Sep 2019 | N/A | N/A (was 1 Women in sport symposuim and sport tournament hosted by 31 March 2020) | N/A |  | R150,000,00 |  |  | The project target was amend due to budget constraints. | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
|  | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 33 | MM-33-19/20 | Disability Sport Day | Number of events hosted by 30 September 2019 (was 30 June 2020) | Project was cancelled during the adjustment budget due to budget constraints. | Number | 1 (was 2) Disability Sport Day by 30 September 2019 (was 30 June 2020) | 1 Disability Sport Day by 30 September 2019 | N/A | N/A | N/A (1 Disability Sport Day by 30 June 2020) |  | R50,000,00 |  |  | The project target was changed in Q4 due to budget constraints | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
[5 empty] | 34 | MM-34-19/20 | ECD's sport day | Number of events hosted by 30 September 2019 (was 30 June 2020) | Achieved. | Number | 1 (was 2) ECD's sport day by 30 September 2019 (was 30 June 2020) | 1 ECD's sport day by 30 September 2019 | N/A | N/A | N/A (was 1 ECD's sport day by 30 June 2020) |  | R20,000,00 |  |  | The project target was amend due to budget constraints | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
[5 empty] | 35 | MM-35-19/20 | Ndwedwe SAFA Associations Awards | Number of events hosted by 30 October 2019 | New measure | Number | 1 Ndwedwe SAFA Awards events by 30 October 2019 | N/A | 1 Ndwedwe SAFA Awards events by 30 October 2019 | N/A | N/A |  | 70000 |  |  |  | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 18 | TS-18-19/20 | Construction of Technical Dept Offices | Construction to be completed- (Parking,electrification, fencing to be completed by 31 March 2020 (was commisioning, operating documentation/as built) by 31 December 2019 | Not achieved. Service provider to be apppointed to complete the construction in the new financial year. | Date | Construction to be completed- (Parking,electrification, fencing to be completed by 31 March 2020 (was commisioning, operating documentation/as built) by 31 December 2019 | Construction (Building roof, Wall plastering, floor tilling, and plumbing) to be completed by 30 September 2019 | Construction (Parking,electrification, fencing, commisioning, operating documentation/as built) to be completed by 31 December 2019 | Construction (Parking,electrification, fencing) to be completed by 31 March 2020 (was N/A) | N/A |  | 4800000 | 6130000 |  | Due to the delays with the unforeseen weather, the project has been extended. | Internal | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 34 | TS-34-19/20 | EPWP - Waste management | Number of work opportunities created by 30 June 2020 (was 30 September 2019) | Not Achieved. Due to budget constraints only 76 instead of 120 workers were employed. This project has also been budgeted for in the 2019/2020 new financial year. | Number | 73 (was 75) EPWP work opportunities created by 30 June 2020 (was 30 September 2019) | 75 EPWP work opportunities created by 30 September 2019 | N/A | N/A | 73 EPWP work opportunities created by 30 June 2020 2019 (was N/A) |  | 1348000 | 1348000 |  | The project has been amended due to resignations and deaths. | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works
[5 empty] | 2 | COM-02-19/20 | Municipal Waste collection | Number of Municipal waste collections by 30 June 2020 | Achieved. | Number | 912 Municipal waste collections by 30 June 2020 | 228 collections done from all sites by 30 September 2019 | 228 collections done from all sites by 31 December 2019 | 228 collections done from all sites by 31 March 2020 | 228 collections done from all sites by 30 June 2020 |  | 900000 | 623567.01 |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager:Community Services
Local Economic Development | A responsive & accountable, effective & efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 2 | EDP-02-19/20 | Ndwedwe Land Use Managament System | Adoptation of Final LUMS document to be completed by 30 June 2020 | Date | New measure | 2nd Draft document produced by 30 June 2020 (was Adoption of Final LUMS document to be completed by 30 June 2020 ) | Appointment of the Service provider by 30 September 2019 | First Draft LUMS document produced by 31 December 2019 | N/A (was 2nd Draft document produced by 31 March 2020) | 2nd Draft document produced by 30 June 2020 (was Adoption of Final LUMS document to be completed by 30 June 2020 ) |  | 200000 | 200000 |  |  | Internal Funding | EDP-BUDG | Default | All wards | Final LUMS document | H | Director: EDP
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive & accountable, effective & efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 1 | CS-01- 19/20 | Implement the Workplace Skills Plan (WSP) | Number of WSP training programmes implemented as per WSP by end of financial year by 30 June 2020 | Achieved. 12WSP training programmes implemented | Number | 8 WSP training programmes implemented as per WSP by 30 June 2020 | 2WSP training programmes implemented as per WSP by 30 September 2019 | 2WSP training programmes implemented as per WSP by 31 December 2019 | 2WSP training programmes implemented as per WSP by 31 March 2020 | 2 WSP training programmes implemented as per WSP by 30 June 2020 |  | 1000000 | 1000000 |  |  | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 2 | CS-02- 19/20 | Filling budgeted posts | Number of Budgeted posts filled by 30 June 2020 | Achieved. 25 Budgeted posts | Number | 12 Budgeted posts be filled by 30 June 2020 | 3 Budgeted posts be filled by 30 September 2019 | 2 Budgeted posts be filled by 31 December 2019 | 5 Budgeted posts be filled by 31 March 2020 | 2 Budgeted posts be filled by 30 June 2020 |  | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Manager: Human Resource
[5 empty] | 6 | CS-11 19/20 | Implementation of Biometric Systerm Register | Number of biometric systems register implemented by 30 June 2020 | Achieved 12 reports prepared | Number | 12 x Biometric systerms reports presented by 30 June 2020 | 3x Biometric systerm reports presented by 30 September 2019 | 3x Biometric systerm reports presented by 31 December 2019 | 3x Biometric systerm reports presented by 31 March 2020 | 3x Biometric systerm reports presented by 30 June 2020 |  | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Biometrics Reports | H | Manager: IT
Financial Viability and Management | A responsive & accountable, effective & efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management. To achieve a clean audit opinion | 2 | F-02-19/20 | Financial Reporting | Number of Section 71 MFMA Reports submitted on time by 30 June 2020 | Achieved. | Number | 12 MFMA Reports submitted at the end 30 June 2020 | 3 monthly reports submitted by 30 September 2019 | 3 monthly reports submitted by 31 December 2019 | 3 monthly reports submitted by 31 March 2020 | 3 monthly reports submitted by 30 June 2020 |  | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 3 | F-02-19/20 | Financial Reporting | Number of Section 72 MFMA Reports sumbitted by 31 January 2020 | Achieved. | Number | 1 MFMA Reports submitted to Council by 31 Janaury 2020 | N/A | N/A | 1 MFMA report submitted to Council by 31 January 2020 | N/A |  | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 22 | F-19-19/22 | Maintain unqualified audit opinion | Maintain unqualified audit opinion by 31 December 2019 | Achieved. | AG Report | Unqualified audit report by the AG for 2018/2019 financial year by 31 December 2019 | Submission of AFS by 31 August 2019. | Unqualified audit report by 31 December 2019 | N/A | N/A |  | 0 | 0 |  |  | Equitable Share | FIN-BUDG | Default | N/A | Unqualified report from AG | H | CFO

## TECHNICAL
DEPARTMENT: TECHNICAL SERVICES
DIRECTOR: MR.D.H.MZOLO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator |  | Unit Measure | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
KPI Ref. No
[11 empty] | Baseline from 2018/2019 Financial Year |  |  | End September 2019 | End December 2019 | End March 2020 | End June 2020 |  |  |  | Reason for Adjustments
TOP LAYER SDBIP
DIRECTOR TECHNICAL SERVICES PERFORMANCE PLAN 2019-2020
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 1 | TS-01-19/20 | Nambithane Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 December 2019) | Achieved. Service provider has been appointed. | Number | 5km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was 31 December 2019) | 1km construction to be completed (Site establishment, drainange systems, layer works and ancillary works) by 30 September 2019 | 5km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 5km construction to be completed (layer works) by 31 March 2020 (was N/A) | 5km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was N/A) | 3500000 | 3500000 |  | The contractor was appointed late. | MIG | TECH-BUDG | Default | 5 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 2 | TS-02-19/20 | KwaNovimba Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 December 2019) | Achieved. Service provider has been appointed. | Number | 3km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was 31 December 2019) | 1km construction to be completed (Site establishment, drainange systems, layer works and ancillary works) by 30 September 2019 | 3km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 3km construction to be completed (layer works) by 31 March 2020 (was N/A) | 3km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was N/A) | 2900000 | 2700000 |  | The contractor was appointed late . | MIG | TECH-BUDG | Default | 18 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 3 | TS-03-19/20 | Chamani Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 December 2019) | Achieved. Service provider has been appointed. | Number | 1km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was 31 December 2019) | 0,5km construction to be completed (Site establishement, drainange systems, layer works and ancillary works) by 30 September 2019 | 1km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 1km construction to be completed (layer works) by 31 March 2020 (was N/A) | 1km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was N/A) | 1000000 | 772714.26 |  | Slow progress of the contractor. | MIG | TECH-BUDG | Default | 16 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 4 | TS-04-19/20 | Mwolokohlo to Sthupha Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 March 2020 | Achieved. The project has been advertised. | Number | 1,5km construction to be completed by 31 March 2020 | Appointment of service provider by 30 September 2019 | 0,5km construction to be completed (Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 1,5km construction to be completed (drainange systems, layer works and ancillary works) by 31 March 2020 | N/A | 2800000 | 1899968.27 |  |  | MIG | TECH-BUDG | Default | 11 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 5 | TS-05-19/20 | Water Fall Sportfield | Technical Services | Administration | Construction to be completed(Earthworks, Buildings/change rooms, Fencing, Plumbing) by 30 June 2020 (was 31 December 2019) | Not achieved. Construction activity not complete - Earthworks, Fencing | Date | Construction to be completed(Plumbing) by 30 June 2020 (was 31 December 2019) | Construction to be completed - Earthworks, Buildings/change rooms, Fencing by 30 September 2019 | Construction to be completed - Earthworks, Buildings/change rooms, Fencing, Plumbing by 31 December 2019 | Construction to be completed (Earthworks, Buildings/change rooms and Fencing) by 31 March (was N/A) | Construction to be completed (Plumbing) by 30 June 2020 (was N/A) | 3000000 | 3000000 |  | Due to slow progress of the contractor. | MIG | TECH-BUDG | Default | 3 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 6 | TS-06-19/20 | Ethafeni Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 March 2020) | Achieved. The project has been advertised | Number | 1.2km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was 31 March 2020) | Appointment of service provider by 30 September 2019 | 0,2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 1.2km construction to be completed (layer works) (was drainage systems, layer works and ancillary works) by 31 March 2020 | 1.2km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was N/A) | 1200000 | 1340955.79 |  | Due to slow progress of the contractor. | MIG | TECH-BUDG | Default | 8 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 7 | TS-07-19/20 | Zesuliwe Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 March 2020) | Achieved. The project has been advertised | Number | 7,46km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was 31 March 2020) | Appointment of service provider by 30 September 2019 | 2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 7,46km construction to be completed (layer works) (was drainage systems, layer works and ancillary works) by 31 March 2021 | 7,46km construction to be completed (drainage systems and ancillary works) by 30 June 2020 (was N/A) | 4000000 | 7267886.45 |  | The were delays in the projects due to community protests. | MIG | TECH-BUDG | Default | 7 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 8 | TS-08-19/20 | Gudlintaba Access Road | Technical Services | Administration | Number of kilometers to be completed by 30 June 2020 (was 31 March 2020) | Achieved. The project has been advertised | Number | 1,75km construction to be completed (layer work, drainage systems and ancillary works) by 30 June 2020 (was 31 March 2020) | Appointment of service provider by 30 September 2019 | 0,5km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Advert for Intention to award by 31 March 2020 (was 1,75km construction to be completed (drainange systems, layer works and ancillary works) by 31 March 2020) | 1,75km construction to be completed (layer work, drainage systems and ancillary works) by 30 June 2020 (was N/A) | 2000000 | 1000000 |  | The contractor was appointed late . | MIG | TECH-BUDG | Default | 17 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 9 | TS-09-19/20 | eMona Community Hall | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Achieved. Construction completed( Building/structure, plumbing) | date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Activites of Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | 2159000 | 1875279.79 |  | completed | MIG | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 10 | TS-10-19/20 | Siyathokoza Hall & Creche | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Not achieved. Construction activity not complete - Building/structure, plumbing | Date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | 3250000 | 2768572.91 |  | completed | MIG | TECH-BUDG | Default | 14 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 11 | TS-11-19/20 | Nondwengu Hall & Creche Ward 10 | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Not Achieved. Project delayed due to heavy floods and some parts of the facility were damaged.Contractor given extension of time to correct damages on the project. The completion time has been extended to Q1 2019-20 financial year | Date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | 1000000 | 399902.32 |  | completed | MIG | TECH-BUDG | Default | 10 | Completion Certificate | H | Manager: PMU
[5 empty] | 12 | TS-12-19/20 | Mangangeni CDC | Technical Services | Administration | Construction to be completed (foundation and walls) by 30 June 2020) (was commisioning, Operating documentation/as builts) by 31 March 2020 | Achieved. The project has been advertised. | Date | Construction to be completed (foundation and walls) by 30 June 2020) (was commisioning, Operating documentation/as builts) by 31 March 2020 | Appointment of service provider by 30 September 2019 | Activities of construction - ( Site establishement, Clear and grub and structure formation) to be completed by 31 December 2019 | Construction to be completed (Site establishment, demolish existing structure, foundation and walls) by 30 June 2020) (was commisioning, Operating documentation/as builts) by 31 March 2020 | Construction to be completed (foundation and walls) by 30 June 2020) (was N/A) | 1500000 | 1500000 |  | The contractor was appointed late . | MIG | TECH-BUDG | Default | 19 | Advert, Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 13 | TS-13-19/20 | Mandlakazi Sport Field | Technical Services | Administration | Construction to be completed (Soccer pitch earthworks and Buildings) by 30 June 2020 (was Parking area, Buildings /change rooms and Plumbing) by 31 March 2020) | Not achieved. In the process of appointing new Service Provider to complete the project. | Date | Construction to be completed (Soccer pitch earthworks and Buildings) by 30 June 2020 (was Parking area, Buildings /change rooms and Plumbing) by 31 March 2020) | Bid Specification document submitted by 30 September 2019 | Construction to be completed -(Site establishment, Soccer field, Combo court, Parking area and Buildings/change rooms) by 30 December 2019 | Appointment of service provider by 31 March 2020 (was Construction to be completed (Parking area, Buildings /change rooms and Plumbing) | Construction to be completed (Soccer pitch earthworks and Buildings) by 30 June 2020 (was N/A) | 2500000 | 2500000 |  | The contractor was appointed late . | MIG/INTERNAL | TECH-BUDG | Default | 4 | Advert, Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 14 | TS-14-19/20 | Electrification Onyazini & Khenana/Nsuze Ward 2 | Technical Services | Administration | Construction to be completed 120 households to be connected by 31 March 2020 | Achieved. Construction completed - (Site establishment, Clear and grub, Pole excavation & plantation) | Number of households connected | Construction to be completed - (Commisioning and Energizing by Eskom of 120 households by 31 March 2020 | Construction to be completed - (Installation of reticulation networks) by 30 September 2019 | N/A | Construction to be completed - (Commisioning and Energizing by Eskom of 120 households by 31 March 2020 | N/A | 2370833.61 | 4458759.49 |  | Electrification infrastructure completed (awaiting Commisioning and Energizing by Eskom of 120 households | Internal | TECH-BUDG | Default | 2 | Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 15 | TS-15-19/20 | Electrification Mcathu Ward 8 | Technical Services | Administration | Construction to be completed 283 (was 157) households to be connected by 31 March 2020 (was 30 September 2019) | Achieved. Construction completed - (Site establishment, Clear and grub, Pole excavation & plantation) | Number of households connected | Construction of electrification infrastructure to 283 (was 157) households connected ) by 31 March 2020 (was 30 September 2019) | Construction to be completed - (157 households connected ) by 30 September 2019 | N/A | Construction of electrification infrastructure to 283 households to be completed by 31 March 2020 (was N/A) | N/A | 1000000 | 1000000 |  | Awaiting ESKOM for power outage. | INEP/INTERNAL | TECH-BUDG | Default | 8 | Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 16 | TS-16-19/20 | Type 2 Electrification Ward 1-19 | Technical Services | Administration | Construction to be completed 288 (was 330) households connected by 30 June 2020 | New measure | Number of households connected | Construction of 288 (was 330) households connected, installation of electricity reticulation and energizing) to be completed by 30 June 2020 | Pre-Marketing Report to be completed by 30 September 2019 | Design Report & Bid Specification document submitted by 31 December 2019 | Advert for Intention to Award by 31 March 2020 (was Construction - (Site establishment, installation of electricity reticulation) to be completed) | Construction of 288 (was 330) households connected, installation of electricity reticulation and energizing) to be completed by 30 June 2020 | 4000000 | 3227751.99 |  | late appointment | Internal | TECH-BUDG | Default | 2 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 17 | TS-17-19/20 | Nhlangwini Sports field | Technical Services | Administration | Construction to be completed - (Soccer pitch/field and Plumbing) by 30 June 2020 (was31 March 2020) | Achieved. Construction completed - ( Roof building, Plumbing) | Date | Construction of (Soccer field eartheworks and Plumbing) by 30 June 2020 (was 31 March 2020) | Bid Specification document by 30 September 2019 | Construction (Site establishment, Soccer pitch/field) to be completed by 31 December 2019 | Appointment of service provider by 31 March 2020 (was Construction (Soccer field and Plumbing) to be completed by 31 March 2020 | Construction of (Soccer field earthworks and Plumbing) to be completed by 30 June 2020 (was N/A) | 1900000 | 1900000 |  | late appointment | Internal | TECH-BUDG | Default | 1 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 18 | TS-18-19/20 | Construction of Technical Dept Offices | Technical Services | Administration | Construction to be completed- (Parking,electrification, fencing to be completed by 31 March 2020 (was commisioning, operating documentation/as built) by 31 December 2019 | Not achieved. Service provider to be apppointed to complete the construction in the new financial year. | Date | Construction to be completed- (Parking,electrification, fencing to be completed by 31 March 2020 (was commisioning, operating documentation/as built) by 31 December 2019 | Construction (Building roof, Wall plastering, floor tilling, and plumbing) to be completed by 30 September 2019 | Construction (Parking,electrification, fencing, commisioning, operating documentation/as built) to be completed by 31 December 2019 | Construction (Parking,electrification, fencing) to be completed by 31 March 2020 (was N/A) | N/A | 4800000 | 6130000 |  | Due to the delays with the unforeseen weather, the project has been extended. | Internal | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 19 | TS-19-19/20 | Augmentation of Water Supply for Ndwedwe Main Office | Technical Services | Administration | Augmentation to be completed (Supply and installtion of JOJO tanks) by 31 December 2019 | Project was cancelled during SDBIP adjustement. Project was cancelled to reduce the scope of works.Project will be advertised and Service Provider will be appointed in Q1 2019-20 FY | Date | Augmentation to be completed (Supply and installation of JOJO tanks) by 31 December 2019 | Appointment of service provider by 30 September 2019 | Augmentation (Supply and installation of JOJO tanks) by 31 December 2019 | N/A | N/A | 200000 | 200000 |  | completed | Internal | TECH-BUDG | Default | 15 | Appointment letter and Technical Progress Report | H | Manager: Public Works
[5 empty] | 20 | TS-20-19/20 | Local Sports Facilities: Grass Cutting | Technical Services | Administration | Number of sports grounds to be completed by 30 June 2020 | Achieved. 30 sport ground completed | Number | 8 (was 40) Sport grounds to be completed by 30 June 2020 | 10 sport grounds to be completed by 30 September 2019 | 10 sport grounds to be completed by 31 December 2019 | 3 (was 10) sport grounds to be completed by 31 March 2020 | 5 sport grounds to be completed by 30 June 2020 (was N/A) | 700000 | 400000 |  | The municipality s n the process of appointing a panel of local service providers | Internal | TECH-BUDG | Default | All | Inspection Report | M | Manager: Public Works
[5 empty] | 21 | TS-21-19/20 | Rehabilitation of Mthebeni road | Technical Services | Administration | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Not Achieved. Service Provider will be appointed in new Financial year 2019-20 | Date | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Appointment of service provider by 30 September 2019 | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | N/A | N/A | 600000 | 600000 |  | completed | Internal | TECH-BUDG | Default | 14 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 22 | TS-22-19/20 | Rehabilitation of Febe road | Technical Services | Administration | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Not Achieved. Service Provider will be appointed in new Financial year 2019-21 | Date | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Appointment of Service provider by 30 September 2019 | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | N/A | N/A | 900000 | 600000 |  | completed | Internal | TECH-BUDG | Default | 14 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 23 | TS-23-19/20 | Johnny Makhathini Hall Renovations | Technical Services | Administration | Jonny Makhathini Hall renovations ( painting, and tiling (was carpentry) to be completed by 30 June 2020 (was 31 March 2020) | Not Achieved. Funds were not enough, re-prioritised for implementation in the new 2019/2020 financial year | Date | Jonny Makhathini Hall renovations ( painting, and tiling (was carpentry) to be completed by 30 June 2020 (was 31 March 2020) | Advertisment of Johny Makhathini Hall Renovations by 30 September 2019 | Appointment of Service provider by 31 December 2019 | Advert for Intention to Award by 31 March 2020 (was Jonny Makhathini Hall renovations completed( painting, tiling and carpentry) | Jonny Makhathini Hall renovations completed (Painting, tiling) by 30 June 2020 (was N/A) | 1200000 | 500000 |  | late appointment | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 24 | TS-24-19/20 | Ndwedwe Public Library Renovations | Technical Services | Administration | Ndwedwe Public Library renovations to be completed( painting, tiling and carpentry) by 31 March 2020 | Achieved | Date | Ndwedwe Public Library renovations to be completed( painting, tiling and carpentry) by 31 March 2020 | Advertisment of Ndwedwe Public Library renovations by 30September 2019 | Appointment of contractor by 30 December 2019 | Ndwedwe Public Library renovations completed( painting, tiling and carpentry by 31 March 2020) | N/A | 400000 | 400000 |  | completed | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 25 | TS-25-19/20 | Mary-Grey Sport Centre Phase 2 | Technical Services | Administration | Mary Grey construction ( Security guard house and paving to be completed 30 June 2020 (was (additional activities paving) to be completed by 31 March 2020) | Not achieved. Therefore, the Service Provider will be appointed in new financial year 2019-2020. | Date | Construction ( Security guard house and paving) to be completed by 30 June 2020 (was additional activities paving) by (was 31 March 2020) | Appointment of Service provider by 30 September 2019 | Construction of security guardroom to be completed - by 30 December 2019 | Advert for Intention to Award by 31 March 2020 (was Construction to be completed - ( additional activities paving) | Construction to be completed - ( Security guard house, paving) by 30 June 2020 (was N/A) | 600000 | 900000 |  | late appointment | Internal | TECH-BUDG | Default | 7 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 26 | TS-26-19/20 | Wewe hall | Technical Services | Administration | Wewe Hall renovations to be completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Not Achieved. Buget constraints. Funds were not enough, re-prioritised for implementation in the new 2019/2020 financial year. | Date | Wewe Hall renovations to be completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Advertisment of Wewe hall renovations by 30 September 2019 | Appoitnment of service provider by 31 December 2019 | Wewe Hall renovations completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | N/A | 200000 | 200000 |  |  | Internal | TECH-BUDG | Default | 2 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 27 | TS-27-19/20 | Noorsburg hall | Technical Services | Administration | Noorsburg Hall renovations (painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | Not Achieved. Buget constraints. Funds were not enough, re-prioritised for implementation in the new 2019/2020 financial year. | Date | Noorsburg Hall renovations (painting and tiling, plumbing and carpentry) to be completed by 31 March 2020 | Advertisment of Noorsburg hall by 30 September 2019 | Appointment of Service provider by 31 December 2019 | Noorsburg Hall renovations (painting and tiling, plumbing and carpentry) to be completed by 31 March 2020 | N/A | 200000 | 200000 |  | THE SCOPE WAS ADJUSTED | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 28 | TS-28-19/20 | Esigedleni hall | Technical Services | Administration | Esigedleni Hall renovations (painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | Not Achieved. Buget constraints. Funds were not enough, re-prioritised for implementation in the new 2019/2020 financial year. | Date | Esigedleni Hall renovations (painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | Advertisment of Esigedleni hall by 30 September 2019 | Appointment of Service provider by 31 December 2019 | Esigedleni Hall renovations (painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | N/A | 200000 | 200000 |  |  | Internal | TECH-BUDG | Default | 19 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 29 | TS-29-19/20 | Thafamasi hall | Technical Services | Administration | Thafamasi Hall renovations (painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | Not Achieved. Buget constraints. Funds were not enough, re-prioritised for implementation in the new 2019/2020 financial year. | Date | Thafamasi Hall renovations to be completed ( painting, tiling, plumbing and carpentry) to be completed by 31 March 2020 | Advertsment of Thafamasi hall by 30 September 2019 | Appoitnment of service provider by 31 December 2019 | Thafamasi Hall renovations (painting, tiling, plumbing and carpentry)to be completed by 31 March 2020 | N/A | 200000 | 200000 |  |  | Internal | TECH-BUDG | Default | 18 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 30 | TS-30-19/20 | Rehabilitation of Noorsburg Access Road | Technical Services | Administration | Noorsburg access road rehabilitation to be completed by 30 June 2020 | New measure | Date | Noorsburg access road (drainage system and gabions) to be completed by 30 June 2020 | Bid Specification and Advertisment of Noorsburg access road by 30 September 2019 | Appoitnment of service provider by 31 December 2019 | Advert for Intention to Award by 31 March 2020 (was Earthworks to be completed ) | Noorsburg access road (drainage system and gabions) to be completed by 30 June 2020 | 800000 | 800000 |  | late appointment | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 31 | TS-31-19/20 | Rehabilitation of Nhlangano Access Road Ward 4 | Technical Services | Administration | Nhlangano access road (drainage system and gabions) to be completed by 30 June 2020 | New measure | Date | Nhlangano access road (drainage system and gabions) to be completed by 30 June 2020 | Bid Specification and Advertisment of Nhlangano access road by 30 September 2019 | Appoitnment of service provider by 31 December 2019 | Advert for Intention to Award by 31 March 2020(was Earthworks to be completed) | Nhlangano access road (drainage system and gabions) to be completed by 30 June 2020 | 600000 | 600000 |  | late appointment | Internal | TECH-BUDG | Default | 4 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 32 | TS-32-19/20 | Rehabilitation of Mthukutheli Access Road Ward 15 | Technical Services | Administration | Mthukutheli cementry access road (concrete slab) to be completed by 30 June 2020 | New measure | Date | Cemetry access road Ward 15 to be completed (concrete slab completed) by 30 June 2020 (was Mthukutheli access road to be completed concrete completed) | Bid Specification and Advertisment of Mthukutheli access road by 30 September 2019 | Appoitnment of service provider by 31 December 2019 | Advert for Intention to Award by 31 March 2020(was Earthworks to be completed) | Cemetry access road Ward 15 to be completed (concrete slab completed) by 30 June 2020 (was Mthukutheli access road to be completed concrete completed) | 600000 | 600000 |  | late appointment | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 33 | TS-33-19/20 | Bhamshela Thusong centre renovations | Technical Services | Administration | External Bhamshela Thusong center renovations to be completed (painting and landscaping) by 31 March 2020 | Not Achieved. Service Provider will be appointed in new Financial year 2019-21 | Date | External Bhamshela Thusong center renovations to be completed (painting and landscaping)by 31 March 2020 | Appointment of service provider by 31 September 2019 | Internal renovations to be completed (painting and carpentry) by 31 December 2019 | External Bhamshela Thusong center renovations to be completed (painting and landscaping) by 31 March 2020 | N/A | R600 000, 00 | R600 000, 00 |  |  | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 34 | TS-34-19/20 | EPWP - Waste management | Technical Services | Administration | Number of work opportunities created by 30 June 2020 (was 30 September 2019) | Not Achieved. Due to budget constraints only 76 instead of 120 workers were employed. This project has also been budgeted for in the 2019/2020 new financial year. | Number | 73 (was 75) EPWP work opportunities created by 30 June 2020 (was 30 September 2019) | 75 EPWP work opportunities created by 30 September 2019 | N/A | N/A | 73 EPWP work opportunities created by 30 June 2020 2019 (was N/A) | 1348000 | 1348000 |  | The project target has been amended due to resignations and deaths. | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works

## FINANCE
DEPARTMENT: FINANCE
Mr S.G. MAJOLA
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Baseline | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[14 empty] | End September 2019 | End December 2019 | End March 2020 | End June 2020 |  |  |  | Reason for Adjustments
TOP LAYER SDBIP
DIRECTOR FINANCE PERFORMANCE PLAN 2019-2020
Financial Viability and Management | A responsive, accountable, effective and efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management | 1 | F-01-19/20 | Transactional mSCOA Reports | FINANCE | Administration | Number of transactional Mscoa reports to Finance Portfolio and Council for 2019 /2020 by 30 June 2020 | Number | Achieved | 12 transactional Mscoa Reports by 30 June 2020 | 3 transactional Mscoa Report by 30 September 2019 | 3 transactional Mscoa Report by 31 December 2019 | 3 transactional Mscoa Report by 31 March 2020 | 3 transactional Mscoa Report by 30 June 2020 | R400,000,00 | R400,000,00 |  |  | Municipality | FIN-BUDG | Default | N/A | 12 Reports | H | CFO
[5 empty] | 2 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 71 MFMA Reports submitted on time by 30 June 2020 | Number | Achieved | 12 MFMA Reports submitted at the end 30 June 2020 | 3 monthly reports submitted by 30 September 2019 | 3 monthly reports submitted by 31 December 2019 | 3 monthly reports submitted by 31 March 2020 | 3 monthly reports submitted by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 3 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 72 MFMA Reports sumbitted by 31 January 2020 | Number | Achieved | 1 MFMA Reports submitted to Council by 31 Janaury 2020 | N/A | N/A | 1 MFMA report submitted to Council by 31 January 2020 | N/A | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 4 | F-04-19/20 | Adjusted Budget for 2019/2020 | FINANCE | Administration | Approved Adjusted Budget adopted by the Council by 29 February 2020 | Date | Achieved | Adopted Adjusted Budget by 29 February 2020 | N/A | N/A | Adjusted Budget adopted by the Council as at 29 February 2020 | N/A | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | 5 | F-05-19/20 | Budget for 2020/ 2021 | FINANCE | Administration | Approved Final Budget adopted by the Council by 31 May 2020 | Date | Achieved | Adopted 2020/2021 Budget by the Council as at 31 May 2020 | N/A | N/A | Draft Budget adopted by the Council as at 31 March 2020 | Final Budget adopted by the Council as at 31 May 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | 6 | F-06-19/20 | Revenue Enhancement Strategy | FINANCE | Administration | Council adopted Revenue Enhancement Strategy by 30 June 2020 | Date | The project was cancelled during budget adjustment due to budget constraints. | Council approved Revenue Enhancement Strategy by 30 June 2020 | N/A | N/A | Workshop the strategy to Council by 31 March 2020 | To be approved and adopted by Council by 30 June 2020 | 300000 | 300000 |  |  | Equitable Share | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Finance
[5 empty] | 7 | F-07-19/20 | Collection of Revenue | FINANCE | Administration | Percentage of revenue collected by 30 June 2020 | Percentage |  | 60% (was 70%) of collected Revenue by 30 June 2020 | 10% of Revenue collected by 30 September 2019 | 15% of Revenue collected by 31 December 2019 | 45% of Revenue collected by 31 March 2020 | 60% (was 70%) of Revenue collected by 30 June 2020 | 0 | 0 |  | The project was amend due to low collection rate. | N/A | FIN-BUDG | Default | N/A | Revenue Reports | H | Mananger: Finance
[5 empty] | 8 | F-08-19/20 | Finances Policies (SCM,Tarrif, Credit Control Policy, S and T, Overtime Policy, Banking and investment, Budget, Indigent, Fixed Assets, Rates, Virement and Disposal) | FINANCE | Administration | Num ber. of Finance Policies developed and reviewed by 30 June 2020 | Number | Achieved | 11 Policies Adopted by Council by 30 June 2020 | N/A | N/A | 11 Draft Policies reviewed by 31 March 2020 | Adopt 11 finance related policies by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | CFO
[5 empty] | 9 | F-09-19/20 | General Valuation Roll | FINANCE | Administration | Adopted General Valuation Roll done by 30 June 2020 | Date | Achieved | Adopted General Valuation Roll Report by 30 June 2020 | N/A | N/A | Approved Draft Genearl valuation Roll Report by 31 March 2020 | Approved Final General Valuation Roll by 30 June 2020 | 600000 | 400000 |  |  | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Finance
[5 empty] | 10 | F-10-19/20 | Screening of State Employees from SCM Database | FINANCE | Administration | Number of reports generated for each quarter by 30 June 2020 | Date | Achieved | 4 Quarterly reports generated by 30 June 2020 | 1 quarterly reports generated by 30 September 2019 | 1 quarterly reports generated by 31 December 2019 | 1 quarterly reports generated by 31 March 2020 | 1 quarterly reports generated by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | 11 | F-11-19/20 | Appointment of Local Service Providers | FINANCE | Administration | Reports on appointed local service providers submitted to Council Portfolio committee by 30 June 2020 | Date | Achieved | 4 Quarterly reports submitted to Council Portfolio committee by 30 June 2020 | 1 quarterly report submitted to Council Portfolio committee by 30 September 2019 | 1 quarterly report submitted to Council Portfolio committee by 31 December 2019 | 1 quarterly report submitted to Council Portfolio committee by 31 March 2020 | 1 quarterly reports submitted to Council Portfolio committee by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | 12 | F-12-19/20 | Governance Reports ( Debtors Reconciliation Book) | FINANCE | Administration | Number of debtors reconciliation by 30 June 2020 | Number | Achieved | 12 debtors reconciliation reports submitted by 30 June 2020 | 3 Monthly Reports by 30 September 2019 | 3 Monthly Reports by 31 December 2019 | 3 Monthly Reports by 31 March 2020 | 3 Monthly Reports by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 13 | F-13-19/20 | Property Rates Reconciliation | FINANCE | Administration | Number of Property rates reconciliations by 30 June 2020 | Number | Achieved | 12 Property Rates Reconciliations by 30 June 2020 | 3 Monthly Reports by 30 September 2019 | 3 Monthly Reports by 31 December 2019 | 3 Monthly Reports by 31 March 2020 | 3 Monthly Reports by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Reports | H | Mananger: Finance
[5 empty] | 14 | F-14-19/20 | Bank Reconciliation | FINANCE | Administration | Number of Bank Reconciliation Report by 30 June 2020 | Number | Achieved | 12 Bank Reconciliation reports by June 2020 | 3 Monthly Reports by 30 September 2019 | 3 Monthly Reports by 31 December 2019 | 3 Monthly Reports by 31 March 2020 | 3 Monthly Reports by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 15 | F-15-19/20 | Investments | FINANCE | Administration | Number of monthly investments reports by 30 June 2020 | Number | Achieved | 12 Monthly Investments reports by 30 June 2020 | 3 Monthly Reports by 30 September 2019 | 3 Monthly Reports by 31 December 2019 | 3 Monthly Reports by 31 March 2020 | 3 Monthly Reports by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 16 | F-16-19/20 | Grant Register | FINANCE | Administration | Number of accurate grant register by 30 June 2020 | Number | Achieved | 12 monthly grant registers by 30 June 2020 | 3 Monthly registers by 30 September 2019 | 3 Monthly registers by 31 December 2019 | 3 Monthly registers by 31 March 2020 | 3 Monthly registers by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | 12 Monthly Registers | H | Mananger: Finance
[5 empty] | 17 | F-17-19/20 | Creditors Payment | FINANCE | Administration | Number of days from submission by 30 June 2020 | Number | Achieved | 30 Days from submission by 30 June 2020 | Payment of Invoice 30 days from submission by 30 September 2019 | Payment of Invoice 30 days from submission by 31 December 2019 | Payment of Invoice 30 days from submission by 31 March 2020 | Payment of Invoice 30 days from submission by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Age analysis Reports | H | Mananger: Finance
[5 empty] | 18 | F-18-19/20 | Third Party Payments | FINANCE | Administration | Number of Third Party Payments produced by 30 June 2020 | Number | Achieved | Last day of the month for 3rd parties by 30 June 2020 | Last day of each month for 3rd parties by 30 September 2019 | Last day of each month for 3rd parties by 31 December 2019 | Last day of each month for 3rd parties by 31 March 2020 | Last day of each month for 3rd parties by 30 June 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Third party payment report | H | Mananger: Finance
[5 empty] | 19 | F-19-19/20 | MFMA Quarterly report 2019/2020 | FINANCE | Administration | Number of MFMA Section 52 d quarterly report prepared and submitted by 31 May 2020 | Number | Achieved | 2 Quarterly report prepared and submitted by 31 May 2020 | N/A | N/A | 1 Quarterly report prepared and submitted by 28 February 2020 | 1 Quarterly report prepared and submitted by 31 May 2020 | 0 | 0 |  |  | N/A | FIN-BUDG | Default | N/A | Financial statement report | H | CFO
[5 empty] | 20 | F-20-19/20 | SCM report | FINANCE | Administration | Number of Quarterly SCM reports submitted to Council by 30 June 2020 | Number | Achieved | 4 Quarterly SCM report submitted to council by 30 June 2020 | 1 Quarterly SCM report submitted to council by 30 September 2019 | 1 Quarterly SCM report submitted to Council by 31 December 2019 | 1 Quarterly SCM report submitted to council by 31 March 2020 | 1 Quarterly SCM report submitted to Council by 30 June 2020 | 0 | 0 |  |  | Equitable Share | FIN-BUDG | Default | N/A | 4 Monthly Reports | H | Manager: SCM
|  |  |  | To achieve a clean audit opinion | 21 | F-21-19/20 | Maintain unqualified audit opinion | FINANCE | Administration | Maintain unqualified audit opinion by 31 December 2019 | AG Report | Achieved | Unqualified audit report by the AG for 2018/2019 financial year by 31 December 2019 | Submission of AFS by 31 August 2019. | Unqualified audit report by 31 December 2019 | N/A | N/A | 0 | 0 |  |  | Equitable Share | FIN-BUDG | Default | N/A | Unqualified report from AG | H | CFO
|  |  |  | Cash flow management | 22 | F-22-19/20 | Liquidity Management (Pg 7 & 8 of MFMA circular 71) | FINANCE | Administration | Cash/Cost Coverage Ratio (Excluding Unspent Conditional Grants) ((Cash and Cash Equivalents - Unspent Conditional Grants - Overdraft) + Short Term Investment) / Monthly Fixed Operational Expenditure excluding (Depreciation, Amortisation, and Provision for Bad Debts, Impairment and Loss on Disposal of Assets)) (Norm: Range between 30 and 90 days with 90 days being ideal) by 30 June 2020 | Number | Achieved | 60 days cash on hand by 30 June 2020 | 60 days cash on hand by 30 September 2019 | 60 days cash on hand by 31 December 2019 | 60 days cash on hand by 31 March 2020 | 60 days cash on hand by 30 June 2020 | 0 | 0 |  |  | Equitable Share | FIN-BUDG | Default | N/A | Monthly Reports | H | CFO

## EPD
DEPARTMENT:ECONOMIC DEVELOPMENT AND PLANNING
DIRECTOR: MR S.D.G. KHUZWAYO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Basline | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[14 empty] | End September 2019 | End December 2019 | End March 2020 | End June 2020 |  |  |  | Reason for Adjustments
TOP LAYER SDBIP
DIRECTOR ECONOMIC DEVELOPMENT AND PLANNING PERFORMANCE PLAN 2019-2020
Local Economic Development | A responsive, accountable, effective and efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 1 | EDP-01-19/20 | Ndwedwe Town Development Project | EDP | Administration | Detail submission Pack to Surveyor General to be completed by 30 June 2020 | Date | Achieved | Detail submission Pack to Surveyor General to be completed by 30 June 2020 | N/A | Beacon sectioned out and preparation of survey records by 31 December 2019 | N/A | Detail submission Pack to Surveyor General to be completed by 30 June 2020 | 2000000 | 2000000 |  |  | Internal Funding | EDP-BUDG | Default | Wards 15 | Proof of submission pack / Title Deed/ Certificate of Proclamation | H | Director: EDP
[5 empty] | 2 | EDP-02-19/20 | Ndwedwe Land Use Managament System | EDP | Administration | 2nd Draft document produced by 30 June 2020 (was Adoption of Final LUMS) | Date | New measure | 2nd Draft document produced by 30 June 2020 (was Adoption of Final LUMS) | Appointment of the Service provider by 30 September 2019 | First Draft LUMS document produced by 31 December 2019 | N/A/ (2nd Draft document produced by 31 March 2020) | 2nd Draft document produced by 30 June 2020 (was Adoption of Final LUMS) | 200000 | 200000 |  |  | Internal Funding | EDP-BUDG | Default | All wards | Final LUMS document | H | Director: EDP
[5 empty] | 3 | EDP-03-19/20 | Makhuluseni Cooperative Support | EDP | Administration | Number of Cooperative assisted by 30 June 2020 | Number | New measure | 1 Functional community garden(Seedlings, Seeds and Fencing) to be completed by 30 June 2020 | Bush Clearing on target Site one to be completed by 30 September 2019 | Seedlings, Seeds, Fencing procurement process done by 31 December 2019 | Bid evaluation process to be completed (was Training of cooperatives done) by 31 March 2020 | 1 Functional community garden(Seedlings, Seeds and Fencing) to be completed by 30 June 2020 | 600000 | 600000 |  |  | Internal Funding | EDP-BUDG | Default | Ward 18 | proof of pipe instalation | p | Director: EDP
[5 empty] | 4 | EDP-04-19/20 | SMME Support | EDP | Administration | Number of SMMEs supported by 30 June 2020 | Number | Achieved | 10 SMME's supported by 30 June 2020 | 3 SMME's supported by 30 September 2019 | 3 SMME's supported by 31 December 2019 | 3 SMME's supported by 31 March 2020 | 1 SMME supported by 30 June 2020 | 200000 | 200000 |  |  | Internal Funding | EDP-BUDG | Default | All wards | Purchase Orders | M | Manager: LED
[5 empty] | 5 | EDP-05-19/20 | Cooperatives Support and SMME support with seeds and seedlings and information | EDP | Administration | Number of Cooperatives/SMMEs supported by 30 June 2020 | Number | Achieved | 10 Cooperatives/SMMEs supported by 30 June 2020 | x3 cooperatives supported by 30 September 2019 | x3 cooperatives supported by 31 December 2019 | x3 cooperatives supported by 31 March 2020 | 1 Cooperatives/SMMEs supported by 30 June 2020 | 400000 | 250000 |  |  | Internal Funding | EDP-BUDG | Default | TBC | Beneficiary signatures | M | Manager: LED
[5 empty] | 6 | EDP-06-19/20 | Housing Forum | EDP | Administration | Number of Housing Forums reports presented by 30 June 2020 | Number | Achieved | 4 Housing Forums reports presented by 30 June 2020 | 1 Housing Forum report presented by 30 September 2019 | 1 Housing Forum report presented by 31 December 2019 | 1 Housing Forum report presented by 31 March 2020 | 1 Housing Forum report presented by 30 June 2020 | 0 | 0 |  |  | Internal Funding | EDP-BUDG | Default | All wards | Attendace Register | M | Director: EDP
[5 empty] | 7 | EDP-07-19/20 | LED Forum | EDP | Administration | Number of LED Forum meetings hosted annually by 30 June 2020 | Number | Achieved | 2 LED Forums meetings hosted by 30 June 2020 | N/A | 1 LED Forum meetings hosted by 31 December 2019 | 1 LED Forum meeting hosted by 31 March 2020 (was N/A) | 1 LED Forum meetings hosted by 30 June 2020 | 0 | 0 |  | Due to clashing of meetings the Q2 target was moved to Q3. | Internal Funding | EDP-BUDG | Default | All wards | Attendance Registers | M | Manager: LED
|  |  |  | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 8 | EDP-08-19/20 | Emerging Subcontractors support programme (capacity building for Grade 1-3) | EDP | Administration | Number of Emerging Contractors trained by 31 March 2020 | Number | The project was cancelled during the Adjustment budget. Due to bduget constraints. | 10 Emerging Contractors to be trained by 31 March 2020 | N/A | N/A | 10 Emerging Contractors to be trained by 31 March 2020 | 11 Emerging Contractors to be trained by 30 June 2020 | 100000 | 100000 |  |  | Internal Funding | EDP-BUDG | Default | TBC | Beneficiary signatures | M | Manager: LED
|  |  |  | To facilitate provision of infrastructure in a sustaianable manner | 9 | EDP-09-19/20 | Mini Factories Access Roads | EDP | Administration | Number of Metre Access Roads constructed for Mini Factories to be completed by 30 June 2020 | Number | New measure | 20 Metre Access roads to be constructed by 30 June 2020 | Advertisement of the project done by 30 September 2019 | Appointment of the Service provider done by 31 December 2019 | Appointment of service provider to be completed by the 31 March 2020(was N/A) | 20 Metre Access roads construction to be completed by 30 June 2020 | R1,200 000,00 | 1200000 |  |  | Equitable share | EDP-BUDG | Default | 18 | Completion certificate | M | Director: EDP
[5 empty] | 10 | EDP-10-19/20 | Hosting of Local Agricultural Indaba | EDP | Administration | Number of Local Agricultural Indaba hosted by 30 September 2019 | Number | New measure | 1 Local Agricultural Indaba hosted by 30 September 2019 | 1 Local Agricultural Indaba hosted by 30 September 2019 | N/A | N/A | N/A | 50000 | 50000 |  |  | Equitable share | EDP-BUDG | Default | Ward 15 | Attendance Registers | M | Director: EDP
|  |  |  | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 11 | EDP-11-19/20 | Hosting of Ndwedwe Home coming Festival | EDP | Administration | Number of Ndwedwe Homecoming Festival by 31 December 2019 | Number | New measure | 1 Ndwedwe Homecoming Festival hosted by 31 December 2019 | N/A | 1 Ndwedwe Homecoming Festival hosted by 31 December 2019 | N/A | N/A | 1000000 | 977597 |  |  | Equitable share | EDP-BUDG | Default | ward 15 | Pictures and Report | M | Director: EDP
[5 empty] | 12 | EDP-12-19/20 | Maskandi Festival | EDP | Administration | Number of Maskandi Festival hosted by 30 September 2019 | Number | New measure | 1 Maskandi Festival hosted by 30 September 2019 | 1 Maskandi Festival hosted by 30 September 2019 | N/A | N/A | N/A | 200000 | 189000 |  |  | Equitable share | EDP-BUDG | Default | Ward 7 | Pictures and Report | M | Director: EDP
[5 empty] | 13 | EDP-13-19/20 | Cannabis farmer programme | EDP | Administration | Cannabis farmers programme to be hosted by 31 March 2020 | dated | New measure | Cannabis farmers programme to be hosted by 31 March 2020 | N/A | N/A | Cannabis farmers programme to be hosted by 31 March 2020 | N/A | 0 | 100000 |  |  | Equitable share | EDP-BUDG | Default | Ward 8 | Pictures and Report | M | Director: EDP
[5 empty] | 14 | EDP-14-19/20 | Tractor plouging programme | EDP | Administration | Number of Cooperatives assisted for Tractor plouging progarmme to be completed by 31 March 2020 | Number | New measure | 5 Cooperatives assisted for Tractor plouging progarmme to be completed by 31 March 2020 | N/A | N/A | 5 Cooperatives assisted for Tractor plouging progarmme to be completed by 31 March 2020 | N/A | 0 | 260000 |  |  | Equitable share | EDP-BUDG | Default | Ward 9 | Pictures and Report | M | Director: EDP
[5 empty] | 15 | EDP-15-19/20 | LED Strategy | EDP | Administration | LED Strategy to be developed by 30 June 2020 | Date | New measure | LED Strategy to be developed and adopted by Council by 30 June 2020 | N/A | N/A | N/A | LED Strategy to be developed and adopted by Council by 30 June 2020 | 0 | 200000 |  |  | Equitable share | EDP-BUDG | Default | Ward 10 | Pictures and Report | M | Director: EDP
[5 empty] | 16 | EDP-16-19/20 | Tourism Strategy | EDP | Administration | TourismStrategy to be developed by 30 June 2020 | Date | New measure | Tourism Strategy to be developed and adopted by 30 June 2020 | N/A | N/A | N/A | Tourism Strategy to be developed and adopted by 30 June 2020 | 0 | 200000 |  |  | Equitable share | EDP-BUDG | Default | Ward 10 | Pictures and Report | M | Director: EDP

## Community Services
DEPARTMENT: COMMUNITY SERVICES
DIRECTOR: VACANT
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure |  | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[5 empty] | KPI Ref. No. | [15 empty] | Reason for Adjustments
[12 empty] | Baseline2018/2019 |  | End September 2019 | End December 2019 | End March 2020 | End June 2020
TOP LAYER SDBIP
DIRECTOR (VACANT) COMMUNITY SERVICES PERFORMANCE PLAN 2019-2020
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of infrastructure | 1 | COM-01-19/20 | Completion of Sonkombo and Anchor Departments Occupation | Community and Social Services | Administration | Number of operational anchor departments in the centre by 30 June 2020 | Number | The project was cancelled during adjustment budget due to budget constraints. The Centre was still under construction and departments could not occupy the centre whilst under construction, to be completed in the new financial year. | Refurbishments completed by 30 September 2019 (was 3 Anchor Departments operational in the Centre by 30 June 2020) | Refurbishments completed by 30 September 2019 | 1 Occupancy operational by 31 December 2019 | N/A (was 1 Occupancy operational by 31 March 2020) | N/A (was 1 Occupancy operational by 30 June 2020) | 5000000 | 0 |  | This project soley relies on the sector depts to occupy the offices however due to financial constraints they a not withn the depts control therefore Quarter 3 and Quarter 4 has been removed. | Department of CoGTA | COMM-BUDG | Default | Ward 11 | Completion Certificate and Lease Agreements | M | Manager: Community Services
[5 empty] | 2 | COM-02-19/20 | Municipal Waste collection | Community and Social Services | Administration | Number of Municipal waste collections by 30 June 2020 | Number | Achieved. | 912 Municipal waste collections by 30 June 2020 | 228 collections done from all sites by 30 September 2019 | 228 collections done from all sites by 31 December 2019 | 228 collections done from all sites by 31 March 2020 | 228 collections done from all sites by 30 June 2020 | (was R900000) | 623567.01 |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager: Community Services
[5 empty] | 3 | COM-03-19/20 | Municipal Waste collection | Community and Social Services | Administration | Percentage of households earning less than R3200 (was R1100) per month with access to waste collection by 30 June 2020 | Percetage | New measure. | 100% of Households access to waste collection by 30 June 2020 | 100% of Households access to waste collection by 30 September 2019 | 100% Households access to waste collection by 31 December 2019 | 100% Households access to waste collection by 31 March 2020 | 100% Households access to waste collection 30 June 2020 |  |  |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager: Community Services
[5 empty] | 4 | COM-04-19/20 | Disaster Awareness Campaigns | Community and Social Services | Administration | Number of Awareness campaigns by 30 June 2020 | Number | Achieved. 8 awareness campaigns held. | 4 Awareness campaignsby 30 June 2020 | 1 Awareness campaign by 30 September 2019 | 1 Awareness campaign by 31 December 2019 | 1 Awareness campaign held by 31 March 2020 | 1 Awareness campaign held by 30 June 2020 | 50000 |  |  |  | Equitable Share | COMM-BUDG | Default | Clustered wards | Attendance Register of Participants | H | Disaster Officer
[5 empty] | 5 | COM-05-19/20 | Disaster Management Advisory Meetings | Community and Social Services | Administration | Number of quartely meetings to be held by 30 June 2020 | Number | Not achieved. 2 Advisory meetings were held in the 1st quarter. Other advisory meetings could not sit because it coincided with the other council commitments which included councillors that sit in the advisory forum. | 4 Quartely Meetings to be held by 30 June 2020 | 1 Quarter Advisory Meeting held by 30 September 2019 | 2 Quarter Advisory Meeting held by 31 December 2019 | 3 Quarter Advisory Meeting held by 31 March 2020 | 4 Quarter Advisory Meeting held by 30 June 2020 |  | 16000 | 16000 |  | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Disaster Officer
[5 empty] | 6 | COM-06-19/20 | Local Disaster Management Workshops | Community and Social Services | Administration | Number of workshops held by 31 March 2020 |  | Achieved | 2 Workshops held by 31 March 2020 | 1 Workshop held by 30 September 2019 | N/A | 1 Workshop held by 31 March 2020 | N/A |  |  |  |  | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Disaster Officer
[5 empty] | 7 | COM-07-19/20 | Review of the Disaster Management Sector Plan | Community and Social Services | Administration | Number of Reviewed Disaster Management Sector Plan by 30 June 2020 | Number | Achieved | Final adopted Disaster Management Sector Plan to be submitted to DDMC by 30 June 2020 | Presenting finding, conducting site visits and review data based on the Ward Based Risk Assessments conducted. Ongoing of staff on risk assessment tools by 30 September 2019 | Establish processes for comprehensive disaster risk assessments by 31 December 2019 | Draft Disaster Sector Plan to be submitted Distrit Disaster Mngt Centre by 31 March 2020. (was Developing of Level 1 Disaster Management Plan. Development Of Disaster Risk Reduction Projects based on prioritiesd risks. Ongoing training of staff on risk assessment tools by 31 March 2020) | Final adopted Disaster Management Sector Plan to be submitted to DDMC by 30 June 2020. (was Level 1 adopted Disaster Management Sector Plan incorporated into IDP by 30 June 2020 ) | 200000 |  |  | The reviewng of the Disaster Sector Plan is being done internally. | Equitable Share | COMM-BUDG | Default | All Wards | Reviewed Disaster Management Plan | M | Disaster Officer
[5 empty] | 8 | COM-08-19/20 | Operation sukuma sakhe local task team meetings | Community services | Administration | Number of meetings held by 30 June 2020 | Number | Achieved | 8 meetings held by 30 June 2020 | 2 meetings held by 30 September 2019 | 2meetings held 31 of 31 December 2019 | 2meetings held by 31 March 2020 | 2meetings held by 30 June 2020 | 60000 | 60000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | M | Manager Social Cohesion
[5 empty] | 9 | COM-09-19/20 | Local Aids Committee Meetings | Community services | Administration | Number of meetings held by 30 June 2020 | Number | Achieved | 8 meetings held by 30 June 2020 | 2meetings held by 30 September 2019 | 2meetings held 31 December 2019 | 2meetings held by 31 March 2020 | 2meetings held by 30 June 2020 | 50000 | 50000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | M | Manager Social Cohesion
[5 empty] | 10 | COM-10-19/20 | Operation MBO | Community services | Administration | Number of meetings held by 30 June 2020 | Number | Achieved | 4 Meetings held by 30 June 2020 | 1meeting held by 30 September 2019 | 1meeting held 31 December 2019 | 1meeting held by 31 March 2020 | 1meeting held by 30 June2020 | 140000 | 140000 |  |  | Equitable share | COMM-BUDG | Default | tbc | Attendance Register | M | Manager Social Cohesion
[5 empty] | 11 | COM-11-19/20 | Men's Dialogue | Community services | Administration | Number of Dialogues held by 30 September 2019 | Number | Achieved | 1 Dialogue to be held by 30 September 2019 | 1 Dialogue held by 30 September 2019 | N/A | N/A | N/A | 100000 | 100000 |  |  | Equitable share | COMM-BUDG | Default |  | Attendance Register and Program | M | Manager Social Cohesion
[5 empty] | 12 | COM-12-19/20 | Womens day Commemoration Dialogue | Community services | Administration | Number of Dialogues held by 30 September 2019 | Number | Not achieved. Due to budget constraints the target was not met. | 1 Dialogue to be held by 30 September 2019 | 1 Dialogue commemoration held by 30 September 2019 | N/A | N/A | N/A | 200000 | 200000 |  |  | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 13 | COM-13-19/20 | Operation Siyaya Emhlangeni | Community services | Administration | Number of eventss hosted by 30 September 2019 | Number | Achieved | 1events hosted by 30 September 2019 | 1 events hosted by 30 September 2019 | N/A | N/A | N/A | 70000 | 70000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 14 | COM-14-19/20 | Umkhosi Womhlanga | Community services | Administration | Number of Maidens participated by 30 September 2019 | Number | Achieved | 490 Maidens Participated by 30 September 2019 | 490 Maidens Participated by 30 September 2019 | N/A | N/A | N/A | 295200 | 295200 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 15 | COM-15-19/20 | Ndwedwe Safety Prayer | Community services | Administration | Number of Prayers hosted by 31 December 2019 | Number | Achieved | 1 Prayer hosted by 31 December 2019 | N/A | 1 Prayer hosted by 31 December 2019 | N/A | N/A | 60000 | 60000 |  |  | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 16 | COM-16-19/20 | Child Protection Program | Community services | Administration | Number of Programs held by 30 June 2020 | Number | New measure. | Program held by 30 June 2020 | N/A | N/A | N/A | 1 Program held by 30 June 2020 | 50000 | 50000 |  |  | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 17 | COM-17-19/20 | Christmas Program for Senior Citizens | Community services | Administration | Number of Programs held by 31 December 2019 | Number | Ahieved. | 1 Program held by 31 December 2019 | N/A | 1 Christmas program held by 31 December 2019 | N/A | N/A | 80000 | 80000 |  |  | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 18 | COM-18-19/20 | 16 Days of Activism | Community services | Administration | Number of meetings held by 31 December 2019 | Number | Ahieved. | 2 meetings held by 31 December 2019 | N/A | 2 meeting held by 31 December 2019 | N/A | N/A | 150000 | 150000 |  |  | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 19 | COM-19-19/20 | Umkhosi kaBhacela | Community services | Administration | Number of Programs held by 31 March 2020 | Number | Ahieved. | 1 Program held by 31 March 2020 | N/A | N/A | 1 Program hosted by 31 March 2020 | N/A | 300000 | 300000 |  |  | Equitable share | COMM-BUDG | Default | 16,17,18,19 and 9 | Attendance Register | M | Manager Social Cohesion
[5 empty] | 20 | COM-20-19/20 | Moral Regeneration and Social Cohesion events | Community services | Administration | Number of eventss hosted by 30 June 2020 | Number | New measure. | 1 events hosted by 30 June 2020 | N/A | N/A | N/A | 1 events hosted by 30 June 2020 | 100000 | 100000 |  |  | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 21 | COM-21-19/20 | Disability Safety awareness | Community services | Administration | Number of Awareness hosted by 31 December 2019 | Number | New measure. | 1 Awareness hosted by 31 December 2019 | N/A | 1 Awareness held by 31 December 2019 | N/A | N/A | 100000 | 100000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 22 | COM-22-19/20 | Disability Games | Community services | Administration | Number of Games hosted by 31 March 2020 | Number | New measure. | 1 Game hosted by 31 March 2020 | N/A | N/A | 1 Game hosted by 31 March 2020 | N/A | 15000 | 15000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 23 | COM-23-19/20 | Farm Workers Program | Community services | Administration | Number of Programs held by 30 June 2020 | Number | New measure. | 1 Program held by 30 June 2020 | N/A | N/A | N/A | 1 Program held by 30 June 2020 | 100000 | 100000 |  |  | Equitable share | COMM-BUDG | Default | 1,8,3 and 12 | Attendance Register | M | Manager Social Cohesion
[5 empty] | 24 | COM-24-19/20 | Ndwedwe Aids Day events | Community services | Administration | Number of eventss hosted by 31 December 2019 | Number | New measure. | 1 events hosted by 31 December 2019 | N/A | 1 events hosted by 31 December 2019 | N/A | N/A | 250000 | 250000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 25 | COM-25-19/20 | Ndwedwe Social Ills Awareness | Community services | Administration | Number of awareness held by 30 June 2020 | Number | New measure. | 1 Awareness held by 30 June 2020 | N/A | 1 Awareness held by 31 December 2019 | N/A | 1 Awareness held by 30 June 2020 | 120000 | 120000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 26 | COM-26-19/20 | Dress a child uniform campaign | Community services | Administration | Number of Campaigns held by 31 March 2020 | Number | Achieved. | 1 Campaign held by 31 March 2020 | N/A | N/A | 1 campaign held by 31 March 2020 | N/A | 500000 | 500000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 27 | COM-27-19/20 | Golden Games | Community services | Administration | Number of eventss hosted by 30 June 2020 | Number | Achieved. | 1 Golden Games event hosted by 30 June 2020 | N/A | N/A | N/A | 1 events hosted by 30 June 2020 | 40000 | 40000 |  |  | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 28 | COM-28-19/20 | Ndwedwe Ingoma Yesintu Program | Community services | Administration | Number of Programs held by 30 March 2020 | Number | New measure. | 2 Programs held by 31 March 2020 | N/A | 1 Program held by 31 December 2019 | 1 Program held by 31 March 2020 | N/A | 80000 | 80000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance register | M | Manager Social Cohesion
[5 empty] | 29 | COM-29-19/20 | Disability and Senior Citizens Forum | Community services | Administration | Number of Forums held by 30 June 2020 | Number | New measure. | 4 Forums held by 30 June 2020 | 1 Forum by 30 September 2019 | 1 Forum by d by 31 December 2019 | 1 Forum by 31 March 2020 | 1 Forum by 30 June 2020 | 20000 | 20000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance register | M | Manager Social Cohesion
[5 empty] | 30 | COM-30-19/20 | Civil Society Forum | Community services | Administration | Number of Forums held by 30 June 2020 | Number | New measure. | 4 Forums held by 30 June 2020 | 1 Forum by 30 September 2019 | 1 Forum by d by 31 December 2019 | 1 Forum by 31 March 2020 | 1 Forum by 30 June 2020 | 200000 | 200000 |  |  | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 31 | COM-31-19/20 | OSS Strategic Session | Community services | Administration | Number of sessions held by 30 September 2019 | Number | New measure. | 1 Session held by 30 September 2019 | 1 Session held by 30 September 2019 | N/A | N/A | N/A | 30000 | 30000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 32 | COM-32-19/20 | Women Empowerment Program | Community services | Administration | Number of Programs held by 30 March 2020 | Number | Not achieved | 1 Program held by 31 March 2020 | N/A | N/A | 1 Program held by 31 March 2020 | N/A | 50000 | 50000 |  |  | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion

## Corporate Services
DEPARTMENT: CORPORATE SERVICES
DIRECTOR: DR M.G. NTULI
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure |  | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 2nd Adjustments 4th Quarter Target | Original Budget for the Year | 1st Adjustments Budget approved by Council 31 March 2020 | 2nd Adjustments Budget approved by Council 15 June 2020 |  | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
KPI Ref No.
[12 empty] | Baseline |  | End September 2019 | End December 2019 | End March 2020 | End June 2020 |  |  |  | Reason for Adjustments
TOP LAYER SDBIP
DIRECTOR CORPORATE SERVICES PERFORMANCE PLAN 2019-2020
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive, accountable, effective and efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 1 | CS-01 19/20 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | Number of WSP training programmes implemented as per WSP by end of financial year by 30 June 2020 | Number | Achieved. 12WSP training programmes implemented | 8 WSP training programmes implemented as per WSP by 30 June 2020 | 2WSP training programmes implemented as per WSP by 30 September 2019 | 2WSP training programmes implemented as per WSP by 31 December 2019 | 2WSP training programmes implemented as per WSP by 31 March 2020 | 2 WSP training programmes implemented as per WSP by 30 June 2020 | 100000 | 100000 |  |  | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 2 | CS-02 19/20 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | The percentage of a municipality’s budget actually spent on implementing its workplace skills plan by 30 June 2020 | Pertcentage | New measure | 1% of budget spent on the municipality WSP by 30 June 2020 | 0.25% of budget spent on WSP by 30 September 2019 | 0.50% of budget spent on WSP by 31 December 2019 | 0.75% of budget spent on WSP by 31 March 2020 | 1% of budget spent on WSP by 30 June 2020 |  |  |  |  | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 3 | CS-03 19/20 | Filling budgeted posts | Corporate Services | Administration | Number of Budgeted posts filled by 30 June 2020 | Number | Achieved. 25 Budgeted posts | 12 Budgeted posts be filled by 30 June 2020 | 3 Budgeted posts be filled by 30 September 2019 | 2 Budgeted posts be filled by 31 December 2019 | 5 Budgeted posts be filled by 31 March 2020 | 2 Budgeted posts be filled by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Manager: Human Resource
[5 empty] | 4 | CS-04 19/20 | Implement, test and maintain ICT system backups | Corporate Services | Administration | Number of successful backups conducted by 30 June 2020 | Number | Not achieved 3 reports submitted | 12 Backup reports submitted by 30 June 2020 | 3 Reports submitted by 30 September 2019 | 3 Reports submitted by 31 December 2019 | 3 Reports submitted by 31 March 2020 | 3 reports submitted by 30 June 2020 | 800000 | 830000 |  |  | Municipality | DCS-BUDG | Default | N/A | Backup Reports | M | Manager: IT
[5 empty] | 5 | CS-05 19/20 | Conduct bi-annual municipal data recovery | Corporate Services | Administration | Number of successful data recovery test reports by 30 June 2020 | Number | Achieved 3 reports submitted | 2 Data recovery test reports by 30 June 2020 | N/A | 1 report submitted by 31 December 2019 | n/a | 1 report submitted by 30 June 2020 |  |  |  |  | Municipality | DCS-BUDG | Default | N/A | Data recovery reports | M | Manager: IT
[5 empty] | 6 | CS-06 19/20 | Ctrack System | Corporate Services | Administration | Number of monthly systeme generated reports by 30 June 2020 | Number | Achieved 12 reports submitted | 12 Monthly C track systerm generated report by 30 June 2020 | 3 reports submitted by 30 September 2019 | 3reports submitted by 31 December 2019 | 3 reports submitted by 31 March 2020 | 3 reports submitted by 30 June 2020 | 384000 | 319645.71 |  |  | Municipality | DCS-BUDG | Default | N/A | Ctrack system reports | M | Manager : Administration
[5 empty] | 7 | CS-07 19/20 | Implementation of Biometric System report | Corporate Services | Administration | Number of biometric system reports implemented by 30 June 2020 | Number | Achieved 12 reports prepared | 12 x Biometric system reports presented by 30 June 2020 | 3x Biometric system reports presented by 30 September 2019 | 3x Biometric system reports presented by 31 December 2019 | 3x Biometric system reports presented by 31 March 2020 | 3x Biometric system reports presented by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Biometrics Reports | H | Manager: IT
[5 empty] | 8 | CS-08 19/20 | Community skills support programme | Corporate Services | Administration | Number of Interns and Inservice trainees recruited by 30 June 2020 | Number | Achieved. 14 interns appointed | 8 Interns and 6 Inservice trainees by 30 June 2020 | N/A | 4 Interns appointed by 31 December 2019 | 2 Interns appointed by 31 March 2020 | 2 Interns appointed by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Appointment Letters | M | Manager: Human Resource
[5 empty] | 9 | CS-09 19/20 | Management and co-ordination of meetings | Corporate Services | Administration | Number of approved schedule of meetings by 30 June 2020 | Number | New measure | 4 Corporate Staff meetings by 30 June 2020 | 1 Corporate Staff Meeting by 30 September 2019 | 1 Corporate Staff meeting by 31 December 2019 | 1 Corporate Staff meeting by 31 March 2020 | 1 Corporate Staff meeting by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Signed and approved schedule of meetings. Extracts from minutes | M | Manager: Administration
[5 empty] | 10 | CS-10 19/20 | Council support services | Corporate Services | Administration | Number of Council meetings held by 30 June 2020 | Number | New measure | 4 Council meetings by 30 June 2020 | 1 Council meeting by 30 September 2019 | 1 Council meeting by 31 December 2019 | 1 Council meeting by 31 March 2020 | 1 Council meeting by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | 11 | CS-11 19/20 | Council support services | Corporate Services | Administration | Number of EXCO meetings held by 30 June 2020 | Number | New measure | 10 EXCO meetings by 30 June 2020 | 3 Exco meetings by 30 September 2019 | 3 Exco meetings by 31 December 2019 | 3 Exco meetings by 31 March 2020 | 1 Council meeting by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | 12 | CS-12 19/20 | Drafting of Service Level Agreements (SLA) | Corporate Services | Administration | Number of SLA's drafted by 30 June 2020 | Number | New measure | 4 SLA's drafted by 30 June 2020 | 1 SLA drafted by 30 September 2019 | 1 SLA drafted by 31 December 2019 | 1 SLA Drafted by 31 March 2020 | 1 SLA drafted by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Copies of SLA's drafted & Register of signed SLA | H | Manager: Legal Services
[5 empty] | 13 | CS-13 19/20 | Training on Policies and Legislations | Corporate Services | Administration | Number of trainings provided for staff and councillors on Policies and Legislations by 30 June 2020 | Number | New measure | 8 Trainings conducted on Policies and Legislations by 30 June 2020 | 2 Training on Policies and Legislations by 30 September 2019 | 2 Traininings on Policies and Legislations by 31 December 2019 | 2 Trainings on Policies and Legislations by 31 March 2020 | 2 Trainings on Policies and Legislations by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance registers | M | Manager: Legal Services
[5 empty] | 14 | CS-14 19/20 | Policies reviewed | Corporate Services | Administration | Number of policies reviewed and developed by the 30 June 2020 | Number | Not achieved 8 policies reviewed. | 6 Policies reviewed and developed by 30 June 2020 | N/A | 2 Policies reviewed and developed by 31 December 2019 | 2 Policies reviewed and developed by 31 March 2020 | 2 Policies reviewed and developed by 30 June 2020 | 0 | 0 |  |  | Municipality | DCS-BUDG | Default | N/A | Signed report on reviewed and developed policies | H | Manager: Legal Services