## Sheet1
ACTION PROGRAMME FOR 2024/2025 IDP REVIEW, BUDGET, OPMS AND 2023/2024 ANNUAL REPORT
Project Period
Nos. |  | Detailed Activity | Description | Legislation | Responsibility | [12 empty] | Oct 2023 | [7 empty] | Dec 2024 |  |  |  | Jan 2024
| Major Activity |  |  |  |  | July 2023 |  |  |  | Aug 2023 |  |  |  | Sept 2023 | [7 empty] | Nov 2023 | [11 empty] | Feb 2024 |  |  |  | March 2024 |  |  |  | April 2024 |  |  |  | May 2024 |  |  |  | June 2022
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Annual Performance Report for 2021/2022 | Collate information from all the municipal Departments | MSA, S46 | MSA, S46 | IDP and PMS Manager | bar: July 2023 1 to July 2023 4
2 | Draft IDP Process Plan for2024/2025 | Prepare the Draft IDP Process Plan |  | MSA, S28 | IDP and PMS Manager | bar: July 2023 1 to July 2023 4
3 | Public Notification | Invitation of the interested parties to register in2024/2025 IDP Representative Forum | Notification of Intent & Call Interested Parties to Register for 2012/2017 IDP Rep Forum (First Meeting) - Public Participation | MSA, S16, S28(3) | IDP and PMS Manager | bar: July 2023 1 to July 2023 4
4 | Annual Performance Report for 2023/2024 | Annual Performance Report prepared, submitted to Audit Committee, Adopted and Submitted to AG, CoGTA, PT & NT | MSA, S46 | MSA, S46 | IDP and PMS Manager | bar: Aug 2023 1 to Aug 2023 4
5 | Annual Report | Tabling of Unaudited 2021/2022 IDM Annual Report by the Mayor and submitted to AG | MFMA, 121 | MFMA, 121 | Mayor and Municipal Manager | bar: Aug 2023 1 to Aug 2023 4
6 | Annual Financial Statement | Annual Financial Statement prepared, submitted to Audit Committee, Adopted and Submitted to AG, CoGTA, PT & NT | MFMA, 126 (1)(a) | MFMA, 126 (1)(a) | CFO | bar: Aug 2023 1 to Aug 2023 4
7 | IDP Review2024/2025 | Adoption of the Final IDP Process Plan | MSA, S28 | MSA, S28 | Council | bar: Aug 2023 1 to Aug 2023 4
8 | Determination of Revenue Projections and Policies | Submission of Report to Council | MFMA Guideline | MFMA Guideline | CFO | bar: Sept 2023 1 to Sept 2023 4
9 | IDP Review2024/2025 | Sitting of first IDP Steering Committee/MANCO | MSA, S34 | MSA, S34 | Municipal Manager | bar: Sept 2023 1 to Sept 2023 4
10 | Public Participation | Sitting of first IDP Rep Forum/ Public Participation Broad based meeting. | MSA, S16 | MSA, S16 | Mayor and EXCO member, Municipal Manager and all Heads of Department | bar: Sept 2023 1 to Nov 2023 4
11 | Public Participation | Meeting with the community through IDP Road-Shows | MSA, S16 | MSA, S16 | Public Participation Manager and IDP and PMS Manager | bar: Sept 2023 1 to Nov 2023 4
12 | Municipal Alignment Session | Collection of relevant information through Multi-sectoral meetings and conduct need analyasis | MSA, S24 | MSA, S24 | IDP and PMS Manager & HODs | bar: Nov 2023 1 to Nov 2023 4
13 | Review Development Strategies | Review the Municipality's priority list of strategies and projects | MSA, S34 | MSA, S34 | HODs and Council | bar: Nov 2023 1 to Nov 2023 4
14 | Policy Review | Undertake policy review | MFMA Guideline | MFMA Guideline | CFO and IDP and PMS Manager | bar: Nov 2023 1 to Nov 2023 4
15 | Tabling of 2021/2022 Annual Report | Tabling of 2021/2022 Annual Report by the Mayor | MFMA, S127 (2) | MFMA, S127 (2) | Mayor | bar: Nov 2023 1 to Nov 2023 4
16 | MPAC Report | MPAC Finalizes assessment on AR. This must be within 7 days of receipt of AG's Report | MFMA, s129, 132 | MFMA, s129, 132 | MPAC | bar: Nov 2023 1 to Nov 2023 4
17 | Adoption of oversight report | Adoption of oversight report by Council | MFMA, s129(1) | MFMA, s129(1) | Council | bar: Nov 2023 1 to Nov 2023 4
18 | Oversight Report is made public | Oversight report is made public | MSA, S21a | MSA, S21a | Communication Office and IT Officer | bar: Nov 2023 1 to Nov 2023 4
19 | Submission | Submission of AR to Treasury and DCoG | MFMA, 132 | MFMA, 132 | Municipal Manager and CFO | bar: Nov 2023 1 to Nov 2023 4
20 | 2023/2024 Mid-Year Budget & Performance Assessment Report | Submission of Report to Council on the performance of the municipality during the first half of the financial year |  | MFMA,S72(1) | CFO and IDP/ PMS Manager | bar: Nov 2023 1 to Nov 2023 4
21 | Municipal Sector Plans | Finalisation of municipal sector plans |  | MSA, S26 | HODs | bar: Nov 2023 1 to Nov 2023 4
22 | IDP Sector Alignment | Sector Alignment with the iLembe Family of Municipalities |  | MSA, S24 | IDM & LMs | bar: Nov 2023 1 to Nov 2023 4
23 | 2023/2024 Mid-Year Budget Adjustment | Submission of Report to Council on implementation of budget and finacial status of the municipality |  | MFMA, S28 | CFO | bar: Feb 2024 1 to Feb 2024 4
24 | 2023/2024 Mid-Year Budget Adjustment | Submission of the Adjustment Budget in the approved format to the Provincial and National Treasuries |  | MFMA,S28 | CFO | bar: March 2024 1 to March 2024 4
25 | Draft IDP and SDF Review | Noting of Draft IDP by Council and Submitting to COGTA |  | MSA, S34 | Council | bar: March 2024 1 to March 2024 4
26 | Budget Preparation - (Internal Processes) | Preparation of2024/2025 Financial Year's, Capital Budget; Opertaional Budget; Salaries Budget; Tariff Budget; Revised Budget; Draft SDBIP |  | MFMA Guideline | CFO, HODS and Relevant Senior Officials | bar: March 2024 1 to March 2024 4
27 | Public Participation | IDP Representative Forum |  | MSA, S34 | Mayor and EXCO member, Municipal Manager and all Heads of Department | bar: March 2024 1 to March 2024 4
28 | A Strategic MTEF Budgetary Framework linked to the IDP Strategic Objectives and Sensitive to the capital investment programme | Draw up an integrated MTEF budgetary framework for inclusion into the IDP; Alignment of MTEF budgetary framework with that of Sector Departments |  | MFMA | All Heads of Department | bar: March 2024 1 to March 2024 4
29 | Complete draft budget document and draft SDBIP for2024/2025 | Present draft budget to the Mayor, Table Draft Budget, Table Draft SDBIP, Commencement of public participation process - advertisement of the budget in local newspapers, municipal office, Conduct budget road - show to let the community know of their budgets, Submit draft budgets to National & Provincial Treasury and other stakeholders |  | MFMA,S22 | EXCO and Chief Financial Officer | bar: March 2024 1 to March 2024 4
30 | Submission of draft2024/2025 IDP | Submit Draft2024/2025 IDP documents to MEC for DCoGTA |  | MSA, S32 | IDP and PMS Manager | bar: March 2024 1 to March 2024 4
31 | IDP Assessment | IDP Assessment Forum | MSA, S31 | MSA, S31 | The Mayor, Municipal Manager and HOD's, | bar: April 2024 1 to April 2024 4
32 | Public Participation | Presentation of the draft IDP for comments and clarity Presentation of final budget documantation for consideration of approval taking into account consultative processes and any other new information of material nature | MSA, S16 | MSA, S16 | The Mayor and all Heads of Derpartments | bar: March 2024 3 to April 2024 4
33 | 2024/2025 Final Budget | Preparation of the final budget documentation for consideration of approval, taking into account consultative processes and any other new information of material nature | MFM, S23 | MFM, S23 | The Mayor | bar: April 2024 1 to April 2024 4
34 | 2024/2025 Budget/IDP/SDF | Adoption of both 2024/2025 Budget & the 2023/2024 IDP and SDF review | MSA, S30 ( c ) | MSA, S30 ( c ) | The Mayor | bar: May 2024 1 to May 2024 4
35 | 2024/2025 Budget | Submission of the Budget in the approved format to the Provincial and National Treasury | MFMA, S23 | MFMA, S23 | CFO | bar: June 2022 1 to June 2022 4
36 | 2023/2024 IDP | Submission of the adopted Final2024/2025 IDP to the MEC for the Cooperative Governance & Traditional Affairs | MSA, S32 | MSA, S32 | IDP and PMS Manager | bar: June 2022 1 to June 2022 4
37 | 2024/2025 Budget | Finalization of the Service Delivery and Budget Implemantation Plan (SDBIP) The Mayor must approve the SDBIP 28 days after the approval of the budget and ensure that annual performance contracts are concluded in accordance with S57 of Municipal Systems Act (MSA). The Mayor must submit the approval SDBIP and performance agreement and make the document public within 14 days after approval | MFMA, S53 | MFMA, S53 | Municipal Manager and HODs | bar: June 2022 1 to June 2022 4
Public Participation