## Organisat Scorecard
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  | Actual Achieved/Not Achived | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[5 empty] | KPI Ref. No | [7 empty] | 1st Quarter Target | 2nd Quarter Target |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec
ORGANISATIONAL SCORECARD 2018/2019
Infrastructure and Service Delivery | A responsive & accountable, effective & efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 52 | TS-01-18/19 | MIG projects | Technical Services | Administration | Percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 60% Construction Completed (Site establishment, Mass earthworks, pipe crossings and road bed preparation) by December 2018 |  |  |  |  | To be Confirmed | MIG | TECH-BUDG | Default | 1 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 65 | TS-14-18/19 | Electrification | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor | 40% Construction - ( Site establishement, Clear and grub, Pole excavation & plantation) |  |  |  |  | To be Confirmed | INEP & Internal | TECH-BUDG | Default | 2 | Completion certificate | H | Director: Technical Services
[5 empty] | 91 | TS-40-18/19 | EPWP - Waste management | Technical Services | Administration | Number of Work opportunities created by June 2019 | Number | 120 EPWP participants by June 2019 | 58 participants by September 2018 | N/A |  |  |  |  | 400000 | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works
Good Governance and Public Participation | A responsive & accountable, effective & efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance | 2 | MM-02-18/19 | Tabling of Draft Annual Report 2017/2018 to Council within 9 months after the end of a financial year | Municipal Manager | Administration | Approved Annual Report for 2017-2018 | Date | Adopted Annual Report | Draft Annual Performance Report adopted by Council | N/A |  |  |  |  | Salaries |  | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 3 | MM-03-18/19 | Tabling of oversight report on the AR 2017/2018 to Council by no later than 2(two) months from the date in which the AR was tabled as per MFMA Section 127 (5) | Municipal Manager | Administration | Approved Oversight Report for 2017-2018 | Date | Adopted Oversight Report for 2018-2019 | N/A | N/A |  |  |  |  | Salaries |  | MM-BUDG | Default | Municipality | Council Resolution | H | Chaiperson MPAC
Local Economic Development | A responsive & accountable, effective & efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 42 | EDP-02-18/19 | Ndwedwe Town Development Proclamation | EDP | Administration | Title Deed/ Certificate of Proclamation by June 2019 | Date | End of June 2019 | Draft Survey Records submitted Report Completed by September 2018 | Final Survey Record/ Report Completed by December 2018 |  |  |  |  | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards | Title Deed/ Certificate of Proclamation by June 2019 | H | Town Planner
[5 empty] | 45 | EDP-05-18/19 | Establishment of x 4 Commercial Gardens | EDP | Administration | Number of Community Gardens established by June 2019 | Number | 4 functional commercial gardens by June 2019 | Assesments and feasibility studies completed by September 2018 | Appointment of the service provider for agricultural equipment completed by 31 December 2018 |  |  |  |  | N/A | Internal Funding | EDP-BUDG | Default | Ward 4, 18,7 and 14 | Assessment Reports | M | Manager: LED
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive & accountable, effective & efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 94 | CS-03-18/19 | Filling budgeted posts | Corporate Services | Administration | Number of Budgeted posts filled by June 2019 | Number | 25 Budgeted posts be filled by 30 June 2019 | 10 Budgeted posts be filled by 30 September 2018 | 5 Budgeted posts be filled by December 2018 |  |  |  |  | N/A | Municipality | #REF! | Default | N/A | Adverts, Appointment Letters | M | Manager: Human Resource
[5 empty] | 106 | CS-15-18/19 | Review of organisational structure | Corporate Services | Administration | Number of organisational structure reviewed and approved by the Council on 30 June 2019 | Number | 1x 2018/2019 approved organisational structure by June 2019 | N/A | N/A | [5 empty] | Municipality | DCS-BUDG | Default | N/A | Council Resolution | M | Manager: Human Resource
[5 empty] | 108 | CS-17-18/19 | Employment Equity Plan | Corporate Services | Administration | Number of employment equity plan submitted to department of labour by June 2019 | Number | 1x Employment Equity report submitted to Department of labour by June 2019 | Development of employment Equity Plan by September 2018 | N/A |  |  |  |  | N/A | Municipality | DCS-BUDG | Default | N/A | Employment Equity Reports | M | Manager: Human Resource
[5 empty] | 112 | F-03-18/19 | Budget for 2019/ 2020 | FINANCE | Administration | Approved final Budget adopted by the Council by June 2019 | Date | adopted 2018/2019 Budget by the Council as at 30 June 2019 | Adopted budget process plan by September 2018 | IDP Budget Consultation meetings done by December 2018 |  |  |  |  | Salaries | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | 129 | F-20-18/19 | AFS 2017/ 2018 | FINANCE | Administration | Adopted AFS for 2017/2018 by June 2019 | Date | Adopted AFS for 2017/2018 by 30 June 2019 | Financial Statements submitted to Auditor General, Treasury and CoGTA - 31 August 2018 | N/A |  |  |  |  | Salaries | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | CFO

## MM
DEPARTMENT: OFFICE OF THE MUNICIPAL MUNICIPAL
ACTING MUNICIPAL MANAGER: MR M.F.HADEBE
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit of Measure | Annual Target |  |  | 2nd Quarter Actual | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Annual Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Evidence | Weightings | Responsible Manager
[13 empty] | 1st Quarter Target | 2nd Quarter Target |  |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
MUNICIPAL MANAGER
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 1 | MM-01-18/19 | Review of 4 Performance reports by Internal Audit on quarterly basis | Municipal Manager | Administration | Number of reports submitted to Audit Committee | Number | 4 submitted to Audit Committee | 1 | 1 | 0 reports -Not Ahieved | 1 reports 2017/18 Annual perforamnce report - Not Achieved | There is no Internal Audit unit present at the Municipality from September 2018 to date | The post for Manager Internal Audit and a Service provider has been advertised. To be appointed in Q3. | Salaries | Salaries | Salaries | MM-BUDG | Default | Municipality |  | Council Resolution | H | Manager IDP/PMS
[5 empty] | 2 | MM-02-18/19 | Tabling of Draft Annual Report 2017/2018 to Council within 9 months after the end of a financial year | Municipal Manager | Administration | Approved Annual Report for 2017-2018 | Date | Adopted Annual Report | Draft Annual Performance Report adopted by Council | N/A | N/A | Draft Annual Report submitted to Council on the 29 August 2018. Achied. | N/A | N/A | Salaries | Salaries |  | MM-BUDG | Default | Municipality |  | Council Resolution | H | Manager IDP/PMS
[5 empty] | 3 | MM-03-18/19 | Tabling of oversight report on the AR 2017/2018 to Council by no later than 2(two) months from the date in which the AR was tabled as per MFMA Section 127 (5) | Municipal Manager | Administration | Approved Oversight Report for 2017-2018 | Date | Adopted Oversight Report for 2018-2019 | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Salaries |  | MM-BUDG | Default | Municipality |  | Council Resolution | H | Chaiperson MPAC
[5 empty] | 4 | MM-04-18/19 | IDP/Budget/PMS Process Plan 2019-2020 | Municipal Manager | Administration | Number of Process Plans by 30 June 2019 | Number | 1 Process plan approved by 30 June 2019 | Adoption of Process Plan for 2018-2021 | N/A | N/A | 1 Process Plan submitted to Council on the 29 August 2018 | N/A | N/A | Salaries | Salaries | N/A | MM-BUDG |  | Municipality |  | Council Resolution | H | Manager IDP/PMS
[5 empty] | 5 | MM-05-18/19 | Speaker Izimbizo | Municipal Manager | Administration | Number of Izimbizo Hosted by June 2019 | Number | 2 Izimbizo Hosted by 30 June 2019 | N/A | 1 Izimbizo by December 2018 | 1 Izimbizo held in December 2018 | 1 Izimbizo held in December 2018 | N/A | N/A | TBC | 1000000 | Equitable Share | MM-BUDG | Default | All Wards |  | Attendance Register of Participants | M | Manager Public Participation
[5 empty] | 6 | MM-06-18/19 | Mayoral/IDP Izimbizo | Municipal Manager | Administration | Number of mayoral/ IDP Izimbizo by June 2019 | Number | 8 Mayoral/ IDP Izimbizo by 30 June 2019 | 4 Izimbizo by September 2018 | N/A | 4 Meetings was held in October and November 2018 | 4 Meetings was held in October and November 2018 | N/A | N/A | TBC | 1000000 | Equitable Share | MM-BUDG | Default | All Wards |  | Attendance Register | M | Manager Public Participation
[5 empty] | 7 | MM-07-18/19 | Ward Committees Training | Municipal Manager | Administration | Number of Trainings of the Ward Committees by June 2019 | Number | 2 Trainings Conducted by 30 June 2019 | 01 training conducted by September 2018 | N/A | 1 Ward Committee Training was held in December 2018 | 1 Ward Committee Training was held in December 2018 | N/A | N/A | TBC | 1250000 | Equitable Share | MM-BUDG | Default | All Wards |  | Attendance Register | M | Manager Public Participation
[5 empty] | 8 | MM-08-18/19 | Ward Committees Quartely Meeting | Municipal Manager | Administration | Number of Ward Committee meetings hosted by June 2019 | Number | 4 Ward Committee meetings hosted by June 2019 | 01 Ward Committee Meeting by September 2018 | 01 Ward Committee Meeting by December 2018 | 1 Ward Committee was held in December 2018 | 1 Ward Committee was held in December 2018 | N/A | N/A | TBC | 200000 | Equitable Share | MM-BUDG | Default | All Wards |  | Attendance Register | M | Manager Public Participation
[5 empty] | 9 | MM-09-18/19 | Development of Public Participation Strategy | Municipal Manager | Administration | Adoption of public participation strategy by June 2019 | Date | Adopted public participation strategy by 30 June 2019 | SCM Processes by September 2018 | Appointment of the Service Provider by December 2018 | Not Achieved | Not Achieved | SCM processes. | To be done in Q3. | 0 | 200000 | Equitable Share | MM-BUDG | Default | All Wards |  | Q1 - SCM Processes Q2-Appt Letter | M | Manager Public Participation
[5 empty] | 10 | MM-10-18/19 | Development of Communication Strategy | Municipal Manager | Administration | Adoption of Communication Strategy by June 2019 | Date | Adopted Communication Strategy by 30 June 2019 | SCM Processes by September 2018 | Appointment of the Service Provider by December 2018 | Not Achieved | Not Achieved | SCM processes. | To be done in Q3. |  | 200000 | Equitable Share | MM-BUDG | Default | All Wards |  | Q1 - SCM Processes Q2-Appt Letter | M | Manager Communication
[5 empty] | 11 | MM-11-18/19 | Mayoral slots | Municipal Manager | Administration | Number of Media slots conducted by June 2019 | Number | 20 Media Slots Conducted by June 2019 | 5 Media slots by September 2018 | 5 Media slots by December 2018 | Achieved | Achieved | N/A | N/A | TBC | 300000 | Equitable Share | MM-BUDG | Default | all wards |  | Attendance Register | M | Manager Communication
[5 empty] | 12 | MM-12-18/19 | Golden games training(football,duck walk,dress up race,pass the ball,500M brisk walk,800Mrun,100M run,200M run,400M run,400M relay,rugby ball throw,juskei,Ring the stick, Pass the ball and kick, ball relay, goal shooting,pegging washing pegs) | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Golden games hosted by June 2019 | Golden games hosted by September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R150,000,00 | equitable share | MM-BUDG | Default | 05,02,01,13,15,17,19,12 ,08 and 11 |  | Attendance Register | L | Sport Officer
[5 empty] | 13 | MM-13-18/19 | Cricket coaching clinics and mini tournaments | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Cricket coaching clinics and mini tournaments by 30 June 2019 | Cricket coaching clinics and mini tournaments by 30 June 2019 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R25,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 14 | MM-14-18/19 | Indigenous Coaching Clinics and mini tournaments (Umlabalaba,Induku,Kho-Kho,Juskei,Drie-Stokies,Incuva,Ingqathu,Amagenda) | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Indigenous Coaching Clinics and mini tournaments (Umlabalaba,Induku,Kho-Kho,Juskei,Drie-Stokies,Incuva,Ingqathu,Amagenda) by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | R120,000,00 | Equitable share | MM-BUDG | Default | 02,05,13,11,15,18,19 and 17 |  | Attendance Register | L | Sport Officer
[5 empty] | 15 | MM-15-18/19 | Tennis Long coaching clinics and mini tournaments | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Tennis Long coaching clinics and mini tournaments by 30 June 2019 | Tennis Long coaching clinics and mini tournaments by 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R30,000,00 | equitable share | MM-BUDG | Default | 5,13,15 |  | Attendance Register | L | Sport Officer
[5 empty] | 16 | MM-16-18/19 | Youth Run Competition | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Youth Run Competition by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | R30,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 17 | MM-17-18/19 | Municipal Sport Indaba | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Number of event hosted by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | R150,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 18 | MM-18-18/19 | Football Coaching Clinics( females) | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Football Coaching Clinics( females) by 30 June 2019 | Football Coaching Clinics(females) by 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R20,000,00 | Equitable share | MM-BUDG | Default | 05,03,01,08,11,12,15,13 and 06 |  | Attendance Register | L | Sport Officer
[5 empty] | 19 | MM-19-18/19 | Rugby Coaching Clinics | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Rugby Coaching Clinics by 30 June 2019 | N/A | Rugby Coaching Clinics by 31 December 2018 | 0 - Not Achived | 0- Not Achived | The sportsfield was not available due to examinations being held. | To be done in quarter 3. | 0 | R20,000,00 | Equitable share | MM-BUDG | Default | 05,04,06,02,11,13,19,15 and 17 |  | Attendance Register | L | Sport Officer
[5 empty] | 20 | MM-20-18/19 | Basket ball coaching clinics and mini tournaments | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | basket ball coaching clinics and mini tournaments by 30 June 2019 | N/A | basket ball coaching clinics and mini tournaments by 31 December 2018 | 1 - Achieved | 1 - Achieved | N/A | N/A | TBC | R20,000,00 | Equitable share | MM-BUDG | Default | 05,06,04,02,08,11,13,15,19,17 |  | Attendance Register | L | Sport Officer
[5 empty] | 21 | MM-21-18/19 | Valleyball coaching clinics and mini tournaments | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Valleyball coaching clinics and mini tournaments by 30 June 2019 | N/A | Valleyball coaching clinics and mini tournaments by 31 December 2018 | 1 - Achieved | 1 - Achieved | N/A | N/A | TBC | R20,000,00 | Equitable share | MM-BUDG | Default | 19,02,14,13,01 |  | Attendance Register | L | Sport Officer
[5 empty] | 22 | MM-22-18/19 | Swimming coaching clinics and swimming gala | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | swimming coaching clinics and swimming gala by 30 June 2019 | swimming coaching clinics and swimming gala by 30 September 2018 | N/A | N/A | 0- Not Achived | The facilitators were not available from Department of Sport and recreation to conduct the coahing | To be done in quarter 3. | 0 | R20,000,00 | Equitable share | MM-BUDG | Default | 01,06,08,03,11,02,13,14,19,18,12 |  | Attendance Register | L | Sport Officer
[5 empty] | 23 | MM-23-18/19 | Karate Coaching Clinics and tournaments | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Karate Coaching Clinics and tournamentsby 30 June 2019 | Karate Coaching Clinics and tournaments 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R30,000,00 | Equitable share | MM-BUDG | Default | 01,05,06,08,11,13,15,19,16 |  | Attendance Register | L | Sport Officer
[5 empty] | 24 | MM-24-18/19 | Dance Coaching Clinics and competition | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Dance Coaching Clinics and competition 30 June 2019 | Dance Coaching Clinics and competition by September 2018 | N/A | N/A | 0- Not Achived | Unavailability of municipal transport to transport people | To be done in quarter 3. | 0 | R30,000,00 | Equitable share | MM-BUDG | Default | 1 |  | Attendance Register | L | Sport Officer
[5 empty] | 25 | MM-25-18/19 | Scathamiya Coaching Clinics | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Scathamiya Coaching Clinics by 30 June 2019 | Scathamiya Coaching Clinics by 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R10,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 26 | MM-26-18/19 | Netball coaching clinics and competition | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Netball coaching clinics and competition by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | R30,000,00 | Equitable share | MM-BUDG | Default | 04,05,06,02,08,01,11,13,14,15.19,16 |  | Attendance Register | L | Sport Officer
[5 empty] | 27 | MM-27-18/19 | Aerobics coaching clinics and marathon | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Aerobics coaching clinics and marathon 30 June 2019 | Aerobics coaching clinics and marathon by 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R20,000,00 | Equitable share | MM-BUDG | Default | 12,13,15,18,19 |  | Attendance Register | L | Sport Officer
[5 empty] | 28 | MM-28-18/19 | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance by 30 June 2019 | N/A | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R900,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 29 | MM-29-18/19 | Women in Sport Symposium and sport day | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Women in Sport Symposium and sport day by 30 June 2019 | Women in Sport Symposium and sport day by 30 Sep 2018 | N/A | N/A | N/A | N/A | N/A | 0 | R150,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 30 | MM-30-18/19 | Promotion of Isigekle | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Promotion of Isigekleby 30 June 2019 | Promotion of Isigekleby 30 September 2018 | N/A | N/A | N/A | N/A | N/A | 0 | R50,000,00 | Equitable share | MM-BUDG | Default | 4,11,13,18,19 |  | Attendance Register | L | Sport Officer
[5 empty] | 31 | MM-31-18/19 | Jonny Makhathini Marathon 5 km and 10 km | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number |  | Jonny Makhathini Marathon 5 km and 10 km by September 2018 | N/A | N/A | N/A | N/A | N/A | 0 | R50,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 32 | MM-32-18/19 | Disability Sport Day | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Disability Sport Day by 30 June 2019 | Disability Sport Day by31 December 2018 | N/A | N/A | N/A | N/A | N/A | 0 | R50,000,00 | Equitable share | MM-BUDG | Default | 2,4,5,9,11,13,14,17,18,19 |  | Attendance Register | L | Sport Officer
[5 empty] | 33 | MM-33-18/19 | Capacity building and training for Sport Confederation Members | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | 1 event by June 2019 | N/ACapacity building and training for Sport Confederation Members by September 2018 | N/A | N/A | N/A | N/A | N/A | 0 | R150,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 34 | MM-34-18/19 | ECD's sport day | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | ECD's sport dayby 30 June 2019 | ECD's sport day 30 September 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R20,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 35 | MM-35-18/19 | Scathamiya Competition | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Scathamiya Competition by 30 June 2019 | Scathamiya Competition 30 September 2018 | N/A | N/A | 2 - Achieved | N/A | N/A | TBC | R30,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 36 | MM-36-18/19 | Hockey Development and tournament | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Hockey Development and tournamentby 30 June 2019 | Hockey Development and tournament by 30 September 2018 | N/A | N/A | 3 - Achieved | N/A | N/A | TBC | R30,000,00 | Equitable share | MM-BUDG | Default | 09,19,17,16,18,15 |  | Attendance Register | L | Sport Officer
[5 empty] | 37 | MM-37-18/19 | Golf development | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Golf development by 30 June 2019 | Golf development 30 June 2018 | N/A | N/A | Not Achieved | Golf Development target not achieved due to unavailability of venue to host. | To be done in Q3. | 0 | R150,000,00 | Equitable share | MM-BUDG | Default | 1,3,8,12 |  | Attendance Register | L | Sport Officer
[5 empty] | 38 | MM-38-18/19 | Diwali Celebration | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Diwali Celebrationby 30 June 2019 | N/A | N/A | 0-Not Ahieved | 0-Not Ahieved | The programme has been moved to the Social Cohesion Unit and has clashed with the SALGA Games. | To be done in the next financial year. | 0 | R15,000,00 | Equitable share | MM-BUDG | Default | 1 |  | Attendance Register | L | Sport Officer
[5 empty] | 39 | MM-39-18/19 | Municipal Sport Award | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Municipal Sport Award by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | R120,000,00 | Equitable share | MM-BUDG | Default | all wards |  | Attendance Register | L | Sport Officer
[5 empty] | 40 | MM-40-18/19 | Chess development and local tournament | Municipal Manager | Administration | Number of event hosted by 30 June 2019 | Number | Chess development and local tournament by 30 June 2019 | Chess development and local tournament by 30 Septmber 2018 | N/A | N/A | 1 - Achieved | N/A | N/A | TBC | R10,000,00 | Equitable share | MM-BUDG | Default | All Wards |  | Attendance Register | L | Sport Officer

## EDP
DEPARTMENT:ECONOMIC DEVELOPMENT AND PLANNING
DIRECTOR: MR S.D.G. KHUZWAYO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  | 2nd Quarter Actual | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Evidence | Weightings | Responsible Manager
[13 empty] | 1st Quarter Target | 2nd Quarter Target |  |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
ECONOMIC DEVELOPMENT AND PLANNING
Local Economic Development | A responsive, accountable, effective and efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 41 | EDP-01-18/19 | Feasbility Study on Purchase of Land for Development ( Residential and Other uses) | EDP | Administration | Council Resolution Adopting the Study by June 2019 | Date | End of 31 December 2018 | Appointment of the Service provider done by 30 September 2018 | Feasibility Study Completed by 31 December 2018 | 1 - Feasibility study completed - Achieved | Appointment of the Service provider and Feasibility Study - Achieved | N/A | N/A | TBC | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards |  | Council Resolution | H | Director: EDP
[5 empty] | 42 | EDP-02-18/19 | Ndwedwe Town Development Proclamation | EDP | Administration | Title Deed/ Certificate of Proclamation by June 2019 | Date | End of June 2019 | Draft Survey Records submitted Report Completed by September 2018 | Final Survey Record/ Report Completed by December 2018 | Final Survey Records submitted Report - Not Ahieved. | Draft Survey Records submitted Report Completed and submitted in September 2018 - Achieved | N/A | N/A | TBC | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards |  | Title Deed/ Certificate of Proclamation by June 2019 | H | Town Planner
[5 empty] | 43 | EDP-03-18/19 | Integrated Transport Plan | EDP | Administration | Council Resolution Adopting the Study by June 2019 | Date | End of June 2019 | Draft Transport Plan report completed by 30 July 2018 | Final Transport Plan Completed by 31 December 2018 | Final Transport Plan Completed - Achieved | Final Transport Plan Completed - Achieved | N/A | N/A | TBC | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards |  | Council Resolution Adopting the Study by June 2019 | H | Director: EDP
[5 empty] | 44 | EDP-04-18/19 | Establishment of x2 Block Making Cooperatives for Housing Projects Supply ( Ndwedwe Central and Bhamshela) | EDP | Administration | 2 x Block Making Cooperatives by June 2019 | Number | 2x Established Block Making Established by June 2019 | Cooperatives Registration and Site Indentification done by 30 September 2018 | Training for Cooperatives done by 31 December 2018 | 1 x Training - Achieved | 2 - Training - Achieved | N/A | N/A | TBC | 1000001 | Internal Funding | EDP-BUDG | Default | Ward 15 and and 2 |  | Registration Certificate | M | Director: EDP
[5 empty] | 45 | EDP-05-18/19 | Establishment of x 4 Commercial Gardens | EDP | Administration | Number of Community Gardens established by June 2019 | Number | 4 functional commercial gardens by June 2019 | Assesments and feasibility studies completed by September 2018 | Assessments of 4 commercial gardens completed by 31 December 2018 | 4 - Assesments of commercial gardens - Achieved. | 4 - Assesmentsof commercial gardens - Achieved. | N/A | N/A | TBC | N/A | Internal Funding | EDP-BUDG | Default | Ward 4, 18,7 and 14 |  | Assessment Reports | M | Manager: LED
[5 empty] | 46 | EDP-06-18/19 | SMME Support | EDP | Administration | Number of SMME supported by June 2019 | Number | x10 SMME supported by June 2019 | x3 SMME supported by September 2018 | 3 SMME Supported by December 2018 | 3 - SMME supported - Achieved. | 6 - SMME supported- Achieved. | N/A | N/A | TBC | R300 000.00 | Internal Funding | EDP-BUDG | Default | All wards |  | Purchase Orders | M | Manager: LED
[5 empty] | 47 | EDP-07-18/19 | 10 Cooperatives supported | EDP | Administration | Number of Cooperatives Supported by June 2019 | Number | x 10 Cooperatives supported by June 2019 | x3 cooperatives supported by September 2018 | 3 cooperatives supported by December 2018 | 3 - Cooperatives supported - Achieved. | 6 - Cooperatives supported - Achieved. | N/A | N/A | TBC | R300 000.00 | Internal Funding | EDP-BUDG | Default | All wards |  |  | M | Manager: LED
|  |  |  | Facilitate the sitting of Housing Forums for stakeholders report on progress | 48 | EDP-08-18/19 | Housing Forum | EDP | Administration | Number of Housing Forums hosted by June 2019 | Number | x4 Housing Forums | X1 Housing Forum hosted | X1 Housing Forum hosted | 1 - Housing Forum hosted - Achieved | 2 - Housing Forum hosted - Achieved | N/A | N/A | TBC | N/A | Internal Funding | EDP-BUDG | Default | All wards |  | attendace Register | M | Director: EDP
[5 empty] | 49 | EDP-09-18/19 | Development of Housing Sector Plan | EDP | Administration | Adoption of Housing Sector Plan by June 2019 | Date | 1 Housing Sector Plan | Appointment of the Service provider done by 30 September 2018 | Draft Housing Sector Plan | Draft Plan not achieved. | Draft Plan not achieved. | The was a shortage of funds to conduct the project due to MSCOA. | The project will be conducted in the Q3. | 0 | R200 000.01 | Internal Funding | EDP-BUDG | Default | All wards |  | Delivery Notes | H | Director: EDP
|  |  |  | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 50 | EDP-10-18/19 | Minifactories Equipment Procument | EDP | Administration | Number of Equipment Purchased by June 2019 | Number | X3 Equipment Procured (Stove, Sewing Machine and AutoMachine) by June 2019 | Specifications and Appointment of the service done done by September 2018 | Delivery of Equipment completed by December 2018 | Not achieved. | Not achieved. | There was delays in the procurement prcoesses. | The procurement will be done in the Q3. | 0 | R200 000.00 | Internal Funding | EDP-BUDG | Default | Ward 15 |  | Delivery Notes | L | Manager: LED
[5 empty] | 51 | EDP-11-18/19 | Tourism Feasbility Study | EDP | Administration | Resolution adopting Tourism Feasbility Study by June 2019 | Date | Tourism Feasbility Study Report and Business Plan | Appointment of the Service provider done by 30 September 2018 | Tourism Feasbility Study Report | Not achieved | Service provider not appointed. | Service provider not appointed. | Insufficient funding to conduct project. | 0 | R200 000.01 | Internal Funding | EDP-BUDG | Default | All wards |  | Delivery Notes | H | Director: EDP

## Tech. Services
DEPARTMENT: TECHNICAL SERVICES
DIRECTOR: MR.D.H.MZOLO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  |  | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
[5 empty] | KPI Ref. No | [7 empty] | 1st Quarter Target | 2nd Quarter Target | 2nd Quarter Actual |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
Technical Services
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 52 | TS-01-18/19 | Dabeka Access Road Ward 1 | Technical Services | Administration | Percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 60% Construction Completed (Site establishment, Mass earthworks, pipe crossings and road bed preparation) by December 2018 | 0% - Not Achieved. Appointment for the Contractor finalised and due for site establishement January 2019 | 20%- Achieved. | The advert was published for appointment of service provider. Appointment letter issued to the Contractor. | The target will be achived in Quarter 3, Project Management Unit will closely provide monitoring on the project | 403451.41 | 3600000 | MIG | TECH-BUDG | Default | 1 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 53 | TS-02-18/19 | Nambithane Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 60% Construction Completed (Site establishment, Mass earthworks, pipe crossings and road bed preparation) by December 2018 | 0% - Not Achieved. The project to be re-advertised | 0 % - Not Achieved. The project to be re-advertised | Tender Validity period expired | The project will be re-prioritised to be advertised in quarter 4 | 0 | 6000000 | MIG | TECH-BUDG | Default | 5 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 54 | TS-03-18/19 | Ward 11 Nkalangwe Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 November 2018 | 80% Construction Completed ( drainange systems, layer works and ancillary works) by September 2018 | 8km complete, commisioning, Operating documentation/as builts - 100% completion by December 2018 | 0% - Not achieved | 2km completed 50% Construction . Not Achieved. | Non performamnce by the contractor | Termination recommended to the Acting Municipal Manager than the outstanding scope of works to be advertised | 0 | 10280000 | MIG | TECH-BUDG | Default | 11 | Completion certificate | H | Manager: PMU
[5 empty] | 55 | TS-04-18/19 | KwaNovimba Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 60% Construction Completed (Site establishment, Mass earthworks, pipe crossings and road bed preparation) by December 2018 | 0% - Not Achieved. The project to be re-advertised | 0% - Not Achieved. The project to be re-advertised | Tender Validity period expired | The project will be re-prioritised to be advertised in quarter 4 | 0 | 3600000 | MIG | TECH-BUDG | Default | 18 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 56 | TS-05-18/19 | Chamani Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 60% Construction Completed (Site establishment, Mass earthworks, pipe crossings and road bed preparation) by December 2018 | 0% - Not Achieved. The project to be re-advertised | 0% - Not Achieved. The project to be re-advertised | Tender Validity period expired | The project will be re-prioritised to be advertised in quarter 4 | 0 | 1100000 | MIG | TECH-BUDG | Default | 16 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 57 | TS-06-18/19 | Mwolokohlo to Sthupha Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the business plan approval by COGTA | The project will be re-prioritised to be advertised in quarter 4 | 0 | 3053931.72 | MIG | TECH-BUDG | Default | 11 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 58 | TS-07-18/19 | Water Fall Sportfield | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | Achieved: Appointment of service provider, returnable documents and site handover to contractor | Achieved: Appointment of service provider, returnable documents and site handover to contractor | N/A | The project will commence quarter 3 January 2019 | 103500 | 7702441.77 | MIG | TECH-BUDG | Default | 3 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 59 | TS-08-18/19 | Ethafeni Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the business plan approval by COGTA | The project will be re-prioritised to be advertised in quarter 4 | 84624.44 | 1677771.52 | MIG | TECH-BUDG | Default | 8 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 60 | TS-09-18/19 | Zesuliwe Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the business plan approval by COGTA | The project will be re-prioritised to be advertised in quarter 4 | 493792.47 | 9875849.4 | MIG | TECH-BUDG | Default | 7 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 61 | TS-10-18/19 | Gudlintaba Access Road | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the business plan approval by COGTA | The project will be re-prioritised to be advertised in quarter 4 | 0 | 2752879.48 | MIG | TECH-BUDG | Default | 17 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 62 | TS-11-18/19 | eMona Community Hall | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor | Actual Achieved: Appointment of service provider, returnable documents and site handover to contractor | Actual Achieved: Appointment of service provider, returnable documents and site handover to contractor | N/A | The project will commence quarter 3 January 2019 | 0 | 5487522.09 | MIG | TECH-BUDG | Default | 15 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 63 | TS-12-18/19 | Siyathokoza Hall & Creche | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor | Achieved - Appointment of service provider, returnable documents and site handover to contractor | Achieved - Appointment of service provider, returnable documents and site handover to contractor | N/A | The project will commence quarter 3 January 2019 | 0 | 4774405 | MIG | TECH-BUDG | Default | 14 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 64 | TS-13-18/19 | Mangangeni CDC | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Approval of Business Plan by MIG COGTA MBPAC and complete design report & drawing | Appointment of service provider, returnable documents and site handover to contractor | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the business plan approval by COGTA | The project will be re-prioritised to be advertised in quarter 4 | 412931.45 | 4474405.5 | MIG | TECH-BUDG | Default | 19 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 65 | TS-14-18/19 | Electrification Onyazini & Khenana Ward 2 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Appointment of service provider, returnable documents and site handover to contractor | 40% Construction - ( Site establishement, Clear and grub, Pole excavation & plantation) | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the Contractor appointment | Bid Committes monitored to finalise the Contractor appointment in January 2019 | 0 | 3500000 | Internal | TECH-BUDG | Default | 2 | Completion certificate | H | Director: Technical Services
[5 empty] | 66 | TS-15-18/19 | Electrification Mcathu Ward 8 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | Design stage-(Design report, Drawing) by September 2018 | Appointment of service provider, returnable documents and site handover to contractor | 0% - Not Achieved. | 0% - Not Achieved. | Delay on the Contractor appointment | Bid Committes monitored to finalise the Contractor appointment in January 2019 | 504000 | 6000000 | INEP | TECH-BUDG | Default | 8 | Completion certificate | H | Director: Technical Services
[5 empty] | 67 | TS-16-18/19 | Electrification Esidumbini & Nkumba Ward 08 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | 40% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | N/A | N/A | 427822.43 | 8927032.81 | INEP & Internal | TECH-BUDG | Default | 8 | Completion certificate | H | Director: Technical Services
[5 empty] | 68 | TS-17-18/19 | Electrification Amabutho Ward 02 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | 40% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | N/A | N/A | 963576.72 | 3545303.95 | INEP & Internal | TECH-BUDG | Default | 2 | Completion certificate | H | Director: Technical Services
[5 empty] | 69 | TS-18-18/19 | Electrification Mary Grey Ward 07 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | 40% Construction - (Pole excavation, Pole plantation,Reticulation lines) by September 2018 | 80% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved Construction - (Pole excavation, Pole plantation,Reticulation lines) | N/A | N/A | 2207785 | 8125149.92 | Internal | TECH-BUDG | Default | 7 | Completion certificate | H | Director: Technical Services
[5 empty] | 70 | TS-19-18/19 | Construction of High Mast Lights Glendale Ward 01 | Technical Services | Administration | percentage completed by 30 June 2019 | Percentage | 100% completion by 30 June 2019 | 40% Construction - (Pole excavation, Pole plantation,Cable lines) by September 2018 | 80% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 80% - Achieved. | 90% - Achieved. |  |  | 1451794.5 | 4197270 | Internal | TECH-BUDG | Default | 1 | Completion certificate | H | Director: Technical Services
[5 empty] | 71 | TS-20-18/19 | Nhlangwini Sports field | Technical Services | Administration | Percentage of construction completed by June 2019 | Percentage | 100% Construction completed by 30 March 2019 | 40% Construction - ( Site establishement, Clear and grub, Structure formation ) by September 2018 | 80% Construction - (Pole excavation, Pole plantation,Reticulation lines) | 60% - Achieved -Construction Completed (Mass earth works, Grassing, Plumbing) | 60% - Achieved -Construction Completed (Mass earth works, Grassing, Plumbing) | N/A | N/A | 895979.92 | 1200000 | MIG | TECH-BUDG | Default | 1 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 72 | TS-21-18/19 | Construction of Technical Dept Offices | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | Advertising, Evaluation by September 2018 | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | 60% Bid Evaluation Committee | Advertising, Evaluation completed-Not Achieved | Delay on the Contractor appointment | Bid Committes monitored to finalise the Contractor appointment in January 2019 | 0 | 9500000 | Internal | TECH-BUDG | Default | 15 | Appointment Letter & Completion certificate | H | Manager: PMU
[5 empty] | 73 | TS-22-18/19 | Hloniphani Hall & Creche ward 12 | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 November 2018 | 60% Construction completed - (Building walls, Roof, Plumbing) by September 2018 | 100% Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achieved -Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achieved -Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) | N/A | N/A | 4264705.15 | 5663741.16 | MIG | TECH-BUDG | Default | 12 | Completion certificate | H | Manager: PMU
[5 empty] | 74 | TS-23-18/19 | Ntabakhathaza Access Road | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 November 2018 | 60% Construction Completed (Mass earthworks, pipe crossings and road bed preparation) by September 2018 | 100% Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | Actual Achieved: 100% Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achieved Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion). | N/A | N/A | 1534739.13 | 2076983.26 | MIG | TECH-BUDG | Default | 2 | Completion certificate | H | Manager: PMU
[5 empty] | 75 | TS-24-18/19 | Mandlakazi Sportfield | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | 60% Construction Completed (Mass earth works, Building/change rooms,Fencing ) | 100% Construction completed - ( Plumbing, Commisioning, Operating documentation/as builts - 100% completion) | 0% - Not Achieved | 60% - Achieved | Delay due to interruption by communities demanding sub-contracting works | The sub-contracting matter was resolved, the project is monitored for completion in Quarter 3 | 3908042.11 | 5173486.15 | MIG | TECH-BUDG | Default | 4 | Completion certificate | H | Manager: PMU
[5 empty] | 76 | TS-25-18/19 | Nhlabamnkosi Access Road | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | 60% Construction Completed (Mass earthworks, pipe crossings and road bed preparation) by September 2018 | 100% Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achived - Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achived - Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2019 | N/A | N/A | 802001.36 | 2140007.4 | MIG | TECH-BUDG | Default | 13 | Completion certificate | H | Manager: PMU
[5 empty] | 77 | TS-26-18/19 | Noorsburg Access Road | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | 60% Construction Completed (Mass earthworks, pipe crossings and road bed preparation) by September 2018 | 100% Construction completed - ( 1.8km complete, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achived - Construction completed - ( 3km complete, Commisioning, Operating documentation/as builts - 100% completion) | 100% - Achived - Construction completed - ( 3km complete, Commisioning, Operating documentation/as builts - 100% completion) | N/A | N/A | 1076983.5 | 2365482.9 | MIG | TECH-BUDG | Default | 6 | Completion certificate | H | Manager: PMU
[5 empty] | 78 | TS-27-18/19 | Sonkombo Sportfield | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | 60% Construction Completed (Mass earth works, Building/change rooms,Fencing ) by September 2018 | 100% Construction completed - ( Plumbing, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | Not Achieved - 20% | 80% completed - Not Achived | The project had additional scope of works therefore extending the completion time in January 2019 | The project will be completed in Quarter 3 January 2019 | 4147500.37 | 9863325.15 | MIG | TECH-BUDG | Default | 11 | Completion certificate | H | Manager: PMU
[5 empty] | 79 | TS-28-18/19 | Nondabula Hall (Ward 09) | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 November 2018 | 60% Construction completed - (Building walls, Roof, Plumbing) by September 2018 | 100% Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achived - Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | 100% - Achived - Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2019 | N/A | N/A | 2211770.07 | 3954131.81 | Internal | TECH-BUDG | Default | 9 | Completion certificate | H | Manager: PMU
[5 empty] | 80 | TS-29-18/19 | Nondwengu Hall & Creche | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Construction completed by 30 June 2019 | 60% Construction completed - (Building walls, Roof, Plumbing) by September 2018 | 100% Construction completed - ( Pavement,Parking, Commisioning, Operating documentation/as builts - 100% completion) by December 2018 | Not Achieved. 20% | 70% completed - Not Achieved. | Delay on the appointment of the Contractor | The project monitored for complettion in Quarter 3 | 2831197.8 | 4674039.21 | MIG | TECH-BUDG | Default | 10 | Completion certificate | H | Manager: PMU
[5 empty] | 81 | TS-30-18/19 | Ndwedwe/Bhamshela Street Light s Upgrade | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | Upgrading of street lights in Ndwedwe & Bhamshela by June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 20% complete upgrade of street lights by december 2018 | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid Specification approval and advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 1970000 | Internal | TECH-BUDG | Default | 6 & 15 | Appointment letter and Completion certificate | H | Director: Technical Services
[5 empty] | 82 | TS-31-18/19 | Mary-Grey Sport Centre Completion | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Complete Mary-Grey Sport Centre by June 2019 | N/A | 20% complete upgrade of street lights by december 2018 | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 300000 | Internal | TECH-BUDG | Default | 7 | Appointment letter and Completion certificate | H | Manager: PMU
[5 empty] | 83 | TS-32-18/19 | Buy Back Centre Structure | Technical Services | Administration | percentage of construction by 30 June 2019 | Percentage | 100% Complete Buy Back Centre Structure by June 2019 | Design stage-(Preliminary design report/inception report, Drawing) by September 2018 | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | Not Achieved | Design report completed-Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 2000000 | Internal | TECH-BUDG | Default | 15 | Appointment letter and Completion certificate | H | Director: Technical Services
[5 empty] | 84 | TS-33-18/19 | Installation of Backup Generator for Electrification | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | Installation of backup Generator for electrification of Municipal Offices by june 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 20% complete upgrade of street lights by december 2018 | 0% - Not Achieved | 0% - Not Achieved | The project was advertised and poor response received from Service Providers | The project was re-advertised and Service Provider will be appointed in Quarter 3 | 0 | 1150000 | Internal | TECH-BUDG | Default | 15 | Appointment letter and delivery report/note of the Generator | H | Manager: Public Works
[5 empty] | 85 | TS-34-18/19 | Augmentation of Water Supply for Ndwedwe Main Office | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | Augmentation of water supply for Ndwedwe Main Office by June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | Not Achieved | Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 2900000 | Internal | TECH-BUDG | Default | 15 | Appointment letter and Completion certificates | H | Manager: Public Works
[5 empty] | 86 | TS-35-18/19 | Local Sports Facilities: Grass Cutting | Technical Services | Administration | number of sport ground completed by 30 June 2019 | Number | 30 sport grounds completed by June 2019 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 10 sport grounds completed by December 2018 | 100% - Achieved: 10 sport grounds completed by December 2018 | 100% - Achieved: 10 sport grounds completed by December 2019 | N/A | N/A | 0 | 1800000 | Internal | TECH-BUDG | Default | All | Inspection Report | M | Manager: Public Works
[5 empty] | 87 | TS-36-18/19 | Rehabilitation of Mthebeni and Febe road | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | Mthebeni access road 100% renovation complete by June 2019 | Visual inspections, project documentation by September 2018 | Appointment of Service Provider, returnable docments and site hand over to contractor | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 700000 | Internal | TECH-BUDG | Default | 14 | Appointment letter and Completion certificate | H | Manager: Public Works
[5 empty] | 88 | TS-37-18/19 | Bhamshela Thusong Centre Renovation | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | 100% completion of Bhamshela Thusong Centre Renovation | N/A | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 300000 | Internal | TECH-BUDG | Default | 6 | Appointment letter and Completion certificate | H | Manager: Public Works
[5 empty] | 89 | TS-38-18/19 | Johnny Makhathini Hall Renovation | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | 100% completion of Jonny Makhathini Hall Renovation by June 2020 | Appointment of service provider, returnable documents and site handover to contractor by September 2018 | 50% Renovations complete | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 800000 | Internal | TECH-BUDG | Default | 15 | Appointment letter, Progress report and Completion certificate | H | Manager: Public Works
[5 empty] | 90 | TS-39-18/19 | Ndwedwe Public Library Renovation | Technical Services | Administration | percentage of completion by 30 June 2019 | Percentage | 100% completion of Ndwedwe Public Library Renovation by June 2019 | N/A | Appointment of service provider, returnable documents and site handover to contractor by December 2018 | 0% - Not Achieved | 0% - Not Achieved | Delay on the Bid advertisement | The project to be advertised in Quarter 3 January 2019 | 0 | 700000 | Internal | TECH-BUDG | Default | 15 | Appointment letter, Progress report and Completion certificate | H | Manager: Public Works
[5 empty] | 91 | TS-40-18/19 | EPWP - Waste management | Technical Services | Administration | Number of Work opportunities created by June 2019 | Number | 120 EPWP participants by June 2019 | 58 participants by September 2018 | N/A | N/A | N/A | N/A | N/A |  | 400000 | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works
Note on P29: Lee-Anne Naidoo: Q1 - 40% - Q 2 60%

## Corp. Services
DEPARTMENT: CORPORATE SERVICES
DIRECTOR: DR M.G. NTULI
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  |  | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Evidence | Weightings | Responsible Manager
[5 empty] | KPI Ref No. | [7 empty] | 1st Quarter Target | 2nd Quarter Target | 2nd Quarter Actual |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
CORPORATE SERVICES
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive, accountable, effective and efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 92 | CS-01-18/19 | Reviews and Development of Policies | Corporate Services | Administration | Number of policies reviewd and developed by the 30th June 2019 | Number | 16 policies reviewed /developed by 30th June 2019 | N/A | 4 policies reviewed /developed by 30th December 2018 | Not Achieved | 0 - Not achieved |  | The policies will be done in Q3. | TBC | N/A | Municipality | DCS-BUDG | Default | N/A | Reviewed Policices & attendance Registers |  | M | Director: Corporate Services
[5 empty] | 93 | CS-02-18/19 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | Number of WSP training programmes implemented as per WSP by end of financial year by June 2019 | Number | 12WSP training programmes implemented as per WSP by 30 June 2019 | 3 WSP training programmes implemented as per WSP by 30 September 2018 | 3 WSP training programmes implemented as per WSP by December 2018 | Achieved | 6 - Achieved | N/A | N/A | TBC | 1000000 | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract |  | M | Manager: Human Resource
[5 empty] | 94 | CS-03-18/19 | Filling budgeted posts | Corporate Services | Administration | Number of Budgeted posts filled by June 2019 | Number | 25 Budgeted posts be filled by 30 June 2019 | 10 Budgeted posts be filled by 30 September 2018 | 5 Budgeted posts be filled by December 2018 | Achieved | 15 - Achieved | N/A | N/A | TBC | N/A | Municipality | #REF! | Default | N/A | Adverts, Appointment Letters |  | M | Manager: Human Resource
[5 empty] | 95 | CS-04-18/19 | Job Descriptions Evaluation | Corporate Services | Administration | % of posts evaluated by the Unit and moderated by June 2019 | Percentage | 100% of posts evaluated by the Job Evaluation Unit by 30 June 2019. | 25 % of posts evaluated by the Unit by September 2018 | 50 % of posts evaluated by the Unit by September 2018 | Not Achieved | Not Achieved | The project will be done in Q3. | The project will be done in Q3. | TBC | N/A | Municipality | DCS-BUDG | Default | N/A | Evaluation Report |  | M | Director: Corporate Services
[5 empty] | 96 | CS-05-18/19 | Cascade individual performance management to managers. | Corporate Services | Administration | Number of employees with signed performance agreements by 30 June 2019 | Number | 30 employees with signed performance agreements by 30 June 2019 | 15 employees with signed performance agreements by 30 September 2018 | 5 employees with signed performance agreements by 30 December 2018 | 5 - Achieved | 5 - Achieved | N/A | N/A | TBC | N/A | Municipality | DCS-BUDG | Default | N/A | Perfomance Agreements |  | M | Director: Corporate Services
[5 empty] | 97 | CS-06-18/19 | Conduct Employee wellbeing Programmes (includes EAP and OHS) | Corporate Services | Administration | Number of EWP Campaigns of of employee wellness conducted by June 2019 | Number | 4 EWP campaigns conducted by 30 June 2019 | 1 EWP campaigns conducted by 30 September 2018 | 1 EWP campaign conducted by 30 December 2018 | 1 - Achieved | 2 - Achieved | N/A | N/A | TBC | 400000 | Municipality | DCS-BUDG | Default | N/A | Attendance Register |  | M | Manager: Human Resource
[5 empty] | 98 | CS-07-18/19 | Implement, test and maintain ICT system backups | Corporate Services | Administration | Number of successful backups conducted by June 2019 | Number | 12 backup reports submitted by June 2019 | 3 reports submitted by 30 September 2018 | 3 reports submitted by 31 December 2018 | Not Achieved | Not Achieved | Tender awaiting adjudication and appointment | Tender will be adjudicated 15/01/2019 | 0 | 300000 | Municipality | DCS-BUDG | Default | N/A | Backup Reports |  | M | Manager: IT
[5 empty] | 99 | CS-08-18/19 | Conduct bi-annual municipal data recovery | Corporate Services | Administration | Number of successful data recovery test reports by June 2019 | Number | 2 data recovery test reports by June 2019 | n/a | 1 report submitted by 31 December 2018 | Not Achieved | Not Achieved | Tender awaiting adjudication and appontment | Tender will be adjudicated 15/01/2019 | 0 | 400000 | Municipality | DCS-BUDG | Default | N/A | Data recovery reports |  | M | Manager: IT
[5 empty] | 100 | CS-09-18/19 | Investment in ICT infrastructure | Corporate Services | Administration | Number of monthly evaluation and monitoring reports by June 2019 | Number | 12 monthly evaluation and monitoring reports by June 2019 | 3 reports submitted by 30 September 2018 | 3 reports submitted by 31 December 2018 | Not Achieved | Not Achieved | Tender awaiting adjudication and appointment | Tender will be adjudicated 15/01/2019 | 0 | 780000 | Municipality | DCS-BUDG | Default | N/A | Evaluation and Monitoring Reports |  | M | Manager: IT
[5 empty] | 101 | CS-10-18/19 | Ctrack System | Corporate Services | Administration | Number of monthly systeme generated reports by June 2019 | Number | 12 monthly C track systerm generated report by June 2019 | 3 reports submitted by 30 September 2018 | 3reports submitted by 31 December 2018 | 3 - Achieved | 6- Achieved | N/A | N/A | TBC | n/A | Municipality | DCS-BUDG | Default | N/A | Ctrack system reports |  | M | Manager : Administration
[5 empty] | 102 | CS-11-18/19 | Branding of 33 municipal vehicles | Corporate Services | Administration | number of vehicles branded by June 2019 | Number | 33 municipal vehicle branded by June 2019 | 2 vehicles branded by September 2018 | 3 vehicles branded by December 2018 | Not Achieved | 2 - Achieved | Two vehicles branded instead of three | SCM processes | TBC | 600000 | Municipality | DCS-BUDG | Default | N/A | Branded Cars |  | M | Manager : Administration
[5 empty] | 103 | CS-12-18/19 | Installation of cameras on 4 municipal plant | Corporate Services | Administration | number of cameras installed in municipal vehicles by June 2019 | Number | 4 cameras installed in municipal plant June 2019 | N/A | 2 plants installed cameras December 2018 | Not Achieved | Not Achieved | Bid process | SCM processes |  | 136000 | Municipality | DCS-BUDG | Default | N/A | Delivery Notes |  | M | Manager : Administration
[5 empty] | 104 | CS-13-18/19 | Installation of E fuel 29 municipal vehicles | Corporate Services | Administration | number of municipal vehicles installed by June 2019 | Number | 29 vehicles intalled by June 2019 | n/a | N/A | Not Achieved | Not Achieved | Bid process | SCM processes |  |  | Municipality | DCS-BUDG | Default | N/A | Delivery Notes |  | M | Manager : Administration
[5 empty] | 105 | CS-14-18/19 | Implementation of Biometric Systerm Register | Corporate Services | Administration | Number of biometric systerms register implemented by 30 June 3019 | Number | Implementation of functional biometric systerms & 12 reports presented by 30 June 2019 | 3x Biometric systerm reports presented by 30 September 2018 | 3x Biometric systerm reports presented by 31 December 2018 | 3 - Achieved | 6 - Achieved | N/A | N/A | TBC |  | Municipality | DCS-BUDG | Default | N/A | Biometrics Reports |  | M | Manager: IT
[5 empty] | 106 | CS-15-18/19 | Review of organisational structure | Corporate Services | Administration | Number of organisational structure reviewed and approved by the Council on 30 June 2019 | Number | 1x 2018/2019 approved organisational structure by June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | TBC |  | Municipality | DCS-BUDG | Default | N/A | Council Resolution |  | M | Manager: Human Resource
[5 empty] | 107 | CS-16-18/19 | Bursary Scheme and Once off registration fees | Corporate Services | Administration | Number of students/ employes granted bursaries by 30 June 2019 | Number | 15 students granted with bursaries June 2019 | N/A | Advertise bursaries for 2019 academic year by December 2018 | Achieved | Achieved | N/A | N/A | TBC | 800000 | Municipality | DCS-BUDG | Default | N/A | Bursary Report |  | M | Manager: Human Resource
[5 empty] | 108 | CS-17-18/19 | Employment Equity Plan | Corporate Services | Administration | Number of employment equity plan submitted to department of labour by June 2019 | Number | 1x Employment Equity report submitted to Department of labour by June 2019 | Development of employment Equity Plan by September 2018 | N/A | N/A | 1 - Plan Achieved | N/A | N/A | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Employment Equity Reports |  | M | Manager: Human Resource
[5 empty] | 109 | CS-18-18/19 | Community skills support programme | Corporate Services | Administration | Number of Interns recruited by 30 June 2019 | Number | 8 Interns and 6 Inservice trainees by June 2019 | 2 Interns appointed by 30 September 2018 | 2 Interns appointed by 31 December 2018 | Achieved | 7 - Interns appointed - Achieved | Waiting for appointment letters from Department | N/A | TBC | N/A | Municipality | DCS-BUDG | Default | N/A | Appointment Letters |  | M | Manager: Human Resource

## Finance
DEPARTMENT: FINANCE
SENIOR MANAGER: MR S.G. MAJOLA
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  |  | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards |  | Evidence | Weightings | Responsible Manager
[13 empty] | 1st Quarter Target | 2nd Quarter Target | 2nd Quarter Actual |  |  |  | Budget Spent for Mid Term | [5 empty] | Evidence
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
FINANCE
Financial Viability and Management | A responsive, accountable, effective and efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management | 110 | F-01-18/19 | Transactional mSCOA Reports | FINANCE | Administration | number of transactional Mscoa reports to Finance Portfolio and Council for 2018 /2019 | Number | 12 transactional Mscoa Reports by 30 June 2019 | 3 transactional Mscoa Report presented by 30 September 2018 | 3 transactional Mscoa Reports presented by 31 December 2018 | 3 -Achived | 6 - Achieved | N/A | N/A | R200,000,00 | R400,000,00 | Municipality | FIN-BUDG | Default | N/A |  | 12 Reports | H | CFO
[5 empty] | 111 | F-02-18/19 | Financial Reporting | FINANCE | Administration | number of MFMA reports submitted on time by June 2019 | Number | 12 MFMA Reports submitted on time after the end of Quarter by June 2019 | 3 monthly Reportssubmitted on time after the end of Quarter by September 2018 | 3 monthly Reportssubmitted on time after the end of Quarter December 2018 | 3 - Achived | 6 - Achieved | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | CFO
[5 empty] | 112 | F-03-18/19 | Budget for 2019/ 2020 | FINANCE | Administration | Approved final Budget adopted by the Council by June 2019 | Date | adopted 2018/2019 Budget by the Council as at 30 June 2019 | Adopted budget process plan by September 2018 | IDP Budget Consultation meetings done by December 2018 | N/A | 1 - Achieved | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Budget
[5 empty] | 113 | F-04-18/19 | Adjusted Budget for 2018/ 2019 | FINANCE | Administration | Approved of Adjusted Budget adopted by the Council by June 2019 | Date | Adopted Adjusted Budget by 30 June 2019 | N/A | N/A | N/A | N/A - To be done in Q3. | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Budget
[5 empty] | 114 | F-05-18/19 | Finances Policies (SCM,Tarrif, Credit Control Policy, S and T, Overtime Policy, Banking and investment, Budget, Indigent, Fixed Assets, Rates, Virement and Disposal) | FINANCE | Administration | Num ber. of Finance Policies developed and Reviewed by 30 May 2019 | Number | 11 Policies Adopted by Council by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Council Resolutions | H | CFO
[5 empty] | 115 | F-06-18/19 | Collection of Revenue | FINANCE | Administration | percentage of revenue collected by 30 June 2019 | Percentage | 70% of collected revenue by 30 June 2019 | 10% of revenue collected by September 2018 | 15% of revenue collected by December 2018 | 15% - Achived | 25% - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Revenue Reports | H | Mananger: Finance
[5 empty] | 116 | F-07-18/19 | General Evaluation Roll | FINANCE | Administration | Adopted General Valuation Roll done by 30 June 2019 | Date | 1 Adopted General Valuation Roll Report by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | R100,000,00 | R200,000,00 | N/A | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Finance
[5 empty] | 117 | F-08-18/19 | Screening of State Employees from SCM Database | FINANCE | Administration | No of reports generated for each quarter by June 2019 | Date | Four Quarterly reports generated by 30 June 2019 | 1 quarterly reports generated by 30 September 2018 | 1 quarterly reports generated by 30 December 2018 | 1 - Achived | 2 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 4 Reports | H | Mananger: SCM
[5 empty] | 118 | F-09-18/19 | Appointment of Local Service Providers | FINANCE | Administration | Reports on appointed local service providers submitted to Council Portfolio committee by 30 June 2019 | Date | four quarterly reports submitted to Council Portfolio committee by 30 June 2019 | 1 quarterly report submitted to Council Portfolio committee by 30 September 2018 | 1 quarterly report submitted to Council Portfolio committee by 31 December 2018 | 1 - Achived | 2 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 4 Reports | H | Mananger: SCM
[5 empty] | 119 | F-10-18/19 | Indigent register | FINANCE | Administration | Approved indigent register by 30 June 2019 | Date | 1 Approved indigent register by 30 June 2019 | N/A | Appointment of service provider by December 2018 | Appoint of Service Provider - Achieved | Appoint of Service Provider - Achieved | N/A | N/A | R2 500,000,00 | R3 200,000,00 | Municipality / COGTA | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Finance
[5 empty] | 120 | F-11-18/19 | Governance Reports ( Debtors Reconciliation Book) | FINANCE | Administration | number of debtors reconciliation by June 2019 | Number | 12 debtors reconciliation submitted by 30 June 2019 | 3 Monthly Reports produced by 30 September 2018 | 3 Monthly Reports produced by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 121 | F-12-18/19 | Property Rates Reconciliation | FINANCE | Administration | number of Property rates reconciliations by 30 June 2019 | Number | 12 Property Rates Reconciliations by June 2019 | 3 Monthly Reports produced by 30 September 2018 | 3 Monthly Reports produced by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Reports | H | Mananger: Finance
[5 empty] | 122 | F-13-18/19 | Consumer Deposit Reconciliation | FINANCE | Administration | number of consumer deposit reconciliation by 30 June 2018 | Number | 12 Consumer Deposit Reconciliations by June 2019 | 3 Monthly Reports produced by 30 September 2018 | 3 Monthly Reports produced by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 123 | F-14-18/19 | Bank Reconciliation | FINANCE | Administration | Number of Bank Reconciliation Report by June 2019 | Number | 12 Bank Reconciliations by June 2019 | 3 Monthly Reports produced by 30 September 2018 | 3 Monthly Reports produced by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 124 | F-15-18/19 | Investments | FINANCE | Administration | Number of monthly investments reports by June 2019 | Number | 12 Monthly Investments Reports by 30 June 2019 | 3 Monthly Reports produced by 30 September 2018 | 3 Monthly Reports produced by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 125 | F-16-18/19 | Grant Register | FINANCE | Administration | percentage of accurate grant register | Percentage | 12 monthly grant registers by 30 June 2018 | 3 monthly reports grant register by September 2018 | 3 monthly reports grant register by December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Registers | H | Mananger: Finance
[5 empty] | 126 | F-17-18/19 | Creditors Payment | FINANCE | Administration | number of days from submission by 30 June 2019 | Number | 30 Days from submission by 30 June 2019 | Payment of Invoice 30 days from submission by September 2018 | Payment of Invoice 30 days from submission December 2018 | 1 Payment -Achived | 1 Payment -Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Age analysis Reports | H | Mananger: Finance
[5 empty] | 127 | F-18-18/19 | Staff/ Councillors Salaries | FINANCE | Administration | Remuneration reports by June 2019 | Date | 12 Remuneration reports by June 2019 | 3 monthly remuneration reports by 30 September 2018 | 3 monthly remuneration reports by 30 December 2018 | 3 - Achived | 6 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 128 | F-19-18/19 | Third Party Payments | FINANCE | Administration | Number of Third Party Payments produced by June 2019 | Number | Last day of the month for 3rd parties by June 2019 | Last day of each month for 3rd parties by September 2018 | Last day of each month for 3rd parties December 2018 | 1 Payment-Achived | 1 Payment -Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Third party payment report | H | Mananger: Finance
[5 empty] | 129 | F-20-18/19 | AFS 2017/ 2018 | FINANCE | Administration | Adopted AFS for 2017/2018 by June 2019 | Date | Adopted AFS for 2017/2018 by 30 June 2019 | Financial Statements submitted to Auditor General, Treasury and CoGTA - 31 August 2018 | N/A | N/A | AFS - 29 August 2018 - Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | Council Resolutions | H | CFO
[5 empty] | 130 | F-21-18/19 | Quarterly Financial Statements 2017/ 2018 | FINANCE | Administration | Number of financial statement prepared and submitted by 30 June 2018 | Number | 2 Financial statement prepared and submitted by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | R200,000,00 | R400,000,00 | N/A | FIN-BUDG | Default | N/A |  | Financial statement report | H | CFO
[5 empty] | 131 | F-22-18/19 | Revenue Enhancement Strategy | FINANCE | Administration | Council adopted Revenue Enhancement Strategy by 30 June 2019 | Date | Council approved Revenue Enhancement Strategy by 30 June 2019 | N/A | Review of Revenue Enhancement Strategy by December 2018 | Strategy - Achieved | Strategy - Achieved | N/A | N/A | R100,000,00 | R200,000,00 | Equitable Share | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Finance
[5 empty] | 132 | F-23-18/19 | Supplementary Valuation Roll | FINANCE | Administration | Council Approved New Valuation Roll by 30 June 2019 | Date | Appointing New Municipal Value by June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | R750,000,00 | R1500,000,00 | Equitable Share | FIN-BUDG | Default | N/A |  | Council Resolutions | H | Mananger: Finance
[5 empty] | 133 | F-24-18/19 | Municipal Billing | FINANCE | Administration | Number of Billing Reports generated by 30 June 2019 | Number | 12 Monthly Billing Reports by 30 June 2019 | Prepare 3 Monthly Billing Reports by September 2018 | Prepare 3 Monthly Billing Reports by December 2018 | 3 Billing reports- Achived | 6 Billing reports- Achived | N/A | N/A | Salaries | Salaries | N/A | FIN-BUDG | Default | N/A |  | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 134 | F-25-18/19 | SCM Report | FINANCE | Administration | Number of Monthly SCM reports submitted to Council by 30 June 2019 | Number | 4 SCM Report submitted to council by 30 June 2019 | 1 SCM Report submitted to council by September 2018 | 1 SCM Report submitted to Council by December 2018 | 1 SCM Report - Achived | 2 SCM Report - Achived | N/A | N/A | Salaries | Salaries | Equitable Share | FIN-BUDG | Default | N/A |  | 4 Monthly Reports | H | Manager: SCM

## Community Services
DEPARTMENT: COMMUNITY SERVICES
DIRECTOR: VACANT
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target |  |  |  | BI-ANNUAL Actual July - Dec | Reason for not Achived | Corrective Measures |  | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Evidence | Weightings | Responsible Manager
[5 empty] | KPI Ref. No. | [7 empty] | 1st Quarter Target | 2nd Quarter Target | 2nd Quarter Actual |  |  |  | Budget Spent for Mid Term
[13 empty] | July-Sept | Oct-Dec | Oct-Dec
PERFORMANCE PLAN 2018-2019
COMMUNITY SERVICES
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of infrastructure | 135 | COM-01-18/19 | Completion of Sonkombo and Anchor Departments Occupation | Community and Social Services | Administration | number of anchor departments in the centre by 30 June 2019 | Number | 3 Anchor Departments operational in the Centre by 30 June 2019 | Refurbishments completed by September 2018 | 1 Occupancy by December 2018 | 1 - Achieved | 1- Achieved | N/A | N/A | N/A | R5 million | Department of CoGTA | COMM-BUDG | Default | Ward 11 | Completion Certificate and Lease Agreements | Awaiting completion certificate | M | Manager:Community Services
[5 empty] | 136 | COM-02-18/19 | Municipal Waste collection to the Landfill Site | Community and Social Services | Administration | number of collections by 30 June 2019 | Number | 168 Collections until 30 June 2019 | 16 collections per collection site done from all sites by September 2018 | 16 collections per collection site done from all sites by December 2018 | 16 - Achieved | 32 - Achieved | N/A | N/A | N/A | 900000 | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms |  | H | Manager:Community Services
[5 empty] | 137 | COM-03-18/19 | Establishment of the Buy-Back Centre | Community and Social Services | Administration | Newly established Buy-Back Centre by June 2019 | Number | 1 Buy-Back Centre constructed by 30 June 2019 | Draft Designs approved by September 2018 | Project Inception by December 2018 | Not achieved | 0 - Not Achieved | Land disputes not resolved between the Municipality and ITB. | IGR engagements are on-going to resolve the matter. | 0 | R2 million | Equitable Share | COMM-BUDG | Default | Ward 15 | Completion Certificate |  | H | Manager:Community Services
[5 empty] | 138 | COM-04-18/19 | Disaster Awareness Campaigns | Community and Social Services | Administration | number of campaigns by 30 June 2019 | Number | 4 Campaigns by 30 June 2019 | 1 Awareness campaign by September 2018 | 1 Awareness campaign by December 2018 | 1 - Achieved | 2 - Achieved | N/A | N/A | 25000 | 50000 | Equitable Share | COMM-BUDG | Default | Clustered wards | Attendance Register of Participants |  | H | Manager:Community Services
[5 empty] | 139 | COM-05-18/19 | Disaster Management Advisory Meetings | Community and Social Services | Administration | number of quartely meetings to be held by 30 June 2019 | Number | 4 Quartely Meetings to be held by 30 June 2019 | 1st Quarter Advisory Meeting held by 30 September 2018 | 2nd Quarter Advisory Meeting held by December 2018 | 0 - Not achieved | 1 - Achieved | The dates coincided with the Council meeting which changed its scheduled date. | To be held in the Q 3. | 12500 | 50000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants |  | M | Manager:Community Services
[5 empty] | 140 | COM-06-18/19 | Local Disaster Management Workshops | Community and Social Services | Administration | number of workshops by June 2019 |  | 4 Workshops by 30 June 2019 | 3 Workshops by 30 June 2019 | 2 Workshops by 30 June 2019 | 2 - Workshops was held - Achieved | 2 - Workshops was held - Achieved | N/A | N/A | 25000 | 50000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants |  | M | Manager:Community Services
[5 empty] | 141 | COM-07-18/19 | Review of the Disaster Management Sector Plan | Community and Social Services | Administration | Number of Reviewed Disaster Management Plan by June 2019 | Number | Adopted Disaster Management Plan by 30 June 2019 | Presenting finding, conducting site visits and review data based on the Ward Based Risk Assessments conducted. Ongoing of staff on risk assessment tools. By September 2018 | Establish processes for comprehensive disaster risk assessments by December 2018 | 1 - Achieved | 1 - Achieved | N/A | N/A |  | 200000 | Equitable Share | COMM-BUDG | Default | All Wards | Reviewed Disaster Management Plan |  | H | Manager:Community Services
[5 empty] | 142 | COM-08-18/19 | Development of safety plan | Community and Social Services | Administration | Number of Developed Safety Plan by June 2019 | Number | Developed Safety Plan by 30 June 2019 | Municipal Ward Safety Assessment by September 2018 | Municipal Ward Safety Assessment by December 2018 | 1 - Saftey Assessments - Achieved | 2 - Saftey Assessments - Achieved | N/A | N/A |  | 200000 | Equitable Share | COMM-BUDG | Default | All Wards | Developed Safety Plan |  | H | Manager:Community Services
[5 empty] | 143 | COM-09-18/19 | Youth Welding Skills Programme | Community and Social Services | Administration | Number of Youth Assisted June 2019 | Number | 60 Youth assisted by 30 June 2019 | 30 Youth Assisted by September 2018 | N/A | N/A | 30 Youth assisted - Achieved | N/A | N/A | 50000 | 100000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 144 | COM-10-18/19 | Nongoma Royal Reed Dance | Community and Social Services | Administration | Number of Maidens Participated in the Reed Dance by June 2019 | Number | 500 Maidens Participated by 30 June 2019 | 500 Maidens Participated by September 2018 | N/A | N/A | 500 Maidens - Achieved | N/A | N/A | 200000 | 200000 | Equitable Share and Department of Arts and Culture | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 145 | COM-11-18/19 | Grade 9 and Grade 10 Career Guidance | Community and Social Services | Administration | Number of Learners Participated by June 2019 | Number | 1200 Learners Participated by 30 June 2019 | 1200 Learners Participated by September 2018 | N/A | N/A | 1200 Learners Participation - Achieved | N/A | N/A | 150000 | 150000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 146 | COM-12-18/19 | Youth Arts and Culture Festival | Community and Social Services | Administration | Number of Arts and Culture Festival hosted by June 2019 | Number | 01 Arts and Culture Festival hosted by 30 June 2019 | Festival Cluster Festival Build-up Competitions by September 2018 | Arts and Culture Festival hosted by December 2018 | 1 - Achieved | 1 - Achieved Indayi Festival. | Incorporated under Indayi Fesival | N/A | 350000 | 350000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 147 | COM-13-18/19 | Examination Prayer Programme | Community and Social Services | Administration | Number of Learners Attended by June 2019 | Number | 1500 Learners Attended by 30 June 2019 | N/A | Prayer Programme Hosted by December 2019 | 1500 Learners Participation - Achieved | 1500 Learners Participation - Achieved | N/A | N/A | 200000 | 200000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 148 | COM-14-18/19 | Youth Sewing and Garmet making skills prgramme | Community and Social Services | Administration | Number of Youth Attended by June 2019 | Number | 80 Youth Attended by 30 June 2019 | N/A | 40 Youth Trained by december 2018 | Not achieved | Not achieved |  |  | 0 | 100000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 149 | COM-15-18/19 | Youth Farming Programme | Community and Social Services | Administration | Number of Youth Attended by June 2019 | Number | 80 Youth Attended by 30 June 2019 | 40 Youth Trained by September 2018 | N/A | N/A | 40 Youth Trained - Achieved | N/A | N/A | 60000 | 120000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 150 | COM-16-18/19 | Right to Learn Campaign | Community and Social Services | Administration | Number of Youth Participated by June 2019 | Number | One event hosted by 30 June 2019 | N/A | N/A | Not achieved | Not achieved |  | To be held on the 18th January 2019 in the Q 3. | 0 | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 151 | COM-17-18/19 | Drivers Licence Programme Code 14 | Community and Social Services | Administration | Number of Youth Participated by June 2019 | Number | 19 Youth participated by 30 June 2019 | Recruitment of 19 youth by September 2018 | Appointment of the Service Provider by December 2018 | Achieved | 19 Youth participated - Achieved | N/A | N/A |  | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 152 | COM-18-18/19 | Youth Month Lecture June 16 | Community and Social Services | Administration | Number of Youth Participated by June 2019 | Number | 1300 Youth Participated by 30 June 2019 | N/A | N/A | N/A | N/A | N/A | To be done in Q 3. | 0 | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 153 | COM-19-18/19 | Youth Art Work Programme | Community and Social Services | Administration | Number of Youth assisted by June 2019 | Number | 40 Youth asssisted by 30 June 2019 | N/A | 20 Youth assisted by December 2018 | Achieved | 20 Youth assisted - Achieved | N/A | N/A | 40000 | 80000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 154 | COM-20-18/19 | Youth Council Advisory Meeting | Community and Social Services | Administration | Number of Youth Attended by June 2019 | Number | 176 Youth attended by 30 June 2019 | 48 Youth attended by September 2018 | 40 Youth attended by December 2018 | Achieved | 88 Youth attended - Achieved | N/A | N/A |  | 80000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 155 | COM-21-18/19 | Job Readiness Programme | Community and Social Services | Administration | Number of Youth assisted by June 2019 | Number | 200 Youth Assisted by 30 June 2019 | N/A | 100 Youth assisted by December 2018 | Not achieved | Not achieved |  | To be held on the 24th January 2019 in Q 3. | 0 | 100000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 156 | COM-22-18/19 | Youth Campaign on social ills | Community and Social Services | Administration | Number of Youth Participated by June 2019 | Number | 1000 Youth Participated by June 2019 | N/A | 1000 Youth Partiicipated by December 2018 | 1000 Youth Partiicipated - Achieved | 1000 Youth Partiicipated - Achieved | N/A | N/A | 200000 | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services
[5 empty] | 157 | COM-23-18/19 | Library Computer Training | Community and Social Services | Administration | Number of learners trained by June 2019 | Number | 180 learners trained by 30 June 2019 | 60 learners trained by 30 September 2018 | N/A | 60 learners trained - Achieved | 60 learners trained - Achieved | N/A | N/A | TBC | N/A | N/A | COMM-BUDG | Default | All Wards | Attendance Register |  | M | Manager:Community Services