## MM Org SCard
DEPARTMENT: OFFICE OF THE MUNICIPAL MUNICIPAL
MUNICIPAL MANAGER: MR M.F.HADEBE
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit of Measure | Annual Target | 2nd QUARTER TARGET End Dec 2018 | 2nd QUARTER ACTUAL End Dec 2018 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
ORGANISATIONAL SCORECARD 2019-2020
MUNICIPAL MANAGER PERFORMANCE PLAN
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 1 | MM-01-19/20 | Internal Audit Reporting to Audit Committee | Municipal Manager | Administration | Number of reports submitted to Audit Committee by 30 April 2020 | Number | 4 submitted to Audit Committee by 30 April 2020 | 1 report submitted by 30 October 2019 | 1 report submitted | 2 Reports submitted by December 2019 | Achieved. 2 Reports submitted | N/A | N/A | N/A | Salaries | Salaries | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 2 | MM-02-19/20 | Tabling of Annual Report 2018/2019 to Council within 9 months after the end of a financial year | Municipal Manager | Administration | Approved Annual Report for 2018/2019 by 31 March 2020 | Date | Adopted Annual Report by 31 March 2020 | N/A | N/A | Draft Annual Performance Report adopted by Council by August 2019 | Achieved. Draft Annual Report adopted by Council in August 2019 | N/A | N/A | N/A | Salaries | Salaries | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 3 | MM-03-19/20 | Tabling of Oversight report on the AR 2018/2019 to Council by no later than 2(two) months from the date in which the AR was tabled as per MFMA Section 127 (5) | Municipal Manager | Administration | Approved Oversight Report for 2018/2019 by 31 March 2020 | Date | Adopted Oversight Report for 2018/2019 by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Equitable Share | MM-BUDG | Default | Municipality | Council Resolution | H | Chaiperson MPAC
[5 empty] | 4 | MM-04-19/20 | IDP/Budget/PMS Process Plan 2020/2021 | Municipal Manager | Administration | Adoption of Process Plan by 30 September 2019 | Date | Process Plan adopted by 30 September 2019 | N/A | N/A | Adoption of Process Plan for 2020/2021 by 30 September 2019 | Achieved. Adoption of Process Plan for 2020/2021 on 29 August 2020 | N/A | N/A | N/A | Salaries | N/A | MM-BUDG | Default | Municipality | Council Resolution | H | Manager IDP/PMS
[5 empty] | 5 | MM-05-19/20 | Speaker Izimbizo | Municipal Manager | Administration | Number of Izimbizo Hosted by June 2020 | Number | 2 Izimbizo hosted by 30 June 2020 | 1 Izimbizo 31 December 2019 | 1 Izimbizo held in December 2019 | 1 Izimbizo 31 December 2019 | Achieved. 1 Izimbizo held in December 2019 | N/A | N/A | N/A | 200000 | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register of Participants | M | Manager Public Participation
[5 empty] | 6 | MM-06-19/20 | Mayoral/IDP Izimbizo | Municipal Manager | Administration | Number of mayoral/ IDP Izimbizo by 30 June 2020 | Number | 8 Mayoral/ IDP Izimbizo by 30 June 2020 | 4 Izimbizo by 31 December 2019 | 4 Izimbizo held in December 2019 | 4 Izimbizo by 31 December 2019 | Achieved. 4 Izimbizo held in December 2019 | N/A | N/A | N/A | 1000000 | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 7 | MM-07-19/20 | Ward Committees Training | Municipal Manager | Administration | Number of Ward Committees training by 31 December 2019 | Number | 1 Training conducted by 31 December 2019 | 1 Training conducted by 31 December 2019 | 1 Training conducted | 1 Training conducted by 31 December 2019 | Achieved. 1 Training conducted | N/A | N/A | N/A | 1250000 | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 8 | MM-08-19/20 | Ward Committees Quartely Meeting | Municipal Manager | Administration | Number of Ward Committee meetings hosted by 30 June 2020 | Number | 4 Ward Committee meetings hosted by 30 June 2020 | 1 Ward Committee Meeting by 31 December 2019 | 1 Ward Committee meeting held | 2 Ward Committee Meeting by 31 December 2019 | Achieved. 2 Ward Committee meetings held | N/A | N/A | N/A | 200000 | Equitable Share | MM-BUDG | Default | All Wards | Attendance Register | M | Manager Public Participation
[5 empty] | 9 | MM-09-19/20 | Review of Public Participation Strategy | Municipal Manager | Administration | Adoption of Reviewed public participation strategy by 30 June 2020 | Date | Adopted Reviewed Public participation strategy by 30 30 June 2020 | Appointment of the Service Provider 31 December 2019 | Not Achieved | SCM Processes/ Appointment of the Service Provider by 31 December 2019 | Not Achieved. | Delays in the processing of documentation to SCM. | To submit documents to commence the Bid specification stage in Q3. |  | 200000 | Equitable Share | MM-BUDG | Default | All Wards | Q1 - SCM Processes Q2-Appt Letter Q3 - Draft Strategy Q4 - Council Resolution | M | Manager Public Participation
[5 empty] | 10 | MM-10-19/20 | Development of Communication Strategy | Municipal Manager | Administration | Adoption of Communication Strategy by 30 June 2020 | Date | Adopted Communication Strategy by 30 June 2020 | Appointment of the Service Provider 31 December 2019 | Not Achieved | Appointment of the Service Provider 31 December 2019 | Not Achieved. | Delays in the processing of documentation to SCM. | To submit documents to commence the Bid specification stage in Q3. |  | 200000 | Equitable Share | MM-BUDG | Default | All Wards | Q1 - SCM Processes Q2-Appt Letter Q3 - Draft Strategy Q4 - Council Resolution | M | Manager Communication
[5 empty] | 11 | MM-11-19/20 | Mayoral slots | Municipal Manager | Administration | Number of Media slots conducted by 30June 2020 | Number | 20 Media Slots Conducted by 30 June 2020 | 5 Media slots by 31 December 2019 | Achieved | 10 Media slots by 31 December 2019 | Achieved. 23 media slots. | N/A | N/A | N/A | 200000 | Equitable Share | MM-BUDG | Default | all wards | Attendance Register | M | Manager Communication
|  |  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | 12 | MM-12-19/21 | Monitoring performance of effective enterprise risk management | Municipal Manager | Administration | Number of risk registers updated by 30 June 2020 | Number | 4 Risk registers by 30 June 2020 | 1 Risk registers updated by 31 December 2019 | Not Achieved | 2 Risk registers updated by 31 December 2019 | Not Achieved | Risk Assessment done by KZN Treasury. Risk registers not yet approved. | There were challenges with Risk Assessments workshop, it was initially planned for 18 July 2019 and 28 Nov 2019, but cancelled as Management had other commitments on that day. Proposed meeting to be held in Q3. |  | salaries | Equitable share | MM-BUDG | Default | All Wards | Risk registers | H | IDM Risk Officer
[5 empty] | 13 | MM-13-19/20 | Review performance of effective enterprise risk management | Municipal Manager | Administration | Number of ethics/Risk Committee meetings held by 30 June 2020 | Number | 4 Ethics/Risk Committee meetings held by 30 June 2020 | 1 Ethics/Risk Committee meeting held by 31 December 2019 | Not Achieved | 2 Ethics/Risk Committee meeting held by 31 December 2019 | Not achieved. 1 Special Ethics/ Risk Meeting held on 25 September 2019. | Due to staff protests the meeting was cancelled. | The meeting will take place in Q3. |  | salaries | Equitable share | MM-BUDG | Default | All Wards | Attendance risk registers | H | IDM Risk Officer
[5 empty] | 14 | MM-14-19/20 | Risk Management | Municipal Manager | Administration | Risk assessment process for the 2019/2020 finalised by 30 June 2020 | Date | Risk assessment process for the 2019/2020 finalised by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries / assistance from Provincial Treasury | Equitable share | MM-BUDG | Default | All Wards | Risk assessment | H | IDM Risk Officer
[5 empty] | 15 | MM-15-19/20 | Enterprise Risk Management Register | Municipal Manager | Administration | 2019/2020 Enterprise Risk Management Register submitted to council for approval by 31 December 2019 | Date | 2019/2020 Enterprise Risk Management Register submitted by 31 December 2019 | Submit the approved risk register to Heads of departments by 31 December 2019 | Not Achieved | Submit the approved risk register to Heads of departments by 31 December 2019 | Not achieved. | Risk Assessment done by KZN Treasury, however the Report will be submitted in October 2019. Risk registers will be submitted to MANCO before end of October 2019. | There were challenges with Risk Assessments workshop, it was initially planned for 18 July 2019, but cancelled as Management had other commitments on that day. The meeting will be held in the second Quarter of 2019/20. Proposed date of meeting is 28 November 2019. |  | Salaries | Equitable share | MM-BUDG | Default | All Wards | Enterprise Risk Management Register | H | IDM Risk Officer
[5 empty] | 16 | MM-16-19/20 | Enterprise Risk Management Policy and Strategy | Municipal Manager | Administration | Reviewed Enterprise Risk Management Framework and Strategy by 30 June 2020 | Date | Reviewed Risk Mngt Framework and Strategy by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries / assistance from Provincial Treasury | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | IDM Risk Officer
[5 empty] | 17 | MM-17-19/20 | Conduct awareness on ERM processes and policies to all staff and Councillors | Municipal Manager | Administration | Number of Enterprise Risk Management workshops held by 30 June 2020 | Number | 2 Enterprise Risk Management workshops held by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Equitable share | MM-BUDG | Default | All Wards | Attendance risk registers | H | IDM Risk Officer
[5 empty] | 18 | MM-18-19/20 | Anti-Fraud and Corruption Strategy & Policy | Municipal Manager | Administration | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2020 | Date | Reviewed Anti-Fraud and Corruption Strategy & Policy by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Equitable share | MM-BUDG | Default | All Wards | Council Resolution | H | IDM Risk Officer
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 19 | MM-19-19/20 | Youth Welding Skills Programme | Municipal Manager | Administration | Number of Youth assisted by 31 March 2020 | Number | 60 Youth assisted by 31 March 2020 | N/A | N/A | 30 Youth assisted by 30 December 2019 | Achieved, 30 Youth asssisted by 31 December 2019 | N/A | N/A | N/A | 100000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 20 | MM-20-19/20 | Nongoma Royal Reed Dance | Municipal Manager | Administration | Number of Maidens participated in the Reed Dance by 30 September 2019 | Number | 500 Maidens participated by 30 September 2019 | N/A | N/A | 500 Maidens participated by 30 December 2019 | Achieved, 500 youth participated | N/A | N/A | N/A | 200000 | Equitable Share and Department of Arts and Culture | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 21 | MM-21-19/20 | Grade 9 and Grade 10 Career Guidance programme | Municipal Manager | Administration | Number of Career Guidance programmes held by 30 September 2019 | Number | 1 Career Guidance programme held by 30 September 2019 | N/A | N/A | 1 Grade 9 and 10 career guidance by 31 December 2019 | Achieved, 1career guidance done | N/A | N/A | N/A | 150000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 22 | MM-22-19/20 | Youth Arts and Culture Festival | Municipal Manager | Administration | Number of Arts and Culture Festival hosted by 31 December 2019 | Number | 1 Arts and Culture Festival hosted by 31 December 2019 | 1 Arts and Culture Festival hosted by 31 December 2019 | Achieved | 1 Arts and Culture Festival hosted by 31 December 2019 | Achieved, 2 Art and culture festival hosted | N/A | N/A | N/A | 450000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 23 | MM-23-19/20 | Examination Prayer Programme | Municipal Manager | Administration | Number of Examination Prayer Programme hosted by 31 December 2019 | Number | 1 Prayer Programme hosted by 31 December 2019 | 1 Prayer Programme hosted by 31 December 2019 | Achieved | 1 Prayer Programme hosted by 31 December 2019 | Achieved, 1 Examination Prayer hosted | N/A | N/A | N/A | 200000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 24 | MM-24-19/20 | Youth Sewing and Garmet making skills prgramme | Municipal Manager | Administration | Number of Youth trained by 30 June 2020 | Number | 80 Youth trained by 30 June 2020 | 40 Youth trained by 31 December 2019 | Not Achieved | 40 Youth trained by 31 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | Once adjustment budget has been concluded to include budget for the project in Q3. |  | 100000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 25 | MM-25-19/20 | Youth Farming Programme | Municipal Manager | Administration | Number of Youth trained by 31 March 2020 | Number | 80 Youth trained by 31 March 2020 | N/A | N/A | 40 Youth Trained by 30 December 2019 | Achieved, 40 Youth trained in youth farming programme | N/A | N/A | N/A | 120000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 26 | MM-26-19/20 | Right to Learn Campaign | Municipal Manager | Administration | Number of Right to Learn campaigns hosted by 30 June 2020 | Number | 1 Right to Learn campaigns hosted by 30 June2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 27 | MM-27-19/20 | Drivers Licence Programme Code 14 | Municipal Manager | Administration | Number of Youth Obtained Drivers Licence by 30 June 2020 | Number | 19 Youth Obtained Drivers Licence by 30 June2020 | Appointment of the Service Provider by 31 December 2019 | Not Achieved | Recruitment of 19 youth/ Appointment of the Service Provider by 31 December 2019 | Not Achieved. | Awaitng the SCM processes to conclude the appoint the service provider. | The Youth will be recruited in Q3 once the finalisation of the appointment has been concluded. |  | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 28 | MM-28-19/20 | Drivers Licence Programme Code 10 | Municipal Manager | Administration | Number of Youth trained by 30 June 2020 | Number | 38 Youth trained by 30 June 2020 | 19 Youth trained by 31 December 2019 | Achieved | 19 Youth trained by 31 December 2019 | Achieved, 19 youth trained | N/A | N/A | N/A | 180000 | Equitable share | COMM-BUDG | Default | All Wards | Attendance register |  | Manager Youth
[5 empty] | 29 | MM-29-19/20 | Youth Month Lecture June 16 | Municipal Manager | Administration | Number of Youth Participated by 30 June 2020 | Number | 1300 Youth participated by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
|  |  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | 30 | MM-30-19/20 | Youth Art Work Programme | Municipal Manager | Administration | Number of Youth assisted by 30 June 2020 | Number | 40 Youth asssisted by 30 June 2020 | 20 Youth assisted by 31 December 2019 | Achieved | 20 Youth assisted by 31 December 2019 | Achieved, 20 Youth assisted by 31 December 2019 | N/A | N/A | N/A | 80000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 31 | MM-31-19/20 | Youth Council Advisory Meeting | Municipal Manager | Administration | Number of Youth Council Advisory meetings held by 30 June 2020 | Number | 4 Youth Council Advisory meetings held by 30 June 2020 | Youth Council Advisory meeting held 31 December 2019 | Achieved | 2 Youth Council Advisory meeting held 31 December 2019 | Achieved, 2 meetings held | N/A | N/A | N/A | 80000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 32 | MM-32-19/20 | Job Readiness Programme | Municipal Manager | Administration | Number of Youth assisted by 30 June 2020 | Number | 200 Youth assisted by 30 June 2020 | 100 Youth assisted by 31 December 2019 | Not Achieved | 100 Youth assisted by 31 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | Once adjustment budget has been concluded to include budget for the project in Q3. | N/A | 100000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 33 | MM-33-19/20 | Youth Campaign on social ills | Municipal Manager | Administration | Number of Youth Campaigns hosted by 31 December 2019 | Number | 1 Youth Campaign hosted by by 31 December 2019 | 1 Youth Campaign hosted by 31 December 2019 | Achieved | 1 Youth Campaign hosted by 31 December 2019 | Achieved, 1 Youth campaign hosted | N/A | N/A | N/A | 200000 | equitable share | COMM-BUDG | Default | All Wards | Attendance Register | M | Manager Youth
[5 empty] | 34 | MM-34-19/20 | Youth in business seminar | Municipal Manager | Administration | Number of Youth trained by 30 June 2020 | Number | 20 Youth trained by 30 June2020 | 10 Youth trained 31 December 2019 | Not Achieved | 10 Youth trained 31 December 2019 | Not Achieved. | Due to the limitation of dates and clashing of meetings the targets was not met. | The project has been rescheduled to take place in Q3. |  | 45000 | tbc | COMM-BUDG | Default | All Wards | attendance register |  | Manager Youth
[5 empty] | 35 | MM-35-19/20 | Golden games training(football,duck walk,dress up race,pass the ball,500M brisk walk,800Mrun,100M run,200M run,400M run,400M relay,rugby ball throw,juskei,Ring the stick, Pass the ball and kick, ball relay, goal shooting,pegging washing pegs) | Municipal Manager | Administration | Number of events hosted by 31 March 2020 | Number | 2 Golden games hosted by 31 March 2020 | N/A | N/A | Golden games hosted by 30 December 2019 | Achieved, 1 golden games hosted | N/A | N/A | N/A | R150,000,00 | equitable share | MM-BUDG | Default | 05,02,01,13,15,17,19,12 ,08 and 11 | Attendance Register | L | Manager Youth
[5 empty] | 36 | MM-36-19/20 | Cricket coaching clinics and mini tournaments | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Cricket coaching clinics and mini tournaments hosted by 30 June 2020 | N/A | N/A | Cricket coaching clinics and mini tournaments hosted by 30 December 2019 | Achieved, 1 Cricket coaching clinics and mini tournaments done | N/A | N/A | N/A | R25,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
Good Governance and Public Participation | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 37 | MM-37-19/20 | Indigenous Coaching Clinics and mini tournaments (Umlabalaba,Induku,Kho-Kho,Juskei,Drie-Stokies,Incuva,Ingqathu,Amagenda) | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 Indigenous Coaching Clinics and mini tournaments (Umlabalaba,Induku,Kho-Kho,Juskei,Drie-Stokies,Incuva,Ingqathu,Amagenda) hosted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R70.000.00 | Equitable share | MM-BUDG | Default | 02,05,13,11,15,18,19 and 17 | Attendance Register | L | Manager Youth
[5 empty] | 38 | MM-38-19/20 | Tennis Long coaching clinics and mini tournaments | Municipal Manager | Administration | Number of events hosted by 31 March 2020 | Number | 2 Tennis Long coaching clinics and mini tournaments hosted by 31 March 2020 | N/A | N/A | 1 Tennis Long coaching clinics and mini tournaments hosted by 30 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | The project has been rescheduled to take place in the new financial year. | N/A | R30,000,00 | equitable share | MM-BUDG | Default | 5,13,15 | Attendance Register | L | Manager Youth
[5 empty] | 39 | MM-39-19/20 | Youth Run Competition | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 1 Youth Run Competition by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R50,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | M
[5 empty] | 40 | MM-40-19/20 | Municipal Sport Indaba | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 1 Number of events hosted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R150,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 41 | MM-41-19/20 | Football Coaching Clinics( females) | Municipal Manager | Administration | Number of events hosted by 31 March 2020 | Number | 2 Football Coaching Clinics( females) by 31 March 2020 | N/A | N/A | Football Coaching Clinics(females) by 30 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 05,03,01,08,11,12,15,13 and 06 | Attendance Register | L | Manager Youth
[5 empty] | 42 | MM-42-19/20 | Rugby Coaching Clinics | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 Rugby Coaching Clinics by 30 June 2020 | 1 Rugby Coaching Clinics hosted by 31 December 2019 | Not Achieved | 1 Rugby Coaching Clinics hosted by 31 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 05,04,06,02,11,13,19,15 and 17 | Attendance Register | L | Manager Youth
[5 empty] | 43 | MM-43-19/20 | Basket ball coaching clinics and mini tournaments | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 basket ball coaching clinics and mini tournaments hosted by 30 June 2020 | 1 basket ball coaching clinics and mini tournaments by 31 December 2019 | Not Achieved | 1 basket ball coaching clinics and mini tournaments by 31 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 05,06,04,02,08,11,13,15,19,17 | Attendance Register | L | Manager Youth
[5 empty] | 44 | MM-44-19/20 | Valleyball coaching clinics and mini tournaments | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Valleyball coaching clinics and mini tournaments hosted by 30 June 2020 | 1 Valleyball coaching clinics and mini tournaments by 31 December 2019 | Not Achieved | 1 Valleyball coaching clinics and mini tournaments by 31 December 2019 | Not Achieved. | Due to budget limitation the project was not met. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 19,02,14,13,01 | Attendance Register | L | Manager Youth
[5 empty] | 45 | MM-45-19/20 | Swimming coaching clinics and swimming gala | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 swimming coaching clinics and swimming gala hosted by 30 June 2020 | N/A | N/A | 1 Swimming coaching clinics and swimming gala hosted by 30 December 2019 | Not Achieved. | The target has not been met due to the clashing of dates with other events. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 01,06,08,03,11,02,13,14,19,18,12 | Attendance Register | L | Manager Youth
[5 empty] | 46 | MM-46-19/20 | Karate Coaching Clinics and tournaments | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Karate Coaching Clinics and tournaments hosted by 30 June 2020 | N/A | N/A | 1 Karate Coaching Clinics and tournaments hosted by 30 December 2019 | Not Achieved. | The target has not been met due to the clashing of dates with other events. | Due to budget constrain tournament will be done after budget adjustment | N/A | R30,000,00 | Equitable share | MM-BUDG | Default | 01,05,06,08,11,13,15,19,16 | Attendance Register | L | Manager Youth
[5 empty] | 47 | MM-47-19/20 | Dance Coaching Clinics and competition | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Dance Coaching Clinics and competition hosted by 30 June 2020 | N/A | N/A | Dance Coaching Clinics and competition hosted by December 2019 | Not Achieved. | The target has not been met due to the clashing of dates with other events. | Due to budget constrain tournament will be done after budget adjustment | N/A | R30,000,00 | Equitable share | MM-BUDG | Default | 1 | Attendance Register | L | Manager Youth
|  |  |  | To implement and maintain compliant, effective and efficient enterprise risk management systems and processes. | 48 | MM-48-19/20 | Ndwedwe Traditional Rural Horse Riding Local Selection | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 1 Ndwedwe Traditional Rural Horse Riding local selection by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R150,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 49 | MM-49-19/20 | Netball coaching clinics and competition | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Netball coaching clinics and competition hosted by 30 June 2020 | 1 Netball coaching clinics and competition hosted by 31 December 2019 | Not Achieved | 1 Netball coaching clinics and competition hosted by 31 December 2019 | Not Achieved. | Budget constrain. The project will be held in the new financial year. | N/A | N/A | R30,000,00 | Equitable share | MM-BUDG | Default | 04,05,06,02,08,01,11,13,14,15.19,16 | Attendance Register | L | Manager Youth
[5 empty] | 50 | MM-50-19/20 | Aerobics coaching clinics and marathon | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Aerobics coaching clinics and marathon hosted by 30 June 2020 | N/A | N/A | 1 Aerobics coaching clinics and marathon by 30 December 2019 | Achieved, 1 Aerobics coaching clinics done | N/A | N/A | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | 12,13,15,18,19 | Attendance Register | L | Manager Youth
[5 empty] | 51 | MM-51-19/20 | Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2019 | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2019 | Not Achieved | 1 Salga Games (males and females football,netball males and females,cricket,tennis,indigenous games,athletics,boxing,karate,swimming,rugby,basketball,valleyball,dance hosted by 31 December 2019 | Not Achieved. | The Games was rescheduled to Q3 due to other games held. | To be done in Q3 | N/A | R900,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | M | Manager Youth
[5 empty] | 52 | MM-52-19/20 | Mayoral Sports Development Cup Tournament | Municipal Manager | Administration | Number of events hosted by 30 September 2019 | Number | 1 Mayoral Cup hosted by 30 September 2019 | N/A | N/A | 1 Mayoral Cup hosted by 30 December 2019 | Not Achieved. | The Games was rescheduled to Q3 due to other games held. | To be done in Q3 | N/A | 200000 | Equitable Share | MM-BUDG | Default | all wards | Attendance Register | M | Manager Youth
[5 empty] | 53 | MM-53-19/20 | Women in Sport Symposium and sport day | Municipal Manager | Administration | Number of events hosted by 31 March 2020 | Number | 2 Women in Sport Symposium and sport day hostedby 31 March 2020 | N/A | N/A | 1 Women in Sport Symposium and sport day hosted by 30 Sep 2019 | Achieved, 1 women in sport done | N/A | N/A | N/A | R150,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 54 | MM-54-19/20 | Jonny Makhathini Marathon 5 km and 10 km | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 Jonny Makhathini Marathon hosted by 30 June 2020 | N/A | N/A | Jonny Makhathini Marathon 5 km and 10 km by September 2019 | Not Achieved. | Budget constrain. The project will be held in the new financial year. | The project has been rescheduled to take place in the new financial year. | N/A | R50,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
|  | 3: Human and Community Development 7: Governance and Policy | To ensure enhancement of good governance and public participation | 1.Compliance and good Governance 2. Conducting annual assesments for ward committes 3. Conducting of municipal employees for section 57 4. Conducting of municipal Municipal Izimbizo | 55 | MM-55-19/20 | Disability Sport Day | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 Disability Sport Day by 30 June 2020 | N/A | N/A | 1 Disability Sport Day by 30 September 2019 | Achieved, 1 disability sport day done | N/A | N/A | N/A | R50,000,00 | Equitable share | MM-BUDG | Default | 2,4,5,9,11,13,14,17,18,19 | Attendance Register | L | Manager Youth
[5 empty] | 56 | MM-56-19/20 | Capacity building and training for Sport Confederation Members | Municipal Manager | Administration | Number of training hosted by 30 June 2020 | Number | 1 Capacity Building training by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R200.000.00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 57 | MM-57-19/20 | ECD's sport day | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 2 ECD's sport day by 30 June 2020 | N/A | N/A | 1 ECD's sport day by 30 September 2019 | Not Achieved. | Budget constrain. The project will be held in the new financial year. | The project has been rescheduled to take place in the new financial year. | N/A | R20,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 58 | MM-58-19/20 | Ndwedwe SAFA Associations Awards | Municipal Manager | Administration | Number of events hosted by 30 October 2019 | Number | 1 Ndwedwe SAFA Awards by 30 October 2019 | 1 Ndwedwe SAFA Awards by 30 October 2019 | Not Achieved | 1 Ndwedwe SAFA Awards by 30 October 2019 | Not Achieved. | Budget constrain. The project will be held in the new financial year. | The project has been rescheduled to take place in the new financial year. | N/A | 70000 | Equitable share | MM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
[5 empty] | 59 | MM-59-19/20 | Hockey Development and tournament | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 3 Hockey Development and tournamentby 30 June 2020 | N/A | N/A | 1 Hockey Development and tournament by 30 September 2019 | Achieved, 1 Hockey development and tournament done | N/A | N/A | N/A | 30000 | Equitable share | MM-BUDG | Default | 09,19,17,16,18,15 | Attendance Register | L | Manager Youth
[5 empty] | 60 | MM-60-19/20 | Golf development | Municipal Manager | Administration | Number of eventss hosted by 30 June 2020 | Number | 1 Golf coaching and tournament by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R150,000,00 | Equitable share | MM-BUDG | Default | 1,3,8,12 | Attendance Register | L | Manager Youth
[5 empty] | 61 | MM-61-19/20 | Municipal Sport Award | Municipal Manager | Administration | Number of events hosted by 31 March 2020 | Number | 1 Municipal Sport Award by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R120,000,00 | Equitable share | MM-BUDG | Default | all wards | Attendance Register | L | Manager Youth
[5 empty] | 62 | MM-62-19/20 | Chess development and local tournament | Municipal Manager | Administration | Number of events hosted by 30 June 2020 | Number | 4 Chess development and local tournament hosted by 30 June 2020 | 1 Chess development and local tournament hosted by 31 December 2019 | Not Achieved | 2 Chess development and local tournament hosted by 31 December 2019 | Not Achieved. | Budget constrain. The project will be held in the new financial year. | The project has been rescheduled to take place in the new financial year. |  | R10,000,00 | Equitable share | MM-BUDG | Default | All Wards | Attendance Register | L | Manager Youth
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 18 | TS-18-19/20 | Construction of Technical Dept Offices | Technical Services | Administration | Construction completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Date | Construction completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Construction completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Achieved | Construction completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Not achieved: Construction items completed - Wall plastering, Parking, Building roof, floor tilling, plumbing | Not all construction items completed like fencing, electrification due to heavy rainfall took place | All outstanding activities to be completed Q3 2019-20 |  | 4800000 | Internal | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 34 | TS-34-19/20 | EPWP - Waste management | Technical Services | Administration | Number of work opportunities created by 30 September 2019 | Date | 75 EPWP work opportunities created by 30 September 2019 | N/A | N/A | 75 EPWP work opportunities created by 30 September 2019 | Achieved | N/A | N/A | N/A | 1348000 | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works
[5 empty] | 2 | COM-02-19/20 | Municipal Waste collection | Community and Social Services | Administration | Number of Municipal waste collections by 30 June 2020 | Number | 912 Municipal wate collections by 30 June 2020 | 228 collections done from all sites by 31 December 2019 | Achieved | 456 collections done from all sites by 31 December 2019 | Achieved, 456 waste collected | N/A | N/A | N/A | 900000 | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager:Community Services
Local Economic Development | A responsive & accountable, effective & efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 2 | EDP-02-19/20 | Ndwedwe Land Use Managament System | EDP | Administration | Adoptation of Final LUMS document by 30 June 2020 | Date | Adoption of Final LUMS document by 30 June 2020 | First Draft LUMS document produced by 31 December 2019 | Achieved | Appointment of service provider/ First Draft LUMS document produced by 31 December 2019 | Achieved. Appointment of service provider and first draft complete. | N/A | N/A | N/A | 200000 | Internal Funding | EDP-BUDG | Default | All wards | Final LUMS document | H | Director: EDP
[5 empty] | 8 | EDP-08-19/20 | Development of Housing Sector Plan | EDP | Administration | Adoption of Housing Sector Plan by 30 June 2020 | Date | Final Housing Sector Plan adopted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards | Delivery Notes | H | Director: EDP
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive & accountable, effective & efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 1 | CS-01- 19/20 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | Number of WSP training programmes implemented as per WSP by end of financial year by 30 June 2020 | Number | 8 WSP training programmes implemented as per WSP by 30 June 2020 | 2WSP training programmes implemented as per WSP by 31 December 2019 | Achieved | 0.50% of budget spent on WSP by 31 December 2019 | Achieved, 0,50% budget spent | N/A | N/A | N/A | 1000000 | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 2 | CS-02- 19/20 | Filling budgeted posts | Corporate Services | Administration | Number of Budgeted posts filled by 30 June 2020 | Number | 12 Budgeted posts be filled by 30 June 2020 | 2 Budgeted posts be filled by 31 December 2019 | Not achieved. 1 post advertised for OHS Officer. | 5 Budgeted posts be filled by 31 December 2019 | Not achieved. 3 Budgeted posts be filled and 1 advert by 31 December 2019 | Some positions were already advertised and due for shortlisting and interviews | To conduct Recruitment processes in the third quarter. | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Manager: Human Resource
[5 empty] | 6 | CS-11 19/20 | Implementation of Biometric Systerm Register | Corporate Services | Administration | Number of biometric systems register implemented by 30 June 2020 | Number | 12 x Biometric systerms reports presented by 30 June 2020 | 3x Biometric systerm reports presented by 31 December 2019 | Achieved | 6x Biometric system reports presented by 31 December 2019 | Achieved, 6 biometrics report presented | N/A | N/A | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Biometrics Reports | H | Manager: IT
Financial Viability and Management | A responsive & accountable, effective & efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management. To achieve a clean audit opinion | 2 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 71 MFMA Reports submitted on time by 30 June 2020 | Number | 12 MFMA Reports submitted at the end 30 June 2020 | 3 monthly reports submitted by 31 December 2019 | Achieved | 6 monthly reports submitted by 31 December 2019 | Achieved, 6 monthly reports submitted by 31 December 2019 | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 3 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 72 MFMA Reports sumbitted by 31 January 2020 | Number | 1 MFMA Reports submitted to Council by 31 Janaury 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 22 | F-19-19/22 | Maintain unqualified audit opinion | FINANCE | Administration | Maintain unqualified audit opinion by 31 December 2019 | AG Report | Unqualified audit report by the AG for 2018/2019 financial year by 31 December 2019 | Unqualified audit report by 31 December 2019 | Achieved | Submitted AFS/ Unqualified audit report by 31 December 2019 | Achieved, AFS submitted and unqualified audit was maintained | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | Unqualified report from AG | H | CFO

## TECHNICAL
DEPARTMENT: TECHNICAL SERVICES
DIRECTOR: MR.D.H.MZOLO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target | 2nd QUARTER TARGET End Dec 2019 | 2nd QUARTER ACTUAL End Dec 2019 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
KPI Ref. No
TOP LAYER SDBIP
DIRECTOR TECHNICAL SERVICES PERFORMANCE PLAN 2019-2020
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 1: Inclusive economic growth 4: Strategic Infrastructure | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of sustainable infrastructure in order to eradicate backlogs | 1 | TS-01-19/20 | Nambithane Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 December 2019 | Number | 5km construction to be completed by 31 December 2019 | 5km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 5km construction completed | 5km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | Achieved. 5km construction completed | N/A | N/A |  | 3500000 | MIG | TECH-BUDG | Default | 5 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 2 | TS-02-19/20 | KwaNovimba Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 December 2019 | Number | 3km contruction to be completed by 31 December 2019 | 3km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 3km construction completed | 3km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | Achieved. 3km construction completed | N/A | N/A |  | 2900000 | MIG | TECH-BUDG | Default | 18 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 3 | TS-03-19/20 | Chamani Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 December 2019 | Number | 1km construction to be completed by 31 December 2019 | 1km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | 1km construction completed | 1km construction to be completed (drainange systems, layer works and ancillary works) by 31 December 2019 | Achieved. 1km construction completed | N/A | N/A |  | 1000000 | MIG | TECH-BUDG | Default | 16 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 4 | TS-04-19/20 | Mwolokohlo to Sthupha Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 March 2020 | Number | 1,5km construction to be completed by 31 March 2020 | 0,5km construction to be completed (Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 0,5km construction completed | 0,5km construction to be completed (Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Achieved. 0,5km construction completed | N/A | N/A |  | 2800000 | MIG | TECH-BUDG | Default | 11 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 5 | TS-05-19/20 | Water Fall Sportfield | Technical Services | Administration | Construction to be completed - Earthworks, Buildings/change rooms, Fencing, Plumbing by 31 December 2019 | Date | Construction to be completed - Earthworks, Buildings/change rooms, Fencing and Plumbing by 31 December 2019 | Construction to be completed - Earthworks, Buildings/change rooms, Fencing and Plumbing by 31 December 2019 | Construction items completed - Earthworks, Buildings/change rooms, Fencing, Parking, Soccer pitch (land scaping) | Construction to be completed - Earthworks, Buildings/change rooms, Fencing and Plumbing by 31 December 2019 | Not achieved: Construction items completed - Earthworks, Buildings/change rooms, Fencing, Parking, Soccer pitch (land scaping) | Plumbing works not completed - Slow progress by the Contractor | Close monitoring and Contractor to be put under terms and conditions in terms of GCC (General Conditions of Conttract) |  | 3000000 | MIG | TECH-BUDG | Default | 3 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 6 | TS-06-19/20 | Ethafeni Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 March 2020 | Number | 1,2km construction to be completed by 31 March 2020 | 0,2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 1,2km construction completed | 1,2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Achieved. 1,2km construction completed | N/A | N/A |  | 1200000 | MIG | TECH-BUDG | Default | 8 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 7 | TS-07-19/20 | Zesuliwe Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 March 2020 | Number | 7,46km construction to be completed by 31 March 2020 | 2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | 2km construction completed | 2km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Not Achieved. | 2 km construction not complete due to slow progress of the contractor. | Close monitoring and Contractor to be put under terms and conditions in terms of GCC (General Conditions of Conttract) |  | 4000000 | MIG | TECH-BUDG | Default | 7 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 8 | TS-08-19/20 | Gudlintaba Access Road | Technical Services | Administration | Number of kilometers to be completed by 31 March 2020 | Number | 1,75km construction to be completed by 31 March 2020 | 0,5km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | 0,5km construction to be completed ( Site establishment, drainange systems, layer works and ancillary works) by 31 December 2019 | Not achieved: Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 2000000 | MIG | TECH-BUDG | Default | 17 | Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 9 | TS-09-19/20 | eMona Community Hall | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | N/A | N/A | N/A |  | 2159000 | MIG | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 10 | TS-10-19/20 | Siyathokoza Hall & Creche | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | N/A | N/A | N/A |  | 3250000 | MIG | TECH-BUDG | Default | 14 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 11 | TS-11-19/20 | Nondwengu Hall & Creche Ward 10 | Technical Services | Administration | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | Date | Construction to be completed - (Building walls, roofing, plumbing and fencing) by 30 September 2019 | N/A | N/A | N/A | N/A | N/A | N/A |  | 1000000 | MIG | TECH-BUDG | Default | 10 | Completion Certificate | H | Manager: PMU
[5 empty] | 12 | TS-12-19/20 | Mangangeni CDC | Technical Services | Administration | Construction to be completed - ( commisioning, Operating documentation/as builts) by 31 March 2020 | Date | Construction to be completed - ( commisioning, Operating documentation/as builts) by 31 March 2020 | Activities of construction - ( Site establishement, Clear and grub and structure formation) by 31 December 2019 | Not commenced with construction - Contractor appointed, construction to start January 2020 Q3 2019-20 | Activities of construction - ( Site establishement, Clear and grub and structure formation) by 31 December 2019 | Not achieved: Not commenced with construction - Contractor appointed, construction to start January 2020 Q3 2019-20 | Delay on SCM process of appointing the Contractor | Contractor appointed and construction scheduled to commence January 2020 Q3 2019-20 |  | 1500000 | MIG | TECH-BUDG | Default | 19 | Advert, Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 13 | TS-13-19/20 | Mandlakazi Sport Field | Technical Services | Administration | Construction to be completed (Soccer field, Combo court, Parking area, Buildings/change rooams, Plumbing) by 31 March 2020 | Date | Construction to be completed (Parking area, Buildings /change rooms and Plumbing) by 31 March 2020 | Construction to be completed -(Site establishment, Soccer field, Combo court, Parking area and Buildings/change rooms) by 30 December 2019 | Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Construction to be completed -(Site establishment, Soccer field, Combo court, Parking area and Buildings/change rooms) by 30 December 2019 | Not achieved: Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 2500000 | MIG | TECH-BUDG | Default | 4 | Advert, Appointment Letter,Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 14 | TS-14-19/20 | Electrification Onyazini & Khenana/Nsuze Ward 2 | Technical Services | Administration | Construction to be completed - (120 households connected ) by 31 March 2020 | Number of households connected | Construction to be completed - (Commisioning and Energizing by Eskom of 120 households by 31 March 2020 | N/A | N/A | Construction to be completed - (Installation of reticulation networks) by 30 September 2019 | Achieved.Construction completed and energizing completed through Eskom | N/A | N/A |  | 2370833.61 | Internal | TECH-BUDG | Default | 2 | Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 15 | TS-15-19/20 | Electrification Mcathu Ward 8 | Technical Services | Administration | Construction to be completed - (157 households connected ) by 30 September 2019 | Number of households connected | Construction to be completed - (157 households connected ) by 30 September 2019 | N/A | N/A | N/A | N/A | N/A | N/A |  | 1000000 | INEP | TECH-BUDG | Default | 8 | Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 16 | TS-16-19/20 | Type 2 Electrification Ward 1-19 | Technical Services | Administration | Construction to be completed - (330 households connected) by 30 June 2020 | Number of households connected | Construction - to be completed -(330 households connected, installation of electricity reticulation and energizing) by 30 June 2020 | Design Report & Bid Specification document by 31 December 2019 | Bid Specification document complete & advertised | Design Report & Bid Specification document by 31 December 2019 | Achieved.Bid Specification document complete & advertised | N/A | N/A |  | 4000000 | Internal | TECH-BUDG | Default | 2 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Director: Technical Services
[5 empty] | 17 | TS-17-19/20 | Nhlangwini Sports field | Technical Services | Administration | Construction to be completed - (Soccer pitch/field and Plumbing) by 31 March 2020 | Date | Construction to be completed - (Soccer field and Plumbing) by 31 March 2020 | Construction to be completed - (Site establishment, Soccer pitch/field) by 31 December 2019 | Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Construction to be completed - (Site establishment, Soccer pitch/field) by 31 December 2019 | Not achieved: Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 1900000 | Internal | TECH-BUDG | Default | 1 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 18 | TS-18-19/20 | Construction of Technical Dept Offices | Technical Services | Administration | Construction to be completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Date | Construction to be completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Construction to be completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Construction items completed - Wall plastering, Parking, Building roof, floor tilling, plumbing | Construction to be completed - (Parking,electrification, fencing, commisioning, operating documentation/as built) by 31 December 2019 | Not achieved: Construction items completed - Wall plastering, Parking, Building roof, floor tilling, plumbing | Not all construction items completed like fencing, electrification due to heavy rainfall took place | All outstanding activities to be completed Q3 2019-20 |  | 4800000 | Internal | TECH-BUDG | Default | 15 | Technical Progress Report & Completion Certificate | H | Manager: PMU
[5 empty] | 19 | TS-19-19/20 | Augmentation of Water Supply for Ndwedwe Main Office | Technical Services | Administration | Augmentation to be completed (Supply and installtion of JOJO tanks) by 31 December 2019 | Date | Augmentation to be completed (Supply and installtion of JOJO tanks) by 31 December 2019 | Augmentation to be completed (Supply and installtion of JOJO tanks) by 31 December 2019 | Water augmentation completed - Supply & installation of JOJO Tanks & Booster pumps | Service provider appointed/ Augmentation to be completed (Supply and installtion of JOJO tanks) by 31 December 2019 | Achieved.Water augmentation completed - Supply & installation of JOJO Tanks & Booster pumps | N/A | N/A |  | 200000 | Internal | TECH-BUDG | Default | 15 | Appointment letter and Technical Progress Report | H | Manager: Public Works
[5 empty] | 20 | TS-20-19/20 | Local Sports Facilities: Grass Cutting | Technical Services | Administration | Number of sports grounds to be completed by 30 June 2020 | Number | 40 Sport grounds to be completed by 30 June 2020 | 10 sport grounds to be completed by 31 December 2019 | 10 sport grounds maintanined | 10 sport grounds to be completed by 31 December 2019 | Achieved.10 sport grounds maintanined | N/A | N/A |  | 700000 | Internal | TECH-BUDG | Default | All | Inspection Report | M | Manager: Public Works
[5 empty] | 21 | TS-21-19/20 | Rehabilitation of Mthebeni road | Technical Services | Administration | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Date | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Mthebeni Road completed - Earthworks, concrete section and drainage system | Service Provider appointed/ Mthebeni Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Achieved.Mthebeni Road completed - Earthworks, concrete section and drainage system | N/A | N/A |  | 600000 | Internal | TECH-BUDG | Default | 14 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 22 | TS-22-19/20 | Rehabilitation of Febe road | Technical Services | Administration | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Date | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Febe Road completed - Earthworks, concrete section and drainage system | Service provider apointed/ Febe Road to be completed (earthworks, concrete section and drainage system) by 31 December 2019 | Achieved.Febe Road completed - Earthworks, concrete section and drainage system | N/A | N/A |  | 900000 | Internal | TECH-BUDG | Default | 14 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 23 | TS-23-19/20 | Johnny Makhathini Hall Renovations | Technical Services | Administration | Jonny Makhathini Hall renovations completed( painting, tiling and carpentry) by 31 March 2020 | Date | Jonny Makhathini Hall renovations completed( painting, tiling and carpentry) by 31 March 2020 | Appointment of Service provider by 31 December 2019 | Not commenced with renovations - Contractor appointment to be done - Bid Evaluation to be done | Project advertised/ Appointment of Service provider by 31 December 2019 | Not achieved: Not commenced with renovations - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 1200000 | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 24 | TS-24-19/20 | Ndwedwe Public Library Renovations | Technical Services | Administration | Ndwedwe Public Library renovations completed( painting, tiling and carpentry) by 31 March 2020 | Date | Ndwedwe Public Library renovations completed( painting, tiling and carpentry) by 31 March 2020 | Appointment of contractor by 30 December 2019 | Ndwedwe Public Library renovations completed | Ndwedwe Public Library renovations complete by 30 December 2019 | Ndwedwe Public Library renovations completed | N/A | N/A |  | 400000 | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 25 | TS-25-19/20 | Mary-Grey Sport Centre Phase 2 | Technical Services | Administration | Mary Grey construction (additional activities paving) to be completed by 31 March 2020 | Date | Construction to be completed - ( additional activities paving) by 31 March 2020 | Construction of security guardroom to be completed - by 30 December 2019 | Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Appointment of service provider/Construction of security guardroom to be completed - by 30 December 2019 | Not achieved: Not commenced with contruction - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 600000 | Internal | TECH-BUDG | Default | 7 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 26 | TS-26-19/20 | Wewe hall | Technical Services | Administration | Wewe Hall renovations completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Date | Wewe Hall renovations completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Appoitnment of service provider by 31 December 2019 | Contractor appointed | Project advertised/ Appoitnment of service provider by 31 December 2019 | Achieved.Contractor appointed | N/A | N/A |  | 200000 | Internal | TECH-BUDG | Default | 2 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 27 | TS-27-19/20 | Noorsburg hall | Technical Services | Administration | Noorsburg Hall renovations completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Date | Noorsburg Hall renovations completed( painting, tiling, plumbing and carpentry) by 31 March 2020 | Appointment of Service provider by 31 December 2019 | Contractor appointed | Project advertised/ Appointment of Service provider by 31 December 2019 | Achieved.Contractor appointed | N/A | N/A |  | 200000 | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 28 | TS-28-19/20 | Esigedleni hall | Technical Services | Administration | Esigedleni Hall renovations to be completed ( painting, tiling, plumbing and carpentry)by 31 March 2020 | Date | Esigedleni Hall renovations to be completed ( painting, tiling, plumbing and carpentry) by 31 March 2020 | Appointment of Service provider by 31 December 2019 | Renovation completed | Esigedleni Hall renovations complete by 30 December 2019 | Achieved.Renovation completed | N/A | N/A |  | 200000 | Internal | TECH-BUDG | Default | 19 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 29 | TS-29-19/20 | Thafamasi hall | Technical Services | Administration | Thafamasi Hall renovations to be completed ( painting, tiling, plumbing and carpentry)by 31 March 2020 | Date | Thafamasi Hall renovations to be completed ( painting, tiling, plumbing and carpentry)by 31 March 2020 | Appoitnment of service provider by 31 December 2019 | Renovation completed | Thafamasi Hall renovations complete by 30 December 2019 | Achieved.Renovation completed | N/A | N/A |  | 200000 | Internal | TECH-BUDG | Default | 18 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 30 | TS-30-19/20 | Rehabilitation of Noorsburg Access Road | Technical Services | Administration | Noorsburg access road rehabilitation to be completed by 30 June 2020 | Date | Noorsburg access road to be completed (drainage system and gabions completed) by 30 June 2020 | Appoitnment of service provider by 31 December 2019 | Not commenced with rehabilitations - Contractor appointment to be done - Bid Evaluation to be done | Bid specification, advertisement and Appoitnment of service provider by 31 December 2019 | Not achieved: Not commenced with rehabilitations. | Contractor appointment to be done. | Bid Evaluation Committee to speed up the process of contractor appointment |  | 800000 | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 31 | TS-31-19/20 | Rehabilitation of Nhlangano Access Road Ward 4 | Technical Services | Administration | Nhlangano access road to be completed (drainage system and gabions completed) by 30 June 2020 | Date | Nhlangano access road to be completed (drainage system and gabions completed) by 30 June 2020 | Appoitnment of service provider by 31 December 2019 | Not commenced with rehabilitations - Contractor appointment to be done - Bid Evaluation to be done | Nhlangano Access road rehabilitation completed by 30 December 2019 | Not achieved: Not commenced with rehabilitations - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 600000 | Internal | TECH-BUDG | Default | 4 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 32 | TS-32-19/20 | Rehabilitation of Mthukutheli Access Road Ward 15 | Technical Services | Administration | Mthukutheli access road to be completed (concrete completed) by 30 June 2020 | Date | Mthukutheli access road to be completed (concrete completed) by 30 June 2020 | Appoitnment of service provider by 31 December 2019 | Not commenced with rehabilitations - Contractor appointment to be done - Bid Evaluation to be done | Mzokhulayo (Cemetry Road) Access road rehabilitation complete by 30 December 2019 | Not achieved: Not commenced with rehabilitations - Contractor appointment to be done - Bid Evaluation to be done | Delay on SCM process of appointing the Contractor | Bid Evaluation Committee to speed up the process of contractor appointment |  | 600000 | Internal | TECH-BUDG | Default | 15 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | H | Manager: Public Works
[5 empty] | 33 | TS-33-19/20 | Bhamshela Thusong centre renovations | Technical Services | Administration | External Bhamshela Thusong center renovations to be completed (painting and landscaping) by 31 March 2020 | Date | External Bhamshela Thusong center renovations to be completed (painting and landscaping)by 31 March 2020 | Internal renovations to be completed (painting and carpentry) by 31 December 2019 | Renovation items completed - Painting, floor tiles & carpentry | Appointment of service provider/ Internal renovations to be completed (painting and carpentry) by 31 December 2019 | Achieved.Renovation items completed - Painting, floor tiles & carpentry | N/A | N/A |  | R600 000, 00 | Internal | TECH-BUDG | Default | 6 | Advert, Appointment Letter, Technical Progress Report & Completion Certificate | M | Manager: Public Works
[5 empty] | 34 | TS-34-19/20 | EPWP - Waste management | Technical Services | Administration | Number of work opportunities created by 30 September 2019 | Date | 75 EPWP work opportunities created by 30 September 2019 | N/A | N/A | N/A | N/A | N/A | N/A |  | 1348000 | Internal | TECH-BUDG | Default | All wards | Appointment letters of the Participants | H | Manager: Public Works

## FINANCE
DEPARTMENT: FINANCE
Mr S.G. MAJOLA
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target | 2nd QUARTER TARGET End Dec 2018 | 2nd QUARTER ACTUAL End Dec 2018 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
TOP LAYER SDBIP
DIRECTOR FINANCE PERFORMANCE PLAN 2019-2020
Financial Viability and Management | A responsive, accountable, effective and efficient local government system | Governance and Policy | To ensure an effective advisory role to management and council | Improvement of Cashflow Liquidity & Promotion of sound financial management | 1 | F-01-19/20 | Transactional mSCOA Reports | FINANCE | Administration | Number of transactional Mscoa reports to Finance Portfolio and Council for 2019 /2020 by 30 June 2020 | Number | 12 transactional Mscoa Reports by 30 June 2020 | 3 transactional Mscoa Report by 31 December 2019 | Achieved | 6 transactional Mscoa Report by 31 December 2019 | Achieved | N/A | N/A | N/A | R400,000,00 | Municipality | FIN-BUDG | Default | N/A | 12 Reports | H | CFO
[5 empty] | 2 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 71 MFMA Reports submitted on time by 30 June 2020 | Number | 12 MFMA Reports submitted at the end 30 June 2020 | 3 monthly reports submitted by 31 December 2019 | Achieved | 6 monthly reports submitted by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 3 | F-02-19/20 | Financial Reporting | FINANCE | Administration | Number of Section 72 MFMA Reports sumbitted by 31 January 2020 | Number | 1 MFMA Reports submitted to Council by 31 Janaury 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | CFO
[5 empty] | 4 | F-04-19/20 | Adjusted Budget for 2019/2020 | FINANCE | Administration | Approved Adjusted Budget adopted by the Council by 29 February 2020 | Date | Adopted Adjusted Budget by 29 February 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | 5 | F-05-19/20 | Budget for 2020/ 2021 | FINANCE | Administration | Approved Final Budget adopted by the Council by 31 May 2020 | Date | Adopted 2020/2021 Budget by the Council as at 31 May 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Budget
[5 empty] | 6 | F-06-19/20 | Revenue Enhancement Strategy | FINANCE | Administration | Council adopted Revenue Enhancement Strategy by 30 June 2020 | Date | Council approved Revenue Enhancement Strategy by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Finance
[5 empty] | 7 | F-07-19/20 | Collection of Revenue | FINANCE | Administration | Percentage of revenue collected by 30 June 2020 (norm 95% ccording to circular 81) | Percentage | 70% of collected Revenue by 30 June 2020 | 15% of Revenue collected by 31 December 2019 | Not Achieved | 25% of Revenue collected by 31 December 2019 | Not achieved. | One of the reasons were due to the non -payment of rental for premises. | The municipality is in the process of developing a Revenue enhancement strategy. The service provider has been appointed. | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Revenue Reports | H | Mananger: Finance
[5 empty] | 8 | F-08-19/20 | Finances Policies (SCM,Tarrif, Credit Control Policy, S and T, Overtime Policy, Banking and investment, Budget, Indigent, Fixed Assets, Rates, Virement and Disposal) | FINANCE | Administration | Num ber. of Finance Policies developed and reviewed by 30 June 2020 | Number | 11 Policies Adopted by Council by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | CFO
[5 empty] | 9 | F-09-19/20 | General Valuation Roll | FINANCE | Administration | Adopted General Valuation Roll done by 30 June 2020 | Date | Adopted General Valuation Roll Report by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R200,000,00 | N/A | FIN-BUDG | Default | N/A | Council Resolutions | H | Mananger: Finance
[5 empty] | 10 | F-10-19/20 | Screening of State Employees from SCM Database | FINANCE | Administration | Number of reports generated for each quarter by 30 June 2020 | Date | 4 Quarterly reports generated by 30 June 2020 | 1 quarterly reports generated by 31 December 2019 | Achieved | 2 quarterly reports generated by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | 11 | F-11-19/20 | Appointment of Local Service Providers | FINANCE | Administration | Reports on appointed local service providers submitted to Council Portfolio committee by 30 June 2020 | Date | 4 Quarterly reports submitted to Council Portfolio committee by 30 June 2020 | 1 quarterly report submitted to Council Portfolio committee by 31 December 2019 | Achieved | 2 quarterly report submitted to Council Portfolio committee by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 4 Reports | H | Mananger: SCM
[5 empty] | 12 | F-12-19/20 | Governance Reports ( Debtors Reconciliation Book) | FINANCE | Administration | Number of debtors reconciliation by 30 June 2020 | Number | 12 debtors reconciliation reports submitted by 30 June 2020 | 3 Monthly Reports by 31 December 2019 | Achieved | 6 Monthly Reports by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 13 | F-13-19/20 | Property Rates Reconciliation | FINANCE | Administration | Number of Property rates reconciliations by 30 June 2020 | Number | 12 Property Rates Reconciliations by 30 June 2020 | 3 Monthly Reports by 31 December 2019 | Achieved | 6 Monthly Reports by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Reports | H | Mananger: Finance
[5 empty] | 14 | F-14-19/20 | Bank Reconciliation | FINANCE | Administration | Number of Bank Reconciliation Report by 30 June 2020 | Number | 12 Bank Reconciliation reports by June 2020 | 3 Monthly Reports by 31 December 2019 | Achieved | 6 Monthly Reports by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 15 | F-15-19/20 | Investments | FINANCE | Administration | Number of monthly investments reports by 30 June 2020 | Number | 12 Monthly Investments reports by 30 June 2020 | 3 Monthly Reports by 31 December 2019 | Achieved | 6 Monthly Reports by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Reports | H | Mananger: Finance
[5 empty] | 16 | F-16-19/20 | Grant Register | FINANCE | Administration | Number of accurate grant register by 30 June 2020 | Number | 12 monthly grant registers by 30 June 2020 | 3 Monthly registers by 31 December 2019 | Achieved | 6 Monthly Reports by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | 12 Monthly Registers | H | Mananger: Finance
[5 empty] | 17 | F-17-19/20 | Creditors Payment | FINANCE | Administration | Number of days from submission by 30 June 2020 | Number | 30 Days from submission by 30 June 2020 | Payment of Invoice 30 days from submission by 31 December 2019 | Achieved | Payment of Invoice 30 days from submission by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Age analysis Reports | H | Mananger: Finance
[5 empty] | 18 | F-18-19/20 | Third Party Payments | FINANCE | Administration | Number of Third Party Payments produced by 30 June 2020 | Number | Last day of the month for 3rd parties by 30 June 2020 | Last day of each month for 3rd parties by 31 December 2019 | Achieved | Last day of each month for 3rd parties by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | N/A | FIN-BUDG | Default | N/A | Third party payment report | H | Mananger: Finance
[5 empty] | 19 | F-19-19/20 | MFMA Quarterly report 2018/2019 | FINANCE | Administration | Number of MFMA Section 52 d quarterly report prepared and submitted by 31 May 2020 | Number | 2 Quarterly report prepared and submitted by 31 May 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R400,000,00 | N/A | FIN-BUDG | Default | N/A | Financial statement report | H | CFO
[5 empty] | 20 | F-20-19/20 | SCM report | FINANCE | Administration | Number of Quarterly SCM reports submitted to Council by 30 June 2020 | Number | 4 Quarterly SCM report submitted to council by 30 June 2020 | 1 Quarterly SCM report submitted to Council by 31 December 2019 | Achieved | 2 Quarterly SCM report submitted to Council by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | 4 Monthly Reports | H | Manager: SCM
|  |  |  | To achieve a clean audit opinion | 21 | F-21-19/20 | Maintain unqualified audit opinion | FINANCE | Administration | Maintain unqualified audit opinion by 31 December 2019 | AG Report | Unqualified audit report by the AG for 2018/2019 financial year by 31 December 2019 | Unqualified audit report by 31 December 2019 | Achieved | Submitted AFS/ Unqualified audit report by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | Unqualified report from AG | H | CFO
|  |  |  | Cash flow management | 22 | F-22-19/20 | Liquidity Management (Pg 7 & 8 of MFMA circular 71) | FINANCE | Administration | Cash/Cost Coverage Ratio (Excluding Unspent Conditional Grants) ((Cash and Cash Equivalents - Unspent Conditional Grants - Overdraft) + Short Term Investment) / Monthly Fixed Operational Expenditure excluding (Depreciation, Amortisation, and Provision for Bad Debts, Impairment and Loss on Disposal of Assets)) (Norm: Range between 30 and 90 days with 90 days being ideal) by 30 June 2020 | Number | 60 days cash on hand by 30 June 2020 | 60 days cash on hand by 31 December 2019 | Achieved | 60 days cash on hand by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | Monthly Reports | H | CFO
|  |  |  | Debt management | 23 | F-23-19/20 | Debt coverage (Pg 9 of MFMA circular 71) | FINANCE | Administration | Debt Total Borrowings & Revenue (Debt (Short Term Borrowing + Bank Overdraft + Short Term Lease + Long Term Borrowing + Long Term Lease) / Total Operating Revenue - Operating Conditional Grant) by 30 June 2020 (Norm is 45% & below) | Percentage | 45% Debt Total Borrowings & Revenue by 30 June 2020 | 45% Debt Total Borrowings & Revenue by 31 December 2019 | Achieved | 45% Debt Total Borrowings & Revenue by 31 December 2019 | Achieved | N/A | N/A | N/A | Salaries | Equitable Share | FIN-BUDG | Default | N/A | Reports | H | CFO

## EPD
DEPARTMENT:ECONOMIC DEVELOPMENT AND PLANNING
DIRECTOR: MR S.D.G. KHUZWAYO
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies | KPI Ref No. | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target | 2nd QUARTER TARGET End Dec 2018 | 2nd QUARTER ACTUAL End Dec 2018 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
TOP LAYER SDBIP
DIRECTOR ECONOMIC DEVELOPMENT AND PLANNING PERFORMANCE PLAN 2019-2020
Local Economic Development | A responsive, accountable, effective and efficient local government system | 1:Inclusive economic growth; 3:Human & Community Development; 5: Spatial Equity | To develop a resilient economy that creates sustainable decent jobs and reduces poverty | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 1 | EDP-01-19/20 | Ndwedwe Town Development Project | EDP | Administration | Detail submission Pack to Surveyor General by 30 June 2020 | Date | Detail submission Pack to Surveyor General by 30 June 2020 | Beacon sectioned out and preparation of survey records by 31 December 2019 | Achieved. | Beacon sectioned out and preparation of survey records by 31 December 2019 | Achieved. | N/A | N/A | N/A | 2000000 | Internal Funding | EDP-BUDG | Default | Wards 15 | Proof of submission pack / Title Deed/ Certificate of Proclamation | H | Director: EDP
[5 empty] | 2 | EDP-02-19/20 | Ndwedwe Land Use Managament System | EDP | Administration | Adoption of Final LUMS document by 30 June 2020 | Date | Adoption of Final LUMS document by 30 June 2020 | First Draft LUMS document produced by 31 December 2019 | Achieved. | Appointment of service provider/ First Draft LUMS document produced by 31 December 2019 | Achieved. Appointment of service provider and first draft complete. | N/A | N/A | N/A | 200000 | Internal Funding | EDP-BUDG | Default | All wards | Final LUMS document | H | Director: EDP
[5 empty] | 3 | EDP-03-19/20 | Support 10 Block making training for Housing Projects at ward 10 | EDP | Administration | Support 10 Certified trained Block makers by 30 June 2020 | Number | Support 10 Certified trained Block makers by 30 June 2020 | 10000 blocks produced by 31 December 2019 | Not achieved. The municipality is struggling to get a accredited local service provider to conduct training. Appointment of a local SP in Q3. | Advertisement of service provider/ 10000 blocks produced by 31 December 2019 | Not achieved. | The municipality is struggling to get a accredited local service provider to conduct training. | To appoint a local service provider in Q3. | There is no local accredited service provider in Ndwedwe. | 200000 | Internal Funding | EDP-BUDG | Default | 10 | Registration Certificate Beneficiary signatures | M | Director: EDP
[5 empty] | 4 | EDP-04-19/20 | Makhuluseni Cooperative Support | EDP | Administration | Number of Cooperative assisted by 30 June 2020 | Number | 1 Functional community garden by 30 June 2020 | Seedlings, Seeds, Fencing procurement process done by 31 December 2019 | Achieved. | Bush clearing on site/ Seedlings, Seeds, Fencing procurement process done by 31 December 2019 | Achieved. | N/A | N/A | N/A | 200000 | Internal Funding | EDP-BUDG | Default | Ward 18 | proof of pipe instalation | p | Director: EDP
[5 empty] | 5 | EDP-05-19/20 | SMME Support | EDP | Administration | Number of SMMEs supported by 30 June 2020 | Number | 10 SMME's supported by 30 June 2020 | 3 SMME's supported by 31 December 2019 | Achieved. 3 SMME support. Achieved | 6 SMME's supported by 31 December 2019 | Achieved. 6 SMME support. Achieved | N/A | N/A | N/A | R300 000.00 | Internal Funding | EDP-BUDG | Default | All wards | Purchase Orders | M | Manager: LED
[5 empty] | 6 | EDP-06-19/20 | Cooperatives Support and SMME support with seeds and seedlings and information | EDP | Administration | Number of Cooperatives/SMMEs supported by 30 June 2020 | Number | 10 Cooperatives/SMMEs supported by 30 June 2020 | 3 cooperatives supported by 31 December 2019 | Achieved. 3 cooperatives supported. | 6 cooperatives supported by 31 December 2019 | Achieved. 6 cooperatives supported. | N/A | N/A | N/A | R200 000.00 | Internal Funding | EDP-BUDG | Default | TBC | Beneficiary signatures | M | Manager: LED
[5 empty] | 7 | EDP-07-19/20 | Housing Forum | EDP | Administration | Number of Housing Forums reports presented by 30 June 2020 | Number | 4 Housing Forums reports presented by 30 June 2020 | 1 Housing Forum report presented by 31 December 2019 | Not achieved | 2 Housing Forum report presented by 31 December 2019 | Not Achieved. 1 Housing Forum | Due to staff protests the Housing forum meeting was postponed. | The forum has been rescheduled to be held in Q3. |  | 5000 | Internal Funding | EDP-BUDG | Default | All wards | Attendace Register | M | Director: EDP
[5 empty] | 8 | EDP-08-19/20 | Development of Housing Sector Plan | EDP | Administration | Adoption of Housing Sector Plan by 30 June 2020 | Date | Final Housing Sector Plan adopted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R200 000.00 | Internal Funding | EDP-BUDG | Default | All wards | Delivery Notes | H | Director: EDP
[5 empty] | 9 | EDP-09-19/20 | LED Forum | EDP | Administration | Number of LED Forum meetings hosted annually by 30 June 2020 | Number | 4 LED Forums meetings to be hosted by 30 June 2020 | 1 LED Forum meetings hosted by 31 December 2019 | Not achieved. | 1 LED Forum to be meetings hosted by 31 December 2019 | Not achieved. | Due to staff protests the LED Forum scheduled for the 21 November 2019 was cancelled. | The forum has been rescheduled to be held in Q3. | Due to staff protests the LED Forum was cancelled. | 5000 | Internal Funding | EDP-BUDG | Default | All wards | Attendance Registers | M | Manager: LED
|  |  |  | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 10 | EDP-10-19/20 | Emerging Subcontractors support programme (capacity building for Grade 1-3) | EDP | Administration | Number of Emerging Contractors trained by 31 March 2020 | Number | 10 Emerging Contractors trained by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100000 | Internal Funding | EDP-BUDG | Default | TBC | Beneficiary signatures | M | Manager: LED
|  |  |  | To facilitate provision of infrastructure in a sustaianable manner | 11 | EDP-11-19/20 | Mini Factories Access Roads | EDP | Administration | 20 Metre Access Roads Constructed for Mini Factories by 30 June 2020 | Number | 20 Metre Access roads constructed by 30 June 2020 | Appointment of the Service provider to be done by 31 December 2019 | Not achieved. The appointment has not been finalised due to staff protests. The appointment will be finalised n Q3. | Advertisement of project/ Appointment of the Service provider done by 31 December 2019 | Achieved. Project has been advertised and appointment has been finalised. | N/A | N/A | N/A | R1,200 000,00 | Equitable share | EDP-BUDG | Default | 18 | Completion certificate | M | Director: EDP
[5 empty] | 12 | EDP-12-19/20 | Hosting of Local Agricultural Indaba | EDP | Administration | 1 Local Agricultural Indaba hosted by 30 September 2019 | Number | 1 Local Agricultural Indaba hosted by 30 September 2019 | N/A | N/A | 1 Local Agricultural Indaba hosted by 30 September 2019 | Achieved. 1 Local Agricultural Indaba held on 28 August 2019. | N/A | N/A | N/A | 50000 | Equitable share | EDP-BUDG | Default | Ward 15 | Attendance Registers | M | Director: EDP
|  |  |  | Facilitate the provision of support necessary for the development of SMME and cooperatives throughout the municipality | 13 | EDP-12-19/20 | Hosting of Ndwedwe Home coming Festival | EDP | Administration | 1 Ndwedwe Homecoming Festival by 31 December 2019 | Number | 1 Ndwedwe Homecoming Festival hosted by 31 December 2019 | 1 Ndwedwe Homecoming Festival hosted by 31 December 2019 | Achieved. 1 Ndwedwe Homecoming Festival held on 27 December 2019. | 1 Ndwedwe Homecoming Festival hosted by 31 December 2019 | Achieved. 1 Ndwedwe Homecoming Festival held on 27 December 2019. | N/A | N/A | N/A | 1000000 | Equitable share | EDP-BUDG | Default | ward 15 | Pictures and Report | M | Director: EDP
[5 empty] | 14 | EDP-12-19/20 | Maskandi Festival | EDP | Administration | 1 Maskandi Festival hosted by 30 September 2019 | Number | 1 Maskandi Festival hosted by 30 September 2019 | N/A | N/A | 1 Maskandi Festival hosted by 30 September 2019 | Achieved. 1 Maskandi Festival held on 26 October 2019 | N/A | N/A | Due to the delays in the SCM processes. The festival was rescheduled to be held on 26 October 2019 | 200000 | Equitable share | EDP-BUDG | Default | Ward 7 | Pictures and Report | M | Director: EDP

## Community Services
DEPARTMENT: COMMUNITY SERVICES
DIRECTOR: VACANT
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target | 2nd QUARTER TARGET End Dec 2019 | 2nd QUARTER ACTUAL End Dec 2019 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
KPI Ref. No.
TOP LAYER SDBIP
DIRECTOR (VACANT) COMMUNITY SERVICES PERFORMANCE PLAN 2019-2020
Infrastructure and Service Delivery | A responsive, accountable, effective and efficient local government system | 3: Human and Community Development 7: Governance and Policy | To facilitate provision of infrasture throughout the municipality | Facilitate the provision of infrastructure | 1 | COM-01-19/20 | Completion of refurbishments for Sonkombo and Anchor Departments Occupation | Community and Social Services | Administration | Number of operational anchor departments in the centre by 30 June 2020 | Number | 3 Anchor Departments operational in the Centre by 30 June 2020 | 1 Occupancy operational by 31 December 2019 | Not achieved. | Refurbishments completed and 1 Occupancy operational by 31 December 2019 | Achieved. Refurbishments have been completed but no occupancy as yet from the anchor departments. | It is solely dependent on the Department's discretion on how they deploy their resources. | Requests the assistance of the Dept of CoGTA, have been made and still awaiting the Depts responses. i.e. DHA, DSD, SASSA | Refurbishments completed hence departments need to consider moving. | 5000000 | Department of CoGTA | COMM-BUDG | Default | Ward 11 | Completion Certificate and Lease Agreements | M | Manager: Community Services
[5 empty] | 2 | COM-02-19/20 | Municipal Waste collection | Community and Social Services | Administration | Number of Municipal waste collections by 30 June 2020 | Number | 912 Municipal wate collections by 30 June 2020 | 228 collections done from all sites by 31 December 2019 | 228 | 456 collections done from all sites by 31 December 2019 | 456 collections done | N/A | N/A | N/A | 900000 | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager: Community Services
[5 empty] | 3 | COM-03-19/20 | Municipal Waste collection | Community and Social Services | Administration | Percentage of households earning less than R1100 per month with access to waste collection by 30 June 2020 | Percetage | 100% of Households access to waste collection by 30 June 2020 | 100% Households access to waste collection by 31 December 2019 | 100% | 100% Households access to waste collection by 31 December 2019 | 100% Households access to waste collection by 31 December 2019 | N/A | N/A | N/A |  | Equitable Share | COMM-BUDG | Default | All Wards | Signed Collection Forms | H | Manager: Community Services
[5 empty] | 4 | COM-04-19/20 | Establishment of the Buy-Back Centre | Community and Social Services | Administration | Newly established Buy-Back Centre constructed by 30 June 2020 | Date | Buy-Back Centre constructed (Activities of Construction completed - ( commisioning, Operating documentation/as builts)) by 30 June 2020 | Project Inception by 31 December 2019 | Not achieved. | Draft designs/ Project Inception by 31 December 2019 | Not achieved. Draft designs done but the project has not commenced as yet. | Land dispute has not been resolved between Ndwedwe and Ingonyama Trust Board | The Municipal Legal Department needs to expedite the process towards resolving the land issue. However, there have been several IGR discussions between Ndwedwe and ITB. To be resolved in Q3. |  | 2000000 | Equitable Share | COMM-BUDG | Default | Ward 15 | Completion Certificate | H | Manager: Community Services
[5 empty] | 5 | COM-05-19/20 | Disaster Awareness Campaigns | Community and Social Services | Administration | Number of Awareness campaigns by 30 June 2020 | Number | 4 Awareness campaigns by 30 June 2020 | 1 Awareness campaign by 31 December 2019 | Achieved. 1 Awareness held. | 2 Awareness campaign by 31 December 2019 | Achieved | N/A | N/A | N/A | 50000 | Equitable Share | COMM-BUDG | Default | Clustered wards | Attendance Register of Participants | H | Manager: Community Services
[5 empty] | 6 | COM-06-19/20 | Disaster Management Advisory Meetings | Community and Social Services | Administration | Number of quartely meetings to be held by 30 June 2020 | Number | 4 Quartely Meetings to be held by 30 June 2020 | 2nd Quarter Advisory Meeting held by 31 December 2019 | Achieved. 1 meeting held. | 2nd Quarter Advisory Meeting held by 31 December 2019 | Achieved | N/A | N/A | N/A | 50000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Manager: Community Services
[5 empty] | 7 | COM-07-19/20 | Local Disaster Management Workshops | Community and Social Services | Administration | Number of workshops held by 31 March 2020 |  | 2 Workshops held by 31 March 2020 | N/A | Achieved. 1 workshop held. | 1 Workshop held by 30 December 2019 | Achived | N/A | N/A | N/A | 50000 | Equitable Share | COMM-BUDG | Default | All Wards | Attendance Register of Participants | M | Manager: Community Services
[5 empty] | 8 | COM-08-19/20 | Review of the Disaster Management Sector Plan | Community and Social Services | Administration | Number of Reviewed Disaster Management Sector Plan by 30 June 2020 | Number | Disaster Management Sector Plan by 30 June 2020 | Establish processes for comprehensive disaster risk assessments by 31 December 2019 | Achieved. 1 disaster risk assessment completed. | Establish processes for comprehensive disaster risk assessments by 31 December 2019 | Achieved. 1 disaster risk assessment completed. | N/A | N/A | N/A | 200000 | Equitable Share | COMM-BUDG | Default | All Wards | Reviewed Disaster Management Plan | H | Manager: Community Services
[5 empty] | 9 | COM-09-19/20 | Operation sukuma sakhe local task team meetings | Community services | Administration | Number of meetings held by 30 June 2020 | Number | 8 meetings to be held by 30 June 2020 | 2meetings to be held 31 of 31 December 2019 | Achieved. 1 meetings held 06 November 2019 | 4 meetings to be held by 31 December 2019 | Achieved. 4 meetings held. 04 July 2019; 07 August 2019; 04 Septermber 2019 & 06 November 2019 | N/A | N/A | N/A | 60000 | Equitable share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | M | Manager Social Cohesion
[5 empty] | 10 | COM-10-19/20 | Local Aids Committee Meetings | Community services | Administration | Number of meetings held by 30 June 2020 | Number | 8 meetings to be held by 30 June 2020 | 2meetings held 31 December 2019 | Achieved. 2 meetings held. 16 August 2019 & 06 November 2019 | 4 meetings to be held by 31 December 2019 | Achieved. 2 meetings held. 16 August 2019 & 06 November 2019 | N/A | N/A | N/A | 50000 | Equitable share | COMM-BUDG | Default | All wards | Attendance register and Minutes of the meeting | M | Manager Social Cohesion
[5 empty] | 11 | COM-11-19/20 | Operation MBO | Community services | Administration | Number of meetings held by 30 June 2020 | Number | 4 meetings to be held by 30 June 2020 | 1meeting held 31 December 2019 | Achieved. 1 held on 27 November 2019 | 2 meetings to be held by 31 December 2019 | Not Achieved. 1 held on 27 November 2019 | The Sector departments did not respond effectively to all issues that were referred to them. | To enforce on time reporting, conduct follow ups and responses regarding all issues raised. | The meeting did not commence. | 140000 | Equitable share | COMM-BUDG | Default | tbc | Attendance Register | M | Manager Social Cohesion
[5 empty] | 12 | COM-12-19/20 | Men's Dialogue | Community services | Administration | Number of Dialogues held by 30 September 2019 | Number | 1 Dialogue to be held by 30 September 2019 | N/A | N/A | 1 Dialogue to be held by 30 September 2019 | Achieved. 1 Dialogue held in 30 July 2019 | N/A | N/A | N/A | 100000 | Equitable share | COMM-BUDG | Default |  | Attendance Register and Program | M | Manager Social Cohesion
[5 empty] | 13 | COM-13-19/20 | Womens day Commemoration | Community services | Administration | Number of Dialogues held by 30 September 2019 | Number | 1 Dialogue to be held by 30 September 2019 | N/A | N/A | 1 Dialogue commemoration to be held by 30 September 2019 | Achieved. 1 Dialogue held on 22 August 2019 | N/A | N/A | N/A | 200000 | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 14 | COM-14-19/20 | Operation Siyaya Emhlangeni | Community services | Administration | Number of eventss hosted by 30 September 2019 | Number | 1event to be hosted by 30 September 2019 | N/A | N/A | 1 event to be hosted by 30 September 2019 2019 | Not achieved. The District did not host the event due to budget constraints. | The event will be held in the next financial year. | N/A | N/A | 70000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 15 | COM-15-19/20 | Umkhosi Womhlanga | Community services | Administration | Number of Maidens participated by 30 September 2019 | Number | 490 Maidens Participated by 30 September 2019 | N/A | N/A | 490 Maidens Participated by 30 September 2019 | Achieved. Held on 6 -8 September 2019 | N/A | N/A | N/A | 295200 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 16 | COM-16-19/20 | Ndwedwe Safety Prayer | Community services | Administration | Number of Prayers hosted by 31 December 2019 | Number | 1 Prayer hosted by 31 December 2019 | 1 Prayer hosted by 31 December 2019 | Achieved. 1 Prayer held 31 December 2019 | 1 Prayer hosted by 31 December 2019 | Achieved. 1 Prayer held on 31 December 2019 | N/A | N/A | N/A | 60000 | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 17 | COM-17-19/20 | Child Protection Program | Community services | Administration | Number of Programs held by 30 June 2020 | Number | 1 Program held by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50000 | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 18 | COM-18-19/20 | Christmas Program for Senior Citizens | Community services | Administration | Number of Programs held by 31 December 2019 | Number | 1 Program held by 31 December 2019 | 1 Christmas program held by 31 December 2019 | Achieved. Held on 20 December 2019 | 1 Christmas program held by 31 December 2019 | Achieved. Held on 20 December 2019 | N/A | N/A | N/A | 80000 | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 19 | COM-19-19/20 | 16 Days of Activism | Community services | Administration | Number of meetings held by 31 December 2019 | Number | 2 meetings held by 31 December 2019 | 2 meeting held by 31 December 2019 | Achieved. 2 meetings held on 22 October & 3 December 2019 | 2 meeting held by 31 December 2019 | Achieved. 2 meetings held on 22 October & 3 December 2019 | N/A | N/A | N/A | 150000 | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 20 | COM-20-19/20 | Umkhosi kaBhacela | Community services | Administration | Number of Programs held by 31 March 2020 | Number | 1 Program to be held by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 300000 | Equitable share | COMM-BUDG | Default | 16,17,18,19 and 9 | Attendance Register | M | Manager Social Cohesion
[5 empty] | 21 | COM-21-19/20 | Moral Regeneration and Social Cohesion events | Community services | Administration | Number of eventss hosted by 30 June 2020 | Number | 1 event to be hosted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100000 | Equitable share | COMM-BUDG | Default |  | Attendance Register | M | Manager Social Cohesion
[5 empty] | 22 | COM-22-19/20 | Disability Safety awareness | Community services | Administration | Number of Awareness hosted by 31 December 2019 | Number | 1 Awareness to be hosted by 31 December 2019 | 1 Awareness to be held on 31 December 2019 | Not achieved. | 1 Awareness to be held by 31 December 2019 | Not Achieved. | Due to the staff protests the awareness program did not take place. | The program has been rescheduled to take place in Q3. |  | 100000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 23 | COM-23-19/20 | Disability Games | Community services | Administration | Number of Games hosted by 31 March 2020 | Number | 1 Game to be hosted by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 24 | COM-24-19/20 | Farm Workers Program | Community services | Administration | Number of Programs held by 30 June 2020 | Number | 1 Program to beheld by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100000 | Equitable share | COMM-BUDG | Default | 1,8,3 and 12 | Attendance Register | M | Manager Social Cohesion
[5 empty] | 25 | COM-25-19/20 | Ndwedwe Aids Day events | Community services | Administration | Number of eventss hosted by 31 December 2019 | Number | 1 event to be hosted by 31 December 2019 | 1 event to be hosted by 31 December 2019 | Achieved. 1 event held on 28 November 2019. | 1 event to be hosted by 31 December 2019 | Achieved. 1 event held on 28 November 2019. | N/A | N/A | N/A | 250000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 26 | COM-26-19/20 | Ndwedwe Social Ills Awareness | Community services | Administration | Number of awareness held by 30 June 2020 | Number | 2 Awareness to be held by 30 June 2020 | 1 Awareness to be held by 31 December 2019 | Not achieved. | 1 Awareness to be held by 31 December 2019 | Not achieved. | Due to the clashing of dates with the Mayoral Imbizo the awareness program was postponed. | The program has been rescheduled to take place in Q3. |  | 120000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 27 | COM-27-19/20 | Dress a child uniform campaign | Community services | Administration | Number of Campaigns held by 31 March 2020 | Number | 1 Campaign to be held by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 500000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 28 | COM-28-19/20 | Golden Games | Community services | Administration | Number of eventss hosted by 30 June 2020 | Number | 1 events to be hosted by 30 June 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 40000 | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 29 | COM-29-19/20 | Ndwedwe Ingoma Yesintu Program | Community services | Administration | Number of Programs held by 30 March 2020 | Number | 2 Program to be held by 31 March 2020 | 1 Program to be held by 31 December 2019 | Not achieved. | 1 Program to be held by 31 December 2019 | Not achieved. | Due to the staff protests the awareness program did not take place. | The program has been rescheduled to take place in Q3. |  | 80000 | Equitable share | COMM-BUDG | Default | All wards | Attendance register | M | Manager Social Cohesion
[5 empty] | 30 | COM-30-19/20 | Disability and Senior Citizens Forum | Community services | Administration | Number of Forums held by 30 June 2020 | Number | 4 Forums to be held by 30 June 2020 | 1 Forum by 31 December 2019 | Achieved | 2 Forums to be held by 31 December 2019 | Achieved. 2 meetings held meetings on Disability- 9 September 2019, Senior Citizens-19 September 2019 | N/A | N/A | N/A | 20000 | Equitable share | COMM-BUDG | Default | All wards | Attendance register | M | Manager Social Cohesion
[5 empty] | 31 | COM-31-19/20 | Civil Society Forum | Community services | Administration | Number of Forums held by 30 June 2020 | Number | 4 Forums to be held by 30 June 2020 | 1 Forum to be held by 31 December 2019 | Achieved. 1 Meeting held: 18 November 2019 | 2 Forums to be held by 31 December 2019 | Achieved. 2 Meetings. 29 July 2019 & 18 November 2019 | N/A | N/A | N/A | 200000 | Equitable share | COMM-BUDG | Default | All wards | attendance register | M | Manager Social Cohesion
[5 empty] | 32 | COM-32-19/20 | OSS Strategic Session | Community services | Administration | Number of sessions held by 30 September 2019 | Number | 1 Session to be held by 30 September 2019 | N/A | N/A | 1 Session to be held by 30 September 2019 | Not achieved. | Due to the unavailabilty of sectors departments the session was postponed. | The session has been rescheduled to take place in Q3. |  | 30000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion
[5 empty] | 33 | COM-33-19/20 | Women Empowerment Program | Community services | Administration | Number of Programs held by 30 March 2020 | Number | 1 Program to be held by 31 March 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50000 | Equitable share | COMM-BUDG | Default | All wards | Attendance Register | M | Manager Social Cohesion

## Corporate Services
DEPARTMENT: CORPORATE SERVICES
DIRECTOR: DR M.G. NTULI
National KPA | Outcome 9 | KZN PGDS | IDP Objective | Strategies |  | IDP/SDBIP REF No. | Projects | Function/Sub-Function | Regional Identifier | Key Performance Indicator | Unit Measure | Annual Target | 2nd QUARTER TARGET End Dec 2018 | 2nd QUARTER ACTUAL End Dec 2018 | BI-ANNUAL TARGET JULY - DEC | BI-ANNUAL ACTUAL JULY - DEC | REASON FOR VARIANCE / COMMENTS | MEASURES TAKEN TO IMPROVE PERFORMANCE/CORRECTIVE MEASURE | PMS COMMENTS | Total Budget for the Year | Source of Funding | MSC | Costing | Wards | Evidence | Weightings | Responsible Manager
KPI Ref No.
TOP LAYER SDBIP
DIRECTOR CORPORATE SERVICES PERFORMANCE PLAN 2019-2020
MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | A responsive, accountable, effective and efficient local government system | 2:Human Resource Development | To improve , attract, develop and retain human capital | Number of Organisational Structure Reviewed and Approved by the Council | 1 | CS-01 19/20 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | Number of WSP training programmes implemented as per WSP by end of financial year by 30 June 2020 | Number | 8 WSP training programmes implemented as per WSP by 30 June 2020 | 2WSP training programmes implemented as per WSP by 31 December 2019 | Achieved. 7 trainining implimented | 4WSP training programmes implemented as per WSP by 31 December 2019 | Achieved.10 WSP training programmes implemented as per WSP by 31 December 2019 | N/A | N/A | N/A | 1000000 | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 2 | CS-02 19/20 | Implement the Workplace Skills Plan (WSP) | Corporate Services | Administration | The percentage of a municipality’s budget actually spent on implementing its workplace skills plan by 30 June 2020 | Pertcentage | 1% of budget spent on the municipality WSP by 30 June 2020 | 0.50% of budget spent on WSP by 31 December 2019 | Achieved. | 0.50% of budget spent on WSP by 31 December 2019 | Achieved. | N/A | N/A | N/A |  | Municipality | DCS-BUDG | Default | N/A | Appointment Letter & Employment Contract | M | Manager: Human Resource
[5 empty] | 3 | CS-03 19/20 | Filling budgeted posts | Corporate Services | Administration | Number of Budgeted posts filled by 30 June 2020 | Number | 12 Budgeted posts be filled by 30 June 2020 | 2 Budgeted posts be filled by 31 December 2019 | Not achieved. 1 post advertised for OHS Officer. | 5 Budgeted posts be filled by 31 December 2019 | Not achieved. 3 Budgeted posts be filled and 1 advert by 31 December 2019 | Some positions were already advertised and due for shortlisting and interviews | To conduct Recruitment processes in the third quarter. | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Adverts, Appointment Letters | H | Manager: Human Resource
[5 empty] | 4 | CS-04 19/20 | Implement, test and maintain ICT system backups | Corporate Services | Administration | Number of successful backups conducted by 30 June 2020 | Number | 12 Backup reports submitted by 30 June 2020 | 3 Reports submitted by 31 December 2019 | Achieved.3 Reports submitted by 31 December 2019 | 6 Reports submitted by 31 December 2019 | Achieved.6 Reports submitted by 31 December 2019 | N/A | N/A | N/A | 300000 | Municipality | DCS-BUDG | Default | N/A | Backup Reports | M | Manager: IT
[5 empty] | 5 | CS-05 19/20 | Conduct bi-annual municipal data recovery | Corporate Services | Administration | Number of successful data recovery test reports by 30 June 2020 | Number | 2 Data recovery test reports by 30 June 2020 | 1 report submitted by 31 December 2019 | Achieved.1 Report submitted by 31 December 2019 | 1 report submitted by 31 December 2019 | Achieved.1 Reports submitted by 31 December 2019 | N/A | N/A | N/A | 400000 | Municipality | DCS-BUDG | Default | N/A | Data recovery reports | M | Manager: IT
[5 empty] | 6 | CS-06 19/20 | Ctrack System | Corporate Services | Administration | Number of monthly systeme generated reports by 30 June 2020 | Number | 12 Monthly C track systerm generated report by 30 June 2020 | 3reports submitted by 31 December 2019 | Achieved.3 Reports submitted by 31 December 2019 | 6 reports submitted by 31 December 2019 | Achieved.6 reports submitted by 31 December 2019 | N/A | N/A | N/A | n/A | Municipality | DCS-BUDG | Default | N/A | Ctrack system reports | M | Manager : Administration
[5 empty] | 7 | CS-07 19/20 | Implementation of Biometric System report | Corporate Services | Administration | Number of biometric system reporter implemented by 30 June 2020 | Number | 12 Biometric system reports presented by 30 June 2020 | 3 Biometric system reports presented by 31 December 2019 | Achieved.3 Reports submitted by 31 December 2019 | 6 Biometric system reports presented by 31 December 2019 | Achieved.6 Biometric system reports presented by 31 December 2019 | N/A | N/A | N/A |  | Municipality | DCS-BUDG | Default | N/A | Biometrics Reports | H | Manager: IT
[5 empty] | 8 | CS-08 19/20 | Community skills support programme | Corporate Services | Administration | Number of Interns and Inservice trainees recruited by 30 June 2020 | Number | 8 Interns and 6 Inservice trainees recruited by 30 June 2020 | 4 Interns appointed by 31 December 2019 | Not achieved. No intern appointed | 4 Interns appointed by 31 December 2019 | Not achieved. No intern appointed | Some Interns positions were already advertised and due for shortlisting and interviews | To conduct Recruitment processes on the third quarter | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Appointment Letters | M | Manager: Human Resource
[5 empty] | 9 | CS-09 19/20 | Management and co-ordination of meetings | Corporate Services | Administration | Number of approved schedule of meetings by 30 June 2020 | Number | 4 Corporate Staff meetings by 30 June 2020 | 1 Corporate Staff meeting by 31 December 2019 | Not achieved. | 2 Corporate Staff meeting by 31 December 2019 | Not achieved.1 Corporate Staff meeting held by 31 December 2019 | Clashes of dates regarding second meeting. | To be done in Quarter 3 | N/A |  | Municipality | DCS-BUDG | Default | N/A | Signed and approved schedule of meetings. Extracts from minutes | M | Manager: Administration
[5 empty] | 10 | CS-10 19/20 | Council support services | Corporate Services | Administration | Number of Council meetings held by 30 June 2020 | Number | 4 Council meetings by 30 June 2020 | 1 Council meeting by 31 December 2019 | Achieved.4 Council meeting by 31 December 2019 | 2 Council meeting by 31 December 2019 | Achieved.7 Council meeting by 31 December 2019 | N/A | N/A | N/A |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | 11 | CS-11 19/20 | Council support services | Corporate Services | Administration | Number of EXCO meetings held by 30 June 2020 | Number | 10 EXCO meetings by 30 June 2020 | 3 Exco meetings by 31 December 2019 | Achieved.3 Exco meetings by 31 December 2019 | 6 Exco meetings by 31 December 2019 | Achieved.6 Exco meetings by 31 December 2019 | N/A | N/A | N/A |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance register | H | Manager: Administration
[5 empty] | 12 | CS-12 19/20 | Drafting of Service Level Agreements (SLA) | Corporate Services | Administration | Number of SLA's drafted by 30 June 2020 | Number | 4 SLA's drafted by 30 June 2020 | 1 SLA drafted by 31 December 2019 | Achieved.1 SLA drafted by 31 December 2019 | 2 SLA drafted by 31 December 2019 | Achieved.2 SLA drafted by 31 December 2019 | N/A | N/A | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Copies of SLA's drafted & Register of signed SLA | H | Manager: Legal Services
[5 empty] | 13 | CS-13 19/20 | Training on Policies and Legislations | Corporate Services | Administration | Number of trainings provided for staff and councillors on Policies and Legislations by 30 June 2020 | Number | 8 Trainings conducted on Policies and Legislations by 30 June 2020 | 2 Traininings on Policies and Legislations by 31 December 2019 | Not achieved. 1 Traininings on Policies by 31 December 2019 | 4 Traininings on Policies and Legislations by 31 December 2019 | Not achieved. 3 Trainings on Policies and Legislations by 31 December 2019 | Due to the clashes of dates the | To be done in Quarter 3 | N/A |  | Municipality | DCS-BUDG | Default | N/A | Notices and attendance registers | M | Manager: Legal Services
[5 empty] | 14 | CS-14 19/20 | Policies reviewed | Corporate Services | Administration | Number of policies reviewed and developed by the 30 June 2020 | Number | 6 Policies reviewed and developed by 30 June 2020 | 2 Policies reviewed and developed by 31 December 2019 | Achieved.4 Policies reviewed and developed by 31 December 2019 | 2 Policies reviewed and developed by 31 December 2019 | Achieved.4 Policies reviewed and developed by 31 December 2019 | N/A | N/A | N/A | N/A | Municipality | DCS-BUDG | Default | N/A | Signed report on reviewed and developed policies | H | Manager: Legal Services